## Project List
Project Name | E-SRG or E-PWF | Status | Capacity (kW) | Expected GWh/yr | Technology | Price ($/MWh) | Vintage | Term (yrs) | Location | Execution Date | 18-month COD Deadline | Current GCOD** | Actual COD | Achieved COD with 18 months
Buckeye Hydroelectric Project | E-SRG | Online | 400 | 0-2.0 | Small Hydro | 92.71 | Existing | 20 | El Dorado County | 2008-06-02 | 2009-12-02 | N/A | 2008-08-15 | Yes
Tunnel Hill Hydroelectric Project | E-SRG | Online | 600 | 0-3.0 | Small Hydro | 96.96 | Existing | 20 | El Dorado County | 2008-06-02 | 2009-12-02 | N/A | 2009-05-22 | Yes
Castelanelli Bros. Biogas | E-SRG | Online | 300 | 0-1.3 | Digester Gas | 100.43 | Existing | 10 | Lodi | 2009-06-11 | 2010-12-11 | N/A | 2009-06-17 | Yes
Nevada Irrigation District (Combie North Powerhouse) | E-SRG | Online | 500 | 0-1.3 | Small Hydro | 105.37 | Existing | 15 | Grass Valley | 2009-05-28 | 2010-11-28 | N/A | 2009-10-06 | Yes
Snow Mountain Hydro,LLC (Lost Creek 1) | E-SRG | Online | 1100 | 0-5.5 | Small Hydro | 101.75 | Existing | 10 | Shasta County | 2009-12-18 | 2011-06-18 | N/A | 2010-01-01 | Yes
Snow Mountain Hydro, LLC (Lost Creek 2) | E-SRG | Online | 500 | 0-2.5 | Small Hydro | 101.75 | Existing | 10 | Shasta County | 2009-12-18 | 2011-06-18 | N/A | 2010-01-01 | Yes
Nevada Irrigation District (Combie South Powerhouse) | E-SRG | Online | 1500 | 0-3.9 | Small Hydro | 101.75 | Existing | 10 | Grass Valley | 2009-11-23 | 2011-05-23 | N/A | 2010-05-01 | Yes
Nevada Irrigation District (Scotts Flat Dam) | E-SRG | Online | 850 | 0-3.2 | Small Hydro | 84.48 | Existing | 10 | Nevada City | 2010-04-06 | 2011-10-06 | N/A | 2010-06-01 | Yes
Sierra Green Energy, LLC (SGE Site 1) | E-SRG | Online | 37.5 | 0-0.2 | Small Hydro | 113.9 | New | 20 | Grass Valley | 2009-12-24 | 2011-06-24 | N/A | 2010-06-24 | Yes
Santa Maria II | E-SRG | Online | 1420 | 0-6.2 | Landfill gas | 95.91 | New | 15 | Santa Barbara County | 2008-08-06 | 2010-02-06 | N/A | 2010-09-13 | No
Blake's Landing Farms, Inc. (80 kw Generator) | E-SRG | Online | 80 | 0-0.6 | Digester Gas | 84.48 | Existing | 10 | Marin County | 2010-09-24 | 2012-03-24 | N/A | 2010-11-02 | Yes
Vecino Vineyards LLC | E-SRG | Online | 330 | 0-0.1 | Small Hydro | 94.65 | Existing | 15 | Mendocino County | 2010-03-01 | 2011-09-01 | N/A | 2011-04-01 | Yes
Ortigalita Power Company LLC | E-SRG | Online | 750 | 0-5.6 | Biomass | 110.46 | New | 15 | Merced County | 2009-05-27 | 2010-11-27 | N/A | 2011-06-17 | No
San Jose Water Company (Cox Ave Hydro) | E-SRG | Online | 112 | 0-0.6 | Small Hydro | 100.98 | Existing | 20 | Santa Clara County | 2011-08-17 | 2013-02-17 | N/A | 2011-11-22 | Yes
South Sutter Water (Vanjop No. 1) | E-PWF | Online | 395 | 0-2.0 | Small Hydro | 95.43 | Existing | 10 | Placer County | 2011-12-23 | 2013-06-23 | N/A | 2012-01-24 | Yes
Twin Valley Hydro (T&G Hydro) | E-SRG | Online | 520 | 0-2.6 | Small Hydro | 121.26 | Existing | 20 | Whitmore | 2010-01-26 | 2011-07-26 | N/A | 2012-01-17 | No
Calaveras Public Utility Disctrict (Calaveras Hydro #1) | E-PWF | Online | 90 | 0-0.4 | Small Hydro | 89.56 | Existing | 20 | Calaveras County | 2012-03-09 | 2013-09-09 | N/A | 2012-04-01 | Yes
Calaveras Public Utility Disctrict (Calaveras Hydro #2) | E-PWF | Online | 90 | 0-0.4 | Small Hydro | 89.56 | Existing | 20 | Calaveras County | 2012-03-09 | 2013-09-09 | N/A | 2012-04-01 | Yes
Calaveras Public Utility Disctrict (Calaveras Hydro #3) | E-PWF | Online | 90 | 0-0.4 | Small Hydro | 89.56 | Existing | 20 | Calaveras County | 2012-03-08 | 2013-09-08 | N/A | 2012-04-01 | Yes
Jackson Valley Irrigation District (Jackson Valley Hydo) | E-PWF | Online | 455 | 0-2.3 | Small Hydro | 89.56 | Existing | 20 | Amador County | 2012-03-28 | 2013-09-28 | N/A | 2012-04-01 | Yes
American Energy, Inc. (Wolfsen Bypass) | E-SRG | Online | 980 | 0-4.9 | Small Hydro | 92.08 | Existing | 10 | Merced | 2011-10-10 | 2013-04-11 | N/A | 2012-05-01 | Yes
American Energy, Inc. (San Luis Bypass) | E-SRG | Online | 600 | 0-3.0 | Small Hydro | 92.08 | Existing | 10 | Merced | 2011-10-10 | 2013-04-11 | N/A | 2012-05-01 | Yes
Browns Valley Irrigation District (Virginia Ranch Dam) | E-PWF | Online | 1040 | 0-5.2 | Small Hydro | 76.88 | Existing | 10 | Yuba County | 2012-03-22 | 2013-09-22 | N/A | 2012-04-12 | Yes
NHL1 Solar, LLC (Nickel 1) | E-SRG | Online | 1500 | 0-2.1 | Solar PV | 105.07 | New | 20 | Kern County | 2011-07-15 | 2013-01-15 | N/A | 2012-11-28 | Yes
GASNA 16P, LLC (La Joya Del Sol #1) | E-SRG | Online | 1500 | 0-2.1 | Solar PV | 105.07 | New | 20 | Frenso County | 2011-02-24 | 2012-08-24 | N/A | 2012-12-24 | No
Hayworth-Fabian LLC (Oakley Executive - Solar) | E-SRG | Online | 1500 | 0-2.1 | Solar PV | 108.98 | New | 20 | Contra Costa County | 2011-09-26 | 2013-03-26 | N/A | 2013-06-12 | No
Yolo County (Grassland 3) | E-PWF | Online | 1000 | 0-1.4 | Solar PV | 93.75 | New | 20 | Yolo County | 2012-08-20 | 2014-02-20 | N/A | 2013-07-01 | Yes
Yolo County (Grassland 4) | E-PWF | Online | 1000 | 0-1.4 | Solar PV | 93.75 | New | 20 | Yolo County | 2012-08-20 | 2014-02-20 | N/A | 2013-07-01 | Yes
Pristine Sun Mosaic LLC (2065_Rogers) | E-SRG | Online | 250 | 0-0.7 | Solar PV | 108.98 | New | 20 | Tehama County | 2011-08-17 | 2013-02-17 | N/A | 2013-07-12 | No
Toro Energy of California - SLO, LLC (Toro SLO Landfill) | E-SRG | Online | 1500 | 0-11.2 | Landfill gas | 108.98 | New | 20 | San Luis Obispo County | 2011-08-31 | 2013-03-03 | N/A | 2013-07-21 | No
Pristine Mosaic, LLC (2158_Stroing) | E-SRG | Online | 750 | 0-1.1 | Solar PV | 112.86 | New | 20 | Tehama County | 2011-08-31 | 2013-03-03 | 2014-03-03 | 2013-10-02 | No
Tulare PV II LLC (Kingsburg 1) | E-SRG | Online | 1500 | 0-2.1 | Solar PV | 112.86 | New | 20 | Tulare County | 2011-10-10 | 2013-04-11 | 2014-04-11 | 2013-12-30 | No
Tulare PV II LLC (Kingsburg 2) | E-SRG | Online | 1500 | 0-2.1 | Solar PV | 112.86 | New | 20 | Tulare County | 2011-10-10 | 2013-04-11 | 2014-04-11 | 2013-12-30 | No
Tulare PV II LLC (Kingsburg 3) | E-SRG | Online | 750 | 0-1.1 | Solar PV | 112.86 | New | 20 | Tulare County | 2011-10-10 | 2013-04-11 | 2014-04-11 | 2013-12-30 | No
Fresh Air Energy IV, LLC (Sonora 1) | E-SRG | Online | 1500 | 0-1.4 | Solar PV | 112.86 | New | 20 | Tuolumne County | 2011-07-15 | 2013-01-15 | 2014-01-15 | 2013-12-31 | No
Pristine Sun Mosaic, LLC (2179_Smotherman) | E-SRG | Online | 250 | 0-0.7 | Solar PV | 112.86 | New | 20 | Sutter County | 2011-08-31 | 2013-03-03 | 2014-03-03 | 2014-01-01 | No
Bear Creek Solar , LLC (Bear Creek Solar Project) | E-SRG | Online | 1500 | 0-2.1 | Solar PV | 112.86 | New | 20 | San Joaquin County | 2011-08-31 | 2013-03-03 | 2014-03-03 | 2014-02-05 | No
Pristine Sun Fund 5, LLC (2102_Christensen) | E-SRG | Online | 999 | 0-1.4 | Solar PV | 112.86 | New | 20 | Fresno County | 2011-08-17 | 2013-02-17 | 2014-02-17 | 2014-02-07 | No
Pristine Sun Fund 5 LLC (2041_Alvares) | E-SRG | Online | 250 | 0-0.4 | Solar PV | 112.86 | New | 20 | Tehama County | 2011-08-31 | 2013-03-03 | 2014-03-03 | 2014-02-10 | No
Pristine Sun Fund 5, LLC (2103_Hill) | E-SRG | Online | 750 | 0-1.1 | Solar PV | 112.86 | New | 20 | San Luis Obispo County | 2011-08-31 | 2013-03-03 | 2014-03-03 | 2014-02-20 | No
Pristine Sun Fund 5, LLC (2096_Cotton) | E-SRG | Online | 999 | 0-1.4 | Solar PV | 112.86 | New | 20 | Butte County | 2011-08-31 | 2013-03-03 | 2014-03-03 | 2014-03-03 | No
Pristine Sun Fund 5, LLC (2056_Jardine) | E-SRG | Online | 999 | 0-1.4 | Solar PV | 112.86 | New | 20 | San Luis Obispo County | 2011-08-31 | 2013-03-03 | 2014-03-03 | 2014-03-03 | No
Pristine Sun Fund 5, LLC (2059_Scherz) | E-SRG | Online | 500 | 0-1.1 | Solar PV | 112.86 | New | 20 | San Luis Obispo County | 2011-08-31 | 2013-03-03 | 2014-03-03 | 2014-03-03 | No
Ignite Solar LLC (Achomawi) | E-SRG | Online | 1500 | 0-2.1 | Solar PV | 112.86 | New | 20 | Shasta County | 2011-09-26 | 2013-03-26 | 2014-03-26 | 2014-03-05 | No
Ignite Solar LLC (Ahjumawi) | E-SRG | Online | 1500 | 0-2.1 | Solar PV | 112.86 | New | 20 | Shasta County | 2011-09-26 | 2013-03-26 | 2014-03-26 | 2014-03-05 | No
Pristine Sun Fund 5, LLC (2094_Buzzelle) | E-SRG | Online | 999 | 0-1.8 | Solar PV | 112.86 | New | 20 | Butte County | 2011-08-31 | 2013-03-03 | 2014-03-03 | 2014-03-06 | No
Vintner Solar , LLC (Vintner Solar Project) | E-SRG | Online | 1500 | 0-2.1 | Solar PV | 112.86 | New | 20 | San Luis Obispo County | 2011-10-10 | 2013-04-11 | 2014-04-11 | 2014-03-06 | No
Kettleman Solar, LLC (Kettleman Solar Project) | E-SRG | Online | 1000 | 0-1.4 | Solar PV | 112.86 | New | 20 | San Joaquin County | 2011-10-10 | 2013-04-11 | 2014-04-11 | 2014-03-14 | No
Pristine Sun Fund 5, LLC (2081_Terzian) | E-SRG | Online | 1250 | 0-1.8 | Solar PV | 112.86 | New | 20 | Fresno County | 2011-08-17 | 2013-02-17 | 2014-02-17 | 2014-06-17 | No
Enerparc CA1, LLC (San Benito Smart Park) | E-SRG | Online | 1499 | 0-2.1 | Solar PV | 112.86 | New | 20 | San Benito County | 2011-09-26 | 2013-03-26 | 2014-03-26 | 2014-06-16 | No
Cloverdale Solar 1, LLC (FSEC1) | E-SRG | Online | 1500 | 0-2.1 | Solar PV | 108.98 | New | 20 | Sonoma County | 2011-12-23 | 2013-06-23 | 2014-06-23 | 2014-06-26 | No
Pristine Sun Fund 5 LLC (2113_Fritzjarrell) | E-SRG | Online | 999 | 0-1.4 | Solar PV | 112.86 | New | 20 | Shasta County | 2011-08-17 | 2013-02-17 | 2014-02-17 | 2014-06-27 | No
Pristine Sun Fund 5, LLC (2125_Jarvis) | E-SRG | Online | 999 | 0-1.4 | Solar PV | 112.86 | New | 20 | Butte County | 2011-08-31 | 2013-03-03 | 2014-03-03 | 2014-06-27 | No
Pristine Sun Fund 5, LLC (2127_Harris) | E-SRG | Online | 1250 | 0-1.8 | Solar PV | 112.86 | New | 20 | Sutter County | 2011-08-31 | 2013-03-03 | 2014-03-03 | 2014-12-02 | No
WGL Energy Systems Inc. (Apex 646-460) | E-SRG | Online | 750 | 0-1.1 | Solar PV | 101.32 | New | 20 | Tulare County | 2013-04-24 | 2014-10-24 | 2015-04-24 | 2015-01-14 | No
Hollister Solar LLC (Hollister Project) | E-SRG | Online | 1500 | 0-2.1 | Solar PV | 101.32 | New | 20 | San Benito County | 2012-10-25 | 2014-04-25 | 2015-04-25 | 2015-04-17 | No
Pristine Sun Fund 5, LLC (2097_Helton) | E-SRG | Online | 1500 | 0-2.1 | Solar PV | 112.86 | New | 20 | Merced County | 2011-08-17 | 2013-02-17 | 2014-02-17 | 2015-04-30 | No
Merced Solar LLC (Merced Solar Project) | E-SRG | Online | 1500 | 0-2.1 | Solar PV | 101.32 | New | 20 | Merced County | 2012-11-21 | 2014-05-21 | 2015-05-21 | 2015-05-12 | No
Mission Solar LLC (Mission Solar Project) | E-SRG | Online | 1500 | 0-2.1 | Solar PV | 101.32 | New | 20 | Merced County | 2013-01-07 | 2014-07-07 | 2015-07-07 | 2015-05-23 | No
Bakersfield III, LLC (Bakersfield III) | E-SRG | Online | 1400 | 0-2.0 | Solar PV | 101.32 | New | 20 | Kern County | 2013-08-01 | 2015-02-01 | 2015-08-01 | 2015-07-28 | No
Placer County Water Agency (Lincoln Metering and Hydroelectric Station) | E-PWF | Online | 320 | 0-1.6 | Small Hydro | 101.32 | New | 20 | Placer County | 2013-06-20 | 2014-12-20 | 2015-06-20 | 2015-09-25 | No
Fresno Cogeneration Partners, L.P. (Fresno Solar South) | E-SRG | Online | 1500 | 0-2.1 | Solar PV | 101.32 | New | 20 | Fresno County | 2013-04-24 | 2014-10-24 | 2015-10-24 | 2015-10-20 | No
Fresno Cogeneration Partners, L.P. (Fresno Solar West | E-SRG | Online | 1500 | 0-2.1 | Solar PV | 101.32 | New | 20 | Fresno County | 2013-04-24 | 2014-10-24 | 2015-10-24 | 2015-10-20 | No
GL Sirius, LLC (Sirius Solar Project) | E-SRG | Online | 999 | 0-2.1 | Solar PV | 101.32 | New | 20 | Merced County | 2013-04-24 | 2014-10-24 | 2015-10-24 | 2015-10-22 | No
Green Light FIT 1, LLC ( Castor Solar Project) | E-SRG | Online | 1500 | 0-2.1 | Solar PV | 105.09 | New | 20 | Kern County | 2013-06-20 | 2014-12-20 | 2015-12-20 | 2016-04-07 | No
Green Light Energy Corp. (Peacock Solar Project) | E-SRG | Online | 999 | 0-2.1 | Solar PV | 105.09 | New | 20 | Fresno County | 2013-07-22 | 2015-01-22 | 2016-01-22 | 2016-02-01 | No
Lemoore PV 1, LLC (Lemoore 1) | E-SRG | Online | 1500 | 0-2.1 | Solar PV | 105.09 | New | 20 | Kings County | 2013-08-01 | 2015-02-01 | 2016-02-01 | 2016-02-01 | No
Oroville Solar, LLC (2192 Ramirez) | E-SRG | Online | 500 | 0-0.7 | Solar PV | 105.09 | New | 20 | Tehama County | 2013-08-01 | 2015-02-01 | 2016-02-01 | 2016-02-11 | No
Pristine Sun Fund 6, LLC (2154 Foote) | E-SRG | Online | 250 | 0-0.4 | Solar PV | 105.09 | New | 20 | Butte County | 2013-08-01 | 2015-02-01 | 2016-02-01 | 2016-12-19 | No
Total Subscription (MW) | [12 empty] | Key
E-PWF: | 4.48 | [11 empty] | Online
E-SRG: | 59.9705 | [11 empty] | E-PWF
Total: | 64.4505
* For online projects, price is based on first deliveries; for projects not yet online, price estimate is based on Current GCOD.
** Projects may have been deemed eligible for extensions of the 18-month deadline for Commercial Operation (the “Guaranteed Commercial Operation Date” or “GCOD”).
Please see the AB 1969 Extension/Termination Policy posted on the FIT webpage for details: www.pge.com/feedintariffs
AB 1969 Extension/Termination Policy