## Overview & Instructions
Step 1: Enter the following information for the GRC and current WMP cycle.
Data Element | Year
WMP Year 1 | 2023
WMP Year 2 | 2024
WMP Year 3 | 2025
Last GRC Test Year | 2023
Next GRC Test Year | 2027
Step 2: Enter information for mitigation initiatives in the "General Info (1 of 5)" tab. This should include all mitigation initiatives and all instances where there is a 1:many relationship between the WMP Tracking ID and the GRC MAT code.
Step 3: Succesful completion of Step 2 will transfer the "Mitigation Initiative Cost Reporting Identification Code " to the subsequent tabs ("HFTD, CapEx (2 of 5)", etc.) and allow for data to be entered by category (HFTD/non-HFTD, CapEx/OpEx).
Step 4: Enter all costs (in thousands of dollars) and unit data for each "Mitigation Initiative Cost Reporting Identification Code ". For any comments, use the comments tab in the relevant tab.
For detailed instructions regarding the above tabs [General Info (1 of 5); HFTD, CapEx (2 of 5); etc.] see Guidance for WMP Cost Reporting.doc
For detailed instructions regarding the Account Tracking tab see Guidance for Accounts Tracking.doc

## General Info (1 of 5)
| 2023-2025 WMP Information | [7 empty] | GRC Activity (e.g., MAT code, Work Breakdown Structure, Cost Center)
Mitigation Initiative Cost Reporting Identification Code | Utility Initiative Tracking ID | WMP Mitigation Initiative Title | WMP Mitigation Initiative Description | WMP Mitigation Initiative Category | Type of Units (e.g., miles, # of inspections, # of poles repaired/replaced, etc.) | WMP File Location (URL) | TEMPORARY TO BE REMOVED BEFORE SUBMISSION Capital / Expense / Both | TEMPORARY TO BE REMOVED BEFORE SUBMISSION Tranche Schedule | Cost requested in original GRC Application ($000s) | GRC Activity Title | GRC Activity Unique Code (MAT, WBS, Budget Code/Cost Center) | GRC Activity Description | GRC Activity Section and Page Number | GRC Appendix | GRC File Location (URL) | Recorded Costs Above GRC Authorization ($) | Cost-Benefit Ratio (CBR) ($) | Risk Spend Efficiency (RSE) Calculation | Comments
AI-01 | AI-01 | Retainment of Inspectors and Internal Workforce Development | 1. Develop a plan to increase retention over time for trained and qualified inspectors. 2. Develop a plan to focus on increasing and sustaining a consistent, year-over-year internal workforce that builds on existing experience and mentors new employees for asset inspections. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives, p. 289 | Grid Design Ops Maintenance | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense
AI-02 | AI-02 | Detailed Inspection Transmission – Ground | 2023: Complete detailed ground inspections on 27,000 transmission structures in PG&E’s asset registry as of January 1, 2023. 2024: Complete detailed ground inspections on approximately 20,000 transmission structures in PG&E’s asset registry as of January 1, 2024. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in accordance with Section 12.3 of the 2023-2025 WMP Process and Evaluation Guidelines. 2025: Complete detailed ground inspections on approximately 22,000 transmission structures in PG&E’s asset registry as of January 1, 2025. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in 2024 as part of the 2025 WMP Annual Update. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 336 | Grid Design Ops Maintenance | # of transmission structures | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense
AI-03 | AI-03 | Develop Distribution Aerial Inspections program | Evaluate the continued use of aerial inspections for distribution overhead equipment. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 289 | Grid Design Ops Maintenance | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense
AI-04 | AI-04 | Detailed Inspection Transmission – Aerial | 2023: Complete detailed aerial inspections on 24,000 transmission structures in PG&E’s asset registry as of January 1, 2023. 2024: Complete detailed aerial inspections on approximately 20,000 transmission structures in PG&E’s asset registry as of January 1, 2024. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in accordance with Section 12.3 of the 2023-2025 WMP Process and Evaluation Guidelines. 2025: Complete detailed aerial inspections on approximately 19,000 transmission structures in PG&E’s asset registry as of January 1, 2025. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in 2024 as part of the 2025 WMP Annual Update. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 336 | Grid Design Ops Maintenance | # of transmission structures | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense
AI-05N/A | AI-05 | Detailed Inspection Transmission – Climbing | 2023: Complete detailed climbing inspections of 1,700 transmission structures in PG&E’s asset registry as of January 1, 2023. 2024: Complete detailed climbing inspections on approximately 1,200 transmission structures in PG&E’s asset registry as of January 1, 2024. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in accordance with Section 12.3 of the 2023-2025 WMP Process and Evaluation Guidelines. 2025: Complete detailed climbing inspections on approximately 1,200 transmission structures in PG&E’s asset registry as of January 1, 2025. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in 2024 as part of the 2025 WMP Annual Update. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 337 | Grid Design Ops Maintenance | # of transmission structures | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense |  | N/A | N/A
AI-06N/A | AI-06 | Perform transmission IR inspections | 2023: Infrared patrols will be performed on 4,000 circuit miles of energized transmission line. 2024: Infrared patrols will be performed on 4,000 circuit miles of energized transmission line. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in accordance with Section 12.3 of the 2023 -2025 WMP Process and Evaluation Guidelines. 2025: Infrared patrols will be performed on 3,500 circuit miles of energized transmission line. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in 2024 as part of the 2025 WMP Annual Update. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 336 | Grid Design Ops Maintenance | # of miles | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense |  | N/A | N/A
AI-07Overhead Inspections - WLDFR-C01A | AI-07 | Detailed Ground and Aerial Inspections - Distribution | 2023: Complete detailed ground inspections on 234,648 distribution poles, which were identified in PG&E's asset registry as of December 27, 2022. As part of the target number above, detailed ground inspections will be completed on a 42,470-pole subset of distribution poles in Severe, Extreme, or High plat maps by July 31, 2023, which were identified in PG&E's asset registry as of December 27, 2022. Similarly, detailed ground inspections will be completed on a 30,062-pole subset of distribution poles in Medium plat maps by September 30, 2023, which were identified in PG&E's asset registry as of December 27, 2022. Lastly, detailed ground inspections will be completed on a 162,116-pole subset of distribution poles in Low plat maps by December 31, 2023, which were identified in PG&E's asset registry as of December 27, 2022. 2024: Complete detailed inspections on approximately 220,016 distribution poles, which will be identified in PG&E's asset registry as of December 27, 2022. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E's asset registry and updated in accordance with Section 12.3 of the 2023-2025 WMP Process and Evaluation Guidelines. 2025: Complete detailed inspections on approximately 244,000 distribution poles, which will be identified in PG&E's asset registry as of December 27, 2022. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E's asset registry and updated in 2024 as part of the 2025 WMP Annual Update. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 338 | Grid Design Ops Maintenance | # of distribution poles | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense |  | 69900.2173 | Overhead Inspections - WLDFR-C01A | BFB
AI-08 | AI-08 | Supplemental Inspections - Substation Distribution | 2023: Complete supplemental inspections on 52 distribution substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2024: Complete supplemental inspections on 76 distribution substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2025: Complete supplemental inspections on 78 distribution substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 339 | Grid Design Ops Maintenance | # of distribution substations | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1
AI-09N/A | AI-09 | Supplemental Inspections - Substation Transmission | 2023: Complete supplemental inspections on 34 transmission substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2024: Complete supplemental inspections on 36 transmission substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2025: Complete supplemental inspections on 41 transmission substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 339 | Grid Design Ops Maintenance | # of transmission substations | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1 | N/A | N/A
AI-10 | AI-10 | Supplemental Inspections - Hydroelectric Substations and Powerhouses | 2023: Complete supplemental inspections on 41 Hydroelectric Generation Substations and Powerhouses. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2024: Complete supplemental inspections on 46 Hydroelectric Generation Substations and Powerhouses. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2025: Complete supplemental inspections on 40 Hydroelectric Generation Substations and Powerhouses. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 339 | Grid Design Ops Maintenance | # of hydroelectric substations and powerhouses | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1 | 0
AI-11N/A | AI-11 | Filling Asset Inventory Data Gaps | Populate missing age data in the Asset Registry (using “Installation Date” data element as a proxy) to 90 percent weighted average across risk prioritized distribution and transmission equipment. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 290 | Grid Design Ops Maintenance | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1 | 0 | N/A | N/A
CO-01 | CO-01 | Community Engagement - Meetings | For 2023-2025, PG&E will hold annually a total of 22 community engagement meetings within the five regions of service that will include, but are not limited to, a mix of webinars, open houses, town halls, and/or answer centers. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1 PG&E's WMP Objectives p. 297 | Community Outreach | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 3
CO-02 | CO-02 | Community Engagement - Surveys | PG&E will complete two PSPS education and outreach surveys (per year, for a total of six). 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2 PG&E's WMP Targets p. 348 | Community Outreach | # of surveys | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 3
CO-04 | CO-04 | Community Engagement - Outreach to HFRA Infrastructure Customers | PG&E will perform outreach via email and/or phone to assigned Critical Infrastructure customers in the HFRA through Business Energy Solutions (assigned account managers). Outreach will cover the CWSP, including potential PSPS and EPSS impacts, and updating contact information for critical accounts in the HFRA. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1 PG&E's WMP Objectives p. 298 | Community Outreach | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 3
CO-05 | CO-05 | Community Engagement - Outage Preparedness Campaign | PG&E will also conduct at least one direct-to-customer outage preparedness campaign annually via email and/or direct mail targeting residential customers in the PSPS more likely or EPSS program scope. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1 PG&E's WMP Objectives p. 298 | Community Outreach | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 3
EP-01 | EP-01 | Complete PSPS and Wildfire Tabletop and Functional Exercises | Complete PSPS and Wildfire Tabletop and Functional Exercise annually in compliance with the guiding principles of the Homeland Security Exercise Evaluation Program (HSEEP). 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 296 | Emergency Preparedness | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 3
EP-02 | EP-02 | Maintain All Hazards planning and preparedness program | Maintain the All Hazards Planning and Preparedness Program to provide emergency response and safely and expeditiously restore service. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 296 | Emergency Preparedness | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 3
EP-04 | EP-04 | Expand All Hazards planning to include additional threats and scenarios | Expand the All Hazards Planning and Preparedness Program to include additional threats and scenarios. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 296 | Emergency Preparedness | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 3
EP-06 | EP-06 | Annually review of the Company Emergency Response Plan (CERP) and Wildfire and PSPS Annex | 3 documents (1 CERP and 2 wildfire-related annexes) (per year) 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 348 | Emergency Preparedness | # of CERPs and wildfire annexes | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 3
EP-07 | EP-07 | Common Operating Picture Technology | Design and deploy a common operating picture. A common operation picture (COP) is a continuously updated overview of an incident compiled throughout an incident’s life cycle from data shared between integrated communication, information management, and intelligence and information sharing systems. The goal of a COP is real-time situational awareness across all levels of incident management and across jurisdictions. https://www.dhs.gov/publication/common-operating-picture-emergency-responders 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 297 | Emergency Preparedness | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 3
EP-08 | EP-08 | Threats and Hazards Identification and Risk Assessment (THIRA) updates executive briefings. | Execute a Threats and Hazards Identification and Risk Assessment (THIRA) update every three years to address changes in hazard landscape. Use information from THIRA to inform changes to the CERP and hazard annexes. According to FEMA, The THIRA is a three-step risk assessment process that helps communities understand their risks and what they need to do to address those risks. https://www.fema.gov/emergency-managers/national-preparedness/goal/risk-capability-assessment#:~:text=The%20Threat%20and%20Hazard%20Identification,hazards%20can%20affect%20our%20community%3F 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 297 | Emergency Preparedness | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 3
EP-09 | EP-09 | County Execute Briefings | Hold briefings with 47 counties within PG&E’s service territory after every THIRA update to support integrated planning discussions. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 297 | Emergency Preparedness | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 3
GH-01 | GH-01 | System Hardening - Distribution | 2023: Complete 420 circuit miles of system hardening work which includes overhead system hardening, undergrounding, and removal of overhead lines in HFTD, HFRA, or buffer zone areas, except for any mileage being undergrounded and tracked separately as part of our Butte County Rebuild and other Community Rebuild efforts. 2024: Complete 280 circuit miles of system hardening work which includes overhead system hardening, undergrounding, and removal of overhead lines in HFTD, HFRA, or buffer zone areas, except for any mileage being undergrounded and tracked separately as part of our Butte County Rebuild and other Community Rebuild efforts. 2025: Complete 520 circuit miles of system hardening work which includes overhead system hardening, undergrounding, and removal of overhead lines in HFTD, HFRA, or buffer zone areas except for any mileage being undergrounded and tracked separately as part of our Butte County Rebuild and other Community Rebuild efforts. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 334 | Grid Design Ops Maintenance | # of circuit miles | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Both | Tranche 1
GH-02 | GH-02 | Evaluate Covered Conductor Effectiveness | Update the covered conductor recorded effectiveness calculation using 2023 and 2024 outage data on the lines that have Covered Conductors for consideration in future system hardening workplans. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 289 | Grid Design Ops Maintenance | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1
GH-03 | GH-03 | Evaluate and Implement Covered Conductor Effectiveness Impact on Inspections and Maintenance Standards | Evaluate the output of the Phase 1 and Phase 2 covered conductor effectiveness study to: (1) determine the impacts of the study on the maintenance and inspections standards for deployed covered conductor assets; and (2) update TD-2305M-JA02 (overhead inspections job aid), as needed. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 289 | Grid Design Ops Maintenance | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1
GH-04 | GH-04 | 10K Undergrounding | 2023: Complete 350 circuit miles of undergrounding work. The 350-circuit mile target includes: (1) undergrounding taking place as part of System Hardening, (2) undergrounding taking place as part of the Butte County Rebuild program (including a small volume of previously hardened overhead lines that are being placed underground) or other Community Rebuild programs, and (3) any other undergrounding work performed in HFTD, HFRA, Buffer Zone, or fire rebuild areas. 2024: Complete 250 circuit miles of undergrounding work. The 250-circuit mile target includes: (1) undergrounding taking place as part of System Hardening, (2) undergrounding taking place as part of the Butte County Rebuild program (including a small volume of previously hardened overhead lines that are being placed underground) or other Community Rebuild programs, and (3) any other undergrounding work performed in HFTD, HFRA, Buffer Zone, or fire rebuild areas. 2025: Complete 330 circuit miles of undergrounding work. The 330-circuit mile target includes: (1) undergrounding taking place as part of System Hardening, (2) undergrounding taking place as part of the Butte County Rebuild program (including a small volume of previously hardened overhead lines that are being placed underground) or other Community Rebuild programs, and (3) any other undergrounding work performed in HFTD, HFRA, Buffer Zone, or fire rebuild areas. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 334 | Grid Design Ops Maintenance | # of circuit miles | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Capital | Tranche 1
GH-05 | GH-05 | System Hardening - Transmission | 2023: Remove or replace 43 circuit miles of transmission conductor on lines. 2024: N/A 2025: Remove or replace 5 circuit miles of transmission conductor. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 334 | Grid Design Ops Maintenance | # of circuit miles | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Capital | Tranche 1
GH-06 | GH-06 | System Hardening - Transmission Shunt Splices | 2023: Install shunt splice(s) on 20 transmission lines. 2024: Install shunt splice(s) on 22 transmission lines. 2025: Install shunt splice(s) on 25 transmission lines. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 335 | Grid Design Ops Maintenance | # of transmission lines | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Capital | Tranche 1
GH-07 | GH-07 | Distribution Protective Devices | 2023: Install and SCADA commission 75 new SCADA protective devices (Line Recloser, Fuse Saver, or Interrupter). 2024: N/A 2025: N/A 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 335 | Grid Design Ops Maintenance | # of distribution sectionalizing devices | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Capital | Tranche 1
GH-08 | GH-08 | Surge Arrestor - Removals | 2023: Remove 663 non-exempt surge arrestors (based on the known population as of 01/12/2023) where known grounding issues exist. If no non-exempt surge arrestor is identified at a location during pre-field work, the unit will be resolved, and the notification will be canceled. Canceled notifications will count towards this target. 2024: N/A 2025: N/A 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 335 | Grid Design Ops Maintenance | # of surge arrestors | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Capital | Tranche 1
GH-09 | GH-09 | Distribution Line Motor Switch Operator (MSO) - Replacements | 2023: Replace or remove 20 MSOs (from the 47 identified as of January 26, 2023). 2024: Replace or remove the remaining MSOs from the 47 identified, as of January 26, 2023. 2025: N/A 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 335 | Grid Design Ops Maintenance | # of mso replacements | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Capital | Tranche 1
GH-10 | GH-10 | Non-Exempt Expulsion Fuse - Removal | 2023: Remove non-exempt expulsion fuses/ cutouts from 3,000 fuse locations identified on distribution poles. 2024: Remove non-exempt expulsion fuses/ cutouts from 3,000 fuse locations identified on distribution poles. 2025: Remove non-exempt expulsion fuses/ cutouts from approximately 1,400 fuse locations (based on known population as of 1/26/23) identified on distribution poles. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 335 | Grid Design Ops Maintenance | # of fuses | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Capital | Tranche 1
GH-11 | GH-11 | System Hardening – Transmission Conductor Segment Replacement | 2023: N/A 2024: N/A 2025: Replace conductor segments on 2 transmission lines 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 335 | Grid Design Ops Maintenance | # of transmission lines | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Capital | Tranche 1
GM-01 | GM-01 | Asset Inspections - Quality Assurance | 2023: Perform system inspection QA audits on QC completed locations and achieve the associated quality pass rates for each asset inspection program as specified below: Transmission Ground Inspection - HFTD/HFRA (Field): 500 audit locations*; 92% pass rate Distribution Ground Inspections - HFTD/HFRA (Field): 1,500 audit locations*; 82% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. 2024: Perform system inspection QA audits on QC completed locations and achieve the associated quality pass rates for each asset inspection program as specified below: Transmission Inspection - HFTD/HFRA: 500 audit locations*; 94% pass rate Distribution Inspections - HFTD/HFRA: 1,500 audit locations*; 90% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. 2025: Perform system inspection QA audits on QC completed locations and achieve the associated quality pass rates for each asset inspection program as specified below: Transmission Ground Inspection - HFTD/HFRA (Field): 500 audit locations*; 95% pass rate Distribution Ground Inspections - HFTD/HFRA (Field): 1,500 audit locations*; 95% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. | Grid Design Ops Maintenance | % pass rate and # of audit locations | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1
GM-02N/A | GM-02 | HFTD/HFRA Open Tag Reduction - Transmission | PG&E will eliminate the known 16,831 HFTD and HFRA transmission Ignition Risk tags (tags found prior to January 1, 2023, with required end dates in 2023 or earlier). | Grid Design Ops Maintenance | # of transmission LC tags | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1 |  | N/A
GM-03 | GM-03 | HFTD/HFRA Open Tag Reduction - Distribution Backlog | 2023: Close 52,000 distribution EC notifications, which at a minimum 29,000 are distribution backlog ignition risk EC notifications. Backlog is defined as the open ignition EC notifications known as of January 5, 2023, and found prior to Jan 1, 2023, in HFTD/HFRA locations. 2024: Close at least 25,000 additional EC notifications on top of closing an equivalent number of EC notifications created in HFRA/HFTD locations in 2024. Based on the forecasted amount of new EC notifications, we expect a total forecasted execution plan of 89,000 EC notifications for 2024. Of these EC notifications, we expect to close 46,000 distribution backlog ignition risk EC notifications with the remaining balance to be from backlog or newly identified EC notifications. 2025: Close at least 25,000 additional EC notifications on top of closing an equivalent number of EC notifications created in HFRA/HFTD locations in 2025. Based on the forecasted amount of new EC notifications, we expect a total forecasted execution plan of 92,000 EC notifications for 2025. Of these EC notifications, we expect to close 63,747 distribution backlog ignition risk EC notifications with the remaining balance to be from backlog or newly identified EC notifications. | Grid Design Ops Maintenance | # of distribution EC tags | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1
GM-06N/A | GM-06 | EPSS - Down Conductor Detection (DCD) | 2023: Make capable for DCD 500 protective device controllers or relays. This count includes protection devices that due to repair status cannot receive the DCD settings, and circuit reconfiguration resulting in descoping of device. 2024: Make capable for DCD 400 protective device controllers or relays. This count includes protection devices that due to repair status cannot receive the DCD settings, and circuit reconfiguration resulting in descoping of device. 2025: Make capable for DCD 250 protective device controllers or relays. This count includes protection devices that due to repair status cannot receive the DCD settings, and circuit reconfiguration resulting in descoping of device. | Grid Design Ops Maintenance | # of protective device controllers or relays | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Capital | Tranche 1 | 0 | N/A | N/A
GM-07N/A | GM-07 | Updates on EPSS Reliability Study | Provide annually an updated EPSS reliability impact study per ACI PG&E-22-32 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 290 | Grid Design Ops Maintenance | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1 | 0 | N/A | N/A
GM-08 | GM-08 | Eliminate HFTD/HFRA Distribution Backlog | Eliminate PG&E’s HFTD/HFRA EC notifications distribution backlog* by 2029 and have all HFTD/HFRA EC notifications in compliance with GO 95 Rule 18 barring External Factors. Backlog is defined as the open ignition EC notifications known as of January 5, 2023, and found prior to Jan 1, 2023, in HFTD/HFRA locations | Grid Design Ops Maintenance | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1
GM-09N/A | GM-09 | Asset Inspection – Quality Control | 2023: Perform system inspection QC audits and achieve the associated quality pass rates for each asset inspection program as specified below: System Inspection Transmission - HFTD (Desktop): 20,000 audit locations*; 90% pass rate System Inspection Transmission – HFTD (Field): 1,800 audit locations*; 90% pass rate System Inspection Distribution – HFTD (Desktop): 140,000 audit locations*; 80% pass rate System Inspection Distribution – HFTD (Field): 30,000 audit locations*; 80% pass rate 2024: Perform system inspection QC audits and achieve the associated quality pass rates for each asset inspection program as specified below: System Inspection Transmission - HFTD: 16,300 audit locations*; 92% pass rate System Inspection Distribution – HFTD: 170,000 audit locations*; 88% pass rate. 2025: Perform system inspection QC audits and achieve the associated quality pass rates for each asset inspection program as specified below: System Inspection Transmission - HFTD (Desktop): 16,000 audit locations*; 95% pass rate System Inspection Transmission – HFTD (Field): 1,450 audit locations*; 95% pass rate System Inspection Distribution – HFTD (Desktop): 140,000 audit locations*; 95% pass rate System Inspection Distribution – HFTD (Field): 30,000 audit locations*; 95% pass rate | Grid Design Ops Maintenance | % pass rate and # of audit locations | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1 |  | N/A
PS-01 | PS-01 | Evaluate enhancements for the PSPS Transmission guidance | Evaluate enhancements for the PSPS Transmission guidance to enhance focus of PSPS events. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 298 | PSPS | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 3
PS-02 | PS-02 | Evaluate incorporation of approved IPW enhancements into the PSPS Distribution guidance | Evaluate incorporation of approved IPW enhancements into the PSPS Distribution guidance to enhance focus of PSPS events. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 298 | PSPS | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 3
PS-05 | PS-05 | Evaluate the transition of the Portable Battery Program to permanent battery solutions | Evaluate the transition of the Portable Battery Program to permanent battery solutions for PG&E customers at risk of PSPS or EPSS, focusing on but not limited to AFN, MBL, and self-identified vulnerable populations. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 299 | PSPS | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 3
PS-06 | PS-06 | Provide 12,000 cumulative new or replacement portable and permanent batteries to PG&E customers at risk of PSPS or EPSS, focusing on but not limited to AFN, MBL, and self-identified vulnerable populations. | 2023: Provide 4,000 cumulative new or replacement portable batteries to PG&E customers. 2024: Provide 4,000 cumulative new or replacement portable batteries to PG&E customers 2025: Provide 3,300(i) cumulative new or replacement portable batteries to PG&E customers 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 348 | PSPS | # of batteries | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 3
PS-07 | PS-07 | Reduce PSPS impacts by ~38k customer events (2.4%) for 2023-2025 period by completing planned Wildfire mitigation projects including but not limited to MSO switch replacements and undergrounding. | 2023: 15,000 customer events based on Wildfire mitigation projects including but not limited to MSO replacements and Undergrounded miles planned for 2023. 2024: 9,980 customer events based on Wildfire mitigation projects including but not limited to MSO replacements and Undergrounded miles planned for 2024.(k) (k): Target unit for 2024 reflects the approved 2024 Change Order Decision. The target unit is corrected to show the incremental number (not cumulative). This is consistent with Table PG&E-9-5. 2025: 13,000(i) customer events based on Wildfire mitigation projects including but not limited to MSO replacements and Undergrounded miles planned for 2025.(l) (i): The target has been updated for 2025. See PG&E’s 2025 WMP Update for more information about the target change. (l): Target unit for 2025 is corrected to show the incremental number (not cumulative). This is consistent with Table PG&E-9-5. The incremental 2025 target unit in the base 2023-2025 WMP was 22,000. We have updated the target to 13,000 for 2025. See PG&E’s 2025 WMP Update for more information about the target change. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 349 | PSPS | # of customer events | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | N/A | Tranche 3
PS-08 | PS-08 | Evaluate emerging technologies to reduce PSPS customer impact | Evaluate emerging technologies for transmission and distribution that may further reduce scale, scope, or frequency of PSPS. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 299 | PSPS | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 3
PS-09 | PS-09 | Reduce PSPS impacts via Undergrounding | Reduce PSPS size, duration, or frequency over the next ten years as part of our 10,000-mile undergrounding program. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 299 | PSPS | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | N/A | Tranche 3
PS-10 | PS-10 | Continue sharing PSPS lessons learned | Continue sharing PSPS lessons learned and best practices with CA IOUs through monthly meetings focused on PSPS. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 300 | PSPS | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 3
PS-11 | PS-11 | Pilot using drones for PSPS restoration | Pilot using drones for PSPS restoration and/or damage assessment to improve PSPS outage restoration time. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 300 | PSPS | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf |  | Tranche 3
SA-01 | SA-01 | Artificial Intelligence (AI) in Wildfire Cameras | Enable Artificial Intelligence processing of Wildfire Camera Data to provide automated wildfire notifications in the internal PG&E monitoring tool (Wildfire Incident Viewer). 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 292 | Situational Awareness | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Both | Tranche 3
SA-02Situational Awareness and Forecasting Initiatives - Line Sensors WLDFR-M07A | SA-02 | Line Sensor - Installations | 2023: Install Line Sensor devices on 40 circuits. 2024: Install Line Sensor devices on 40 circuits. 2025: Install Line Sensor devices on 40 circuits. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 347 | Situational Awareness | # of circuits | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Capital | Tranche 1 | 15088.0445 | Situational Awareness and Forecasting Initiatives - Line Sensors WLDFR-M07A | 49I,FZA | Installation, maintenance, and monitoring of sensors and sensorized equipment used to monitor the condition of electric lines and equipment. Unit of measure: # of devices. | Exhibit (PG&E-4), Chapter 4.3, Section C.3.c.1, p. 4.3-58 | Exhibit (PG&E-4), Chapter 4 Workpapers | Volume 1 Ch. 1-6: https://pgera.azurewebsites.net/Regulation/ValidateDocAccess?docID=660354 | 5709.0196 | N/A | 17.9 | Line Sensors WLDFR-M07A is a mitigation outlined in the GRC that includes forecasts for installation, maintenance, and monitoring. The SA-02 target in the WMP is specific to the installation of line sensors and is one component of the overall WLDFR-M07A mitigation. For transparency and consistency, we have provided both the capital and expense adopted amounts associated with WLDFR-M07A despite the expense not being directly tied to SA-02.
SA-03Situational Awareness and Forecasting Initiatives - EFD WLDFR-M011, Distribution Fault Anticipation (DFA) WLDFR-M012 | SA-03 | EFD and DFA Reporting | Develop scalable processes to: (a) analyze alarms and alerts from Early Fault Detection (EFD) and DFA sensors; (b) conduct field investigation and reporting; (c) track identified mitigations to completion; and (d) track effectiveness of issue identification and remediation using EFD/DFA technologies. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 293 | Situational Awareness | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 3 | 0 | Situational Awareness and Forecasting Initiatives - EFD WLDFR-M011, Distribution Fault Anticipation (DFA) WLDFR-M012 | 49I | This WMP activity is not specifically identified as a wildfire mitigation in the 2023 GRC. PG&E did not specifically describe this activity in the 2023 GRC, but did describe installation of EFD and DFA sensors. EFD: Radio Frequency (RF) sensors are sophisticated technology that listens for the RF signal that is generated by partial discharge arcing on alternating current (AC) circuits and uses precision time measurement of events to locate the source along the conductors. Early Fault Detection is the product name. DFA: Event Classification Through Current and Voltage Monitoring Sensors (ECCVM) (also called Distribution Fault Anticipation) are substation Current Transformers (CT)/Potential Transformer (PT) based devices measuring volts, amps, and arcing conditions. The sensors monitor magnitude, phase, harmonics, real and reactive power, and cycle to cycle deltas in these values. | Exhibit (PG&E-4), Chapter 4.3, Section C.3.c.3, p. 4.3-60 | Exhibit (PG&E-4), Chapter 4 Workpapers | Volume 1 Ch. 1-6: https://pgera.azurewebsites.net/Regulation/ValidateDocAccess?docID=660354 |  | Not Applicable | Not Applicable
SA-04 | SA-04 | FPI and IPW Modeling - Revision Evaluation | Evaluate enhancements to the FPI model and the Ignition Probability Weather model. This involves testing new features and types of model configurations that could improve model skill. At present we do not know if model skills can be improved but we will attempt to do so. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 293 | Situational Awareness | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 3
SA-05 | SA-05 | Evaluate FPI and IPW Modeling enhancements in 2023 - 2025 | Evaluate enhancements to the FPI (Fire Potential Index) model and the IPW (Ignition Probability Weather) model in 2023. This involves testing new features and types of model configurations that could improve model skill. For example, one of the features that will be evaluated for IPW is covered conductor and EPSS on the system. If covered conductor, EPSS, or other model enhancements, do not improve model skill, it will not be deployed as a part of the model improvement. At present we do not know if model skill can be improved but we will attempt to do so in 2023. If model skill can be improved and is approved, we plan to operationalize the new models in 2024 and continue operations in 2025. We do not know if any new models developed will be approved for operations by PG&E’s Wildfire risk governance committee. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 294 | Situational Awareness | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 3
SA-06 | SA-06 | Evaluate FPI and IPW Modeling enhancements in 2026 - 2032 | Evaluate enhancements to the FPI (Fire Potential Index) model and the IPW (Ignition Probability Weather) model in the 2026-2033 period. This work involves testing new features and types of model configurations that could improve model forecasting ability. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 294 | Situational Awareness | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 3
SA-07Situational Awareness and Forecasting Initiatives - Wildfire Cameras (WLDFR-M07D) | SA-07 | Monitor and evaluate the Cameras AI system’s performance | In partnership with Digital Path (the AI vendor that works with us and other agencies on the broader camera network) monitor and evaluate the AI system’s performance. Explore additional features and inputs to further enhance the system. At present we do not know what these enhancements will be specifically, however we will look for opportunities to explore best practices and incorporate enhancements with the vendor. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 295 | Situational Awareness | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 3 | 0 | Situational Awareness and Forecasting Initiatives - Wildfire Cameras (WLDFR-M07D) | AB6 | This WMP activity is not specifically identified as a wildfire mitigation in the 2023 GRC. Artificial Intelligence for wildfire camera's was not specifically identified in the GRC but the purchase, installation, maintenance, and operation of HD cameras is. Cameras are used to identify and track wildfires in real‑time, from ignition to containment. | Exhibit (PG&E-4), Chapter 4.1, Section C.1.b. p. 4-15 | Exhibit (PG&E-4), Chapter 4 Workpapers | Volume 1 Ch. 1-6: https://pgera.azurewebsites.net/Regulation/ValidateDocAccess?docID=660354 |  | Not Applicable | Not Applicable | PG&E included a forecast for installation and ongoing O&M expenses for Wildfire Cameras in the 2023 GRC, but did not provide a forecast for testing and implementing advanced AI-capability software and incorporating it into the preexisting camera network. However PG&E plans to record costs for this activity in the WMBA. There was no CBR or RSE calculated for this WMP initiative in the GRC.
SA-08Situational Awareness and Forecasting Initiatives - Wildfire Cameras (WLDFR-M07D) | SA-08 | Evaluate the Cameras AI system functionalities and technologies | In partnership with Digital Path and its collaboration with other camera sponsors, evaluate the AI system for opportunities to test new functionalities and newly developed break-through technologies. We will also explore new best practices to ensure the ongoing effectiveness of the system. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 295 | Situational Awareness | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 3 | 0 | Situational Awareness and Forecasting Initiatives - Wildfire Cameras (WLDFR-M07D) | AB6 | This WMP activity is not specifically identified as a wildfire mitigation in the 2023 GRC. Artificial Intelligence for wildfire camera's was not specifically identified in the GRC but the purchase, installation, maintenance, and operation of HD cameras is. Cameras are used to identify and track wildfires in real‑time, from ignition to containment. | Exhibit (PG&E-4), Chapter 4.1, Section C.1.b. p. 4-15 | Exhibit (PG&E-4), Chapter 4 Workpapers | Volume 1 Ch. 1-6: https://pgera.azurewebsites.net/Regulation/ValidateDocAccess?docID=660354 |  | Not Applicable | Not Applicable | PG&E included a forecast for installation and ongoing O&M expenses for Wildfire Cameras in the 2023 GRC, but did not provide a forecast for testing and implementing advanced AI-capability software and incorporating it into the preexisting camera network. However PG&E plans to record costs for this activity in the WMBA. There was no CBR or RSE calculated for this WMP initiative in the GRC.
SA-09Situational Awareness and Forecasting Initiatives - EFD WLDFR-M011, Distribution Fault Anticipation (DFA) WLDFR-M012 | SA-09 | EFD and DFA Reporting | Perform a feasibility study on the use of EFD/DFA technologies to successfully identify incipient failures as a supplement to field inspections. If feasible, complete a data driven proposal for integrating sensor findings into the inspection program. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 295 | Situational Awareness | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 3 | 0 | Situational Awareness and Forecasting Initiatives - EFD WLDFR-M011, Distribution Fault Anticipation (DFA) WLDFR-M012 | 49I | This WMP activity is not specifically identified as a wildfire mitigation in the 2023 GRC. PG&E did not specifically describe this activity in the 2023 GRC, but did describe installation of EFD and DFA sensors. EFD: Radio Frequency (RF) sensors are sophisticated technology that listens for the RF signal that is generated by partial discharge arcing on alternating current (AC) circuits and uses precision time measurement of events to locate the source along the conductors. Early Fault Detection is the product name. DFA: Event Classification Through Current and Voltage Monitoring Sensors (ECCVM) (also called Distribution Fault Anticipation) are substation Current Transformers (CT)/Potential Transformer (PT) based devices measuring volts, amps, and arcing conditions. The sensors monitor magnitude, phase, harmonics, real and reactive power, and cycle to cycle deltas in these values. | Exhibit (PG&E-4), Chapter 4.3, Section C.3.c.3, p. 4.3-60 | Exhibit (PG&E-4), Chapter 4 Workpapers | Volume 1 Ch. 1-6: https://pgera.azurewebsites.net/Regulation/ValidateDocAccess?docID=660354 |  | Not Applicable | Not Applicable
SA-10Situational Awareness and Forecasting Initiatives - Distribution Fault Anticipation (DFA) WLDFR-M012 | SA-10 | Distribution Fault Anticipation (DFA) Installations | 2023: Install 5 Distribution Fault Anticipation (DFA) sensors on circuits.(g) One sensor will be installed per circuit at the initiating substation. 2024: Install 15 Distribution Fault Anticipation (DFA) sensors on circuits feeding into HFTD areas or HFRA. One sensor will be installed per circuit at the initiating substation. 2025: Install 15 Distribution Fault Anticipation (DFA) sensors on circuits feeding into HFTD areas or HFRA. One sensor will be installed per circuit at the initiating substation. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 348 | Situational Awareness | # of dfa sensors | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Capital | Tranche 1 | 10127.498 | Situational Awareness and Forecasting Initiatives - Distribution Fault Anticipation (DFA) WLDFR-M012 | 49I | Event Classification Through Current and Voltage Monitoring Sensors (ECCVM) (also called Distribution Fault Anticipation) are substation Current Transformers (CT)/Potential Transformer (PT_-based devices measuring volts, amps, and arcing conditions. The sensors monitor magnitude, phase, harmonica, real and reactive power, and cycle-to-cycle deltas in these values. | Exhibit (PG&E-4), Chapter 4.3, Section C.3.c.3, p. 4.3-60 | Exhibit (PG&E-4), Chapter 4 Workpapers | Volume 1 Ch. 1-6: https://pgera.azurewebsites.net/Regulation/ValidateDocAccess?docID=660354 | 9288.4874 |  | The RSE for SA&FI – DFA (WLDFR-M012) is incorporated into the SA&FI – Line Sensors program (WLDFR-M07A) because the two devices work in tandem and the risk reduction is combined.
SA-11Situational Awareness and Forecasting Initiatives - EFD WLDFR-M011 | SA-11 | Early Fault Detection (EFD) Installations | 2023: Install Early Fault Detection (EFD) sensors on 2 circuits.(h) 2024: Install Early Fault Detection (EFD) sensors on 2 circuits. 2025: Install Early Fault Detection (EFD) sensors on 4 circuits. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 348 | Situational Awareness | # of EFD circuits | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Capital | Tranche 1 | 6138.4203 | Situational Awareness and Forecasting Initiatives - EFD WLDFR-M011 | 49I | Radio Frequency (RF) sensors are sophisticated technology that listens for the RF signal that is generated by partial discharge arcing on alternating current (AC) circuits and uses precision time measurement of events to locate the source along the conductors. Early Fault Detection is the product name. | Exhibit (PG&E-4), Chapter 4.3, Section C.3.c.2, p. 4.3-59 | Exhibit (PG&E-4), Chapter 4 Workpapers | Volume 1 Ch. 1-6: https://pgera.azurewebsites.net/Regulation/ValidateDocAccess?docID=660354 | 5095.5277 |  | 71.5
SA-12Situational Awareness and Forecasting Initiatives - Various | SA-12 | Evaluate the use and effectiveness of real-time monitoring tools | Each year, we will evaluate and discuss our situational awareness tools internally, as well as with other IOUs. These evaluative discussions will include reviewing observations of our various situational awareness tools and identifying potential areas for improvement. We will also discuss best practices and lessons learned. These discussions will help inform potential changes to what situational awareness tools we incorporate, as well as how they are incorporated. This may include equipment upgrades, new tech integrations, model improvements, and enhanced data initiatives. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 296 | Situational Awareness | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 3 | 0 | Situational Awareness and Forecasting Initiatives - Various | Various | This WMP activity is not specifically identified as a wildfire mitigation in the 2023 GRC. PG&E does discuss all Situational Awareness programs in Exhibit 4 Chapters 4.1. | Exhibit (PG&E-4), Chapter 4.3. | Exhibit (PG&E-4), Chapter 4 Workpapers | Volume 1 Ch. 1-6: https://pgera.azurewebsites.net/Regulation/ValidateDocAccess?docID=660354 |  | Not Applicable | Not Applicable
VM-01 | VM-01 | LiDAR Data Collection - Transmission | 2023: Collect LiDAR data of the Transmission System (17,500 circuit miles). The Transmission System circuit miles include both HFTD / HFRA and non-HTFD Transmission circuit miles. 2024: Collect LiDAR data of the Transmission System (17,500 circuit miles). The Transmission System circuit miles include both HFTD / HFRA and non-HFTD Transmission circuit miles. 2025: Collect LiDAR data of the Transmission System (17,500 circuit miles). The Transmission System circuit miles include both HFTD / HFRA and non-HFTD Transmission circuit miles. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 342 | Vegetation Management | # of circuit miles | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1
VM-02 | VM-02 | Pole Clearing Program | 2023: Inspect, clear, and maintain, where clearing is necessary, 77,503 poles per Vegetation Control Standard TD-7112S. 2024: 2024 pole count to be adjusted by the ending pole population in the previous year (2023) poles per Vegetation Control Standard TD-7112S will be inspected, cleared, and maintained where clearing is necessary. 2025: 2025 pole count to be adjusted by the ending pole population in the previous year (2024) poles per Vegetation Control Standard TD-7112S will be inspected, cleared, and maintained where clearing is necessary. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 342 | Vegetation Management | # of distribution poles | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1
VM-03 | VM-03 | Focused Tree Inspection (FTI) | 2023: Complete focus tree inspections of 250 Circuit Miles in defined Areas of Concern (AOC) locations.(c) 2024: Within Areas of Concern (AOC) locations, complete 1,500 circuit miles of FTI inspection which includes performing a level 2 inspection on all potential strike trees. 2025: Within Areas of Concern (AOC) locations complete 1,500 circuit miles of FTI inspection which includes performing a level 2 inspection on all potential strike trees. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 343 | Vegetation Management | # of circuit miles | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1
VM-04 | VM-04 | Tree Removal Inventory (TRI) | 2023: Mitigate(d)15,000 trees identified from the legacy EVM program. 2024: Mitigate(d) 20,000 trees identified from the legacy EVM program. 2025: Mitigate(d) 25,000 trees identified from the legacy EVM program. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 343 | Vegetation Management | # of trees | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1
VM-05 | VM-05 | Defensible Space Inspections - Distribution Substation | 2023: Complete defensible space inspections in alignment with the guidelines set forth in LAND 4001P-01 at 131 distribution substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2024: Complete defensible space inspections in alignment with the guidelines set forth in LAND 4001P-01 at 131 distribution substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2025: Complete defensible space inspections in alignment with the guidelines set forth in LAND 4001P-01 at 131 distribution substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 343 | Vegetation Management | # of distribution substations | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1
VM-06 | VM-06 | Defensible Space Inspections - Transmission Substation | 2023: Complete defensible space inspections in alignment with the guidelines set forth in LAND 4001P-01 at 55 transmission substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2024: Complete defensible space inspections in alignment with the guidelines set forth in LAND 4001P-01 at 55 transmission substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2025: Complete defensible space inspections in alignment with the guidelines set forth in LAND 4001P-01 at 55 transmission substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 343 | Vegetation Management | # of transmission substations | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1
VM-07 | VM-07 | Defensible Space Inspections - Hydroelectric Substations and Powerhouses | 2023: Complete defensible space inspections in alignment with the guidelines set forth in LAND 5201P-01 at 61 Hydroelectric Generation Substations and Powerhouses. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2024: Complete defensible space inspections in alignment with the guidelines set forth in LAND 5201P-01 at 61 Hydroelectric Generation Substations and Powerhouses. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2025: Complete defensible space inspections in alignment with the guidelines set forth in LAND 5201P-01 at 61 Hydroelectric Generation Substations and Powerhouses. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 344 | Vegetation Management | # of hydroelectric substations and powerhouses | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1
VM-08 | VM-08 | Vegetation Management – Quality Assurance | 2023: Perform vegetation management QA audits on QC completed locations and achieve the associated quality pass rates for each vegetation management program as specified below: Distribution Routine VM - HFTD: 2,500 audit locations*; 95% pass rate Transmission VM - HFTD: 1,200 audit locations; 95% pass rate Vegetation Control Pole Clearing - HFTD: 1,800 audit locations*; 95% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. 2024: Perform vegetation management QA audits on QC completed locations and achieve the associated quality pass rates for each vegetation management program as specified below: Distribution Routine VM - HFTD: 2,675 audit locations*; 95% pass rate Transmission VM - HFTD: 1,284 audit locations; 95% pass rate Vegetation Control Pole Clearing - HFTD: 1,926 audit locations*; 95% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. 2025: Perform vegetation management QA audits on QC completed locations and achieve the associated quality pass rates for each vegetation management program as specified below: Distribution Routine VM - HFTD: 2,862 audit locations*; 95% pass rate Transmission VM - HFTD: 1,374 audit locations*; 95% pass rate Vegetation Control Pole Clearing - HFTD: 2,061 audit locations*; 95% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 345 | Vegetation Management | % pass rate and # of audit locations | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1
VM-09 | VM-09 | Constraint Resolution Procedural Guideline | Develop a process of centralizing constraints resolution. As part of the build out of the centralized constraints team, three major categories will be addressed: customer constraints, environmental constraints (including internal PG&E procedures required to perform work) and permitting constraints (including both Land and Environmental permits). For each major constraint category build a process for addressing each constraint type, implement the new process, and create metrics to track each constraint type. Reporting will track total constraints by type and the time it takes to resolve a constraint after it has been identified. PG&E will consider creating a “right tree-right place” program, as part of the centralize Constraints Resolution process. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 8-12 Vegetation Management Implementation Objectives (3-Year Plan) p. 606 | Vegetation Management | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1
VM-10 | VM-10 | Inspection in HFTD and HFRA supporting key vegetation management initiatives | Continue multiple inspection activities in HFTD and HFRA supporting key vegetation management initiatives 2023-2025 Wildfire Mitigation Plan R6 Revised Table 8-13 Vegetation Management Implementation Objectives (10-Year Plan) p. 607 | Vegetation Management | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1
VM-11 | VM-11 | Enhance and refine Focus Tree Inspection – Areas of Concern (AOC) | Enhance and refine Focus Tree Inspection - Areas of Concern (AOC) development criteria and application of the AOCs to vegetation management programs. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 8-13 Vegetation Management Implementation Objectives (10-Year Plan) p. 607 | Vegetation Management | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1
VM-12 | VM-12 | Evaluate emerging technologies | Evaluate emerging technologies to enhance focus of and streamline execution of vegetation management inspections. | Vegetation Management | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1
VM-13 | VM-13 | Routine Ground - Transmission | 2023: Complete Routine Transmission Ground Inspection of 17,740 circuit miles as defined by Transmissions Routine LiDAR detection point data systemwide. 2024: Complete Routine Transmission Ground Inspection of 17,740 circuit miles as defined by Transmissions Routine LiDAR detection point data systemwide. 2025: Complete Routine Transmission Ground Inspection of 17,740 circuit miles as defined by Transmissions Routine LiDAR detection point data systemwide. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 345 | Vegetation Management | # of circuit miles | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1
VM-14 | VM-14 | Transmission Second Patrol | 2023: Complete Transmission Second Patrol Inspection of 5,625 circuit miles dependent on remote sensing (ORTHO Imagery). 2024: Complete Transmission Second Patrol Inspection of 5,625 circuit miles dependent on remote sensing (ORTHO Imagery). 2025: Complete Transmission Second Patrol Inspection of 5,625 circuit miles dependent on remote sensing (ORTHO Imagery). 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 345 | Vegetation Management | # of circuit miles | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1
VM-15 | VM-15 | Integrated Vegetation Management - Transmission | 2023: Complete Integrated Vegetation Management and Fee Inspections of 11,194 acres ROW across the Transmission systemwide 2024: Complete Integrated Vegetation Management and Fee Inspections of 6,504 acres ROW across the Transmission systemwide 2025: Complete Integrated Vegetation Management and Fee Inspections of 6,504 acres ROW across the Transmission systemwide 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 346 | Vegetation Management | # of acres | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1
VM-16 | VM-16 | Distribution Routine Patrol | 2023: Complete Distribution Routine Annual Patrol Inspection of 79,000 overhead circuit miles system wide 2024: Complete Distribution Routine Annual Patrol Inspection of 78,650 overhead circuit miles system wide 2025: Complete Distribution Routine Annual Patrol Inspection of 78,200 overhead circuit miles system wide 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 346 | Vegetation Management | # of circuit miles | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1
VM-17 | VM-17 | Distribution Second Patrol | 2023: Complete Distribution Second Patrol Inspection of 43,600 circuit miles that are in the following map layers FHSZ, WUI, SRA, FRA, HFTD, and HFRA locations. 2024: Complete Distribution Second Patrol Inspection of 25,685 circuit miles in HFTD and HFRA locations. 2025: Complete Distribution Second Patrol Inspection of 25,685 circuit miles in HFTD and HFRA locations. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 346 | Vegetation Management | # of circuit miles | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1
VM-18 | VM-18 | VM for Operational Mitigations (VMOM) | 2023: N/A 2024: Mitigate 6,500 trees for VM for Operational Mitigations program, on EPSS capable circuits. This target will include the previous year's carry-over work and prescriptions resulting from pro-active patrols on EPSS circuits. Future workplans will be dependent on previous year's EPSS outage data analysis. 2025: Mitigate 6,500 trees for VM for Operational Mitigations program, on EPSS capable circuits. This target will include the previous year's carry-over work and prescriptions resulting from pro-active patrols on EPSS circuits. Future workplans will be dependent on previous year's EPSS outage data analysis. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 346 | Vegetation Management | # of trees | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1
VM-19 | VM-19 | One VM Application Record Keeping Enhancement (Routine, Second Patrol) | Enhance the One VM application for Routine, and Second Patrol to include capability to capture factors for prescribing trees for removal. | Vegetation Management | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1
VM-20 | VM-20 | Record Keeping Enhancement (VMOM, TRI) | Enhance the application for the Vegetation Management for Operational Mitigations (VMOM) - VMPI2 - and Tree Removal Inventory (TRI) - Field Maps - program to include capability to capture factors for prescribing trees for removal. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 292 | Vegetation Management | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1
VM-21 | VM-21 | Focused Tree Inspection (FTI) Program Record Keeping Enhancement | Enhance record keeping practices for the Focused Tree Inspection program (FTI) by creating records of all potential strike trees inspected using a digitized Tree Risk Assessment form. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 292 | Vegetation Management | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1
VM-22 | VM-22 | Vegetation Management - Quality Control | 2023: Perform vegetation management QC audits and achieve the associated quality pass rates for each vegetation management program as specified below: Distribution Routine VM – HFTD: 75,000 audit locations*; 80% pass rate Transmission VM – HFTD: 12,500 audit locations*; 88% pass rate Vegetation Control Pole Clearing – HFTD: 10,500 audit locations*; 80% pass rate. 2024: Perform vegetation management QC audits and achieve the associated quality pass rates for each vegetation management program as specified below: Distribution Routine VM – HFTD: 80,000 audit locations*; 88% pass rate Transmission VM – HFTD: 13,500 audit locations*; 92% pass rate Vegetation Control Pole Clearing – HFTD: 11,500 audit locations*; 88% pass rate. 2025: Perform vegetation management QC audits and achieve the associated quality pass rates for each vegetation management program as specified below: Distribution Routine VM – HFTD: 85,000 audit locations*; 95% pass rate Transmission VM – HFTD: 14,500 audit locations*; 95% pass rate Vegetation Control Pole Clearing – HFTD: 12,500 audit locations*; 95% pass rate. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 346 | Vegetation Management | % pass rate and # of audit locations | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1
8.4.6 | 8.4.6 | Customer Support in Wildfire and PSPS Emergencies | Development and deployment of programs, systems, and protocols to support residential and non-residential customers in wildfire emergencies and PSPS events. | Emergency Preparedness | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Both | Tranche 1
8.4.4 | 8.4.4 | Public Emergency Communication Strategy | Development and integration of a comprehensive communication strategy to inform essential customers and other stakeholder groups of wildfires, outages due to wildfires, and PSPS and service restoration, as required by Pub. Util. Code Section 768.6. | Emergency Preparedness | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1
8.1.2.3 | 8.1.2.3 | Distribution pole replacements and reinforcements | Remediation, adjustments, or installations of new equipment to improve or replace existing distribution poles (i.e., those supporting lines under 65 kV), including with equipment such as composite poles manufactured with materials reduce ignition probability by increasing pole lifespan and resilience against failure from object contact and other events. | Grid Design Ops Maintenance | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Both | Tranche 1
8.1.2.6 | 8.1.2.6 | Emerging grid hardening technology installations and pilots | Development, deployment, and piloting of novel grid hardening technology. | Grid Design Ops Maintenance | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Both | Tranche 1
8.1.2.9 | 8.1.2.9 | Line removals (in HFTD) | Removal of overhead lines to minimize the risk of ignition due to the design, location, or configuration of electric equipment in HFTDs. | Grid Design Ops Maintenance | # of circuit miles | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Capital | Tranche 1
8.1.2.7 | 8.1.2.7 | Microgrids | Development and deployment of microgrids that may reduce the risk of ignition, risk from PSPS, and wildfire consequence. "Microgrid" is defined by Pub. Util. Section 8370(d) | Grid Design Ops Maintenance |  | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Both | Tranche 1
8.1.2.11 | 8.1.2.11 | Other grid topology improvements to mitigate or reduce PSPS events | Actions taken to mitigate or reduce PSPS events in terms of geographic scope and number of customers affected not covered by another initiative. | Grid Design Ops Maintenance | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Capital | Tranche 1
8.1.2.12 | 8.1.2.12 | Other technologies and systems not listed above | Other grid design and system hardening actions which the electrical corporation takes to reduce its ignition and PSPS risk not otherwise covered by other initiatives in this section. | Grid Design Ops Maintenance | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1
8.1.8.3 | 8.1.8.3 | Personnel Work Procedures and Training in Conditions of Elevated Fire Risk | Work activity guidelines that designate what type of work can be performed during operating conditions of different levels of wildfire risk. Training for personnel on these guidelines and the procedures they prescribe, from normal operating procedures to increased mitigation measures to constraints on work performed. | Grid Design Ops Maintenance | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | N/A | Tranche 1
8.2.3.2 | 8.2.3.2 | Wood and slash management | Actions taken to manage all downed wood and "slash" generated from vegetation management activities. | Vegetation Management | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1
8.1.9 | 8.1.9 | Workforce Planning | Programs to ensure that the electrical corporation has qualified asset personnel and to ensure that both employees and contractors tasked with asset management responsibilities are adequately trained to perform relevant work. | Grid Design Ops Maintenance | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | N/A | Tranche 1
8.1.2.4 | 8.1.2.4 | Transmission pole/tower replacements and reinforcements | Remediation, adjustments, or installations of new equipment to improve or replace existing transmission towers (e.g., structures such as lattice steel towers or tubular steel poles that support lines at or above 65 kV). | Grid Design Ops Maintenance | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Both | Tranche 1
8.3.6Situational Awareness and Forecasting Initiatives - Fire Potential Index WLDFR-M07K | 8.3.6 | Fire potential index | Calculation and application of a landscape scale index used as a proxy for assessing real-time risk of a wildfire under current and forecasted weather conditions. | Situational Awareness | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1 |  | Situational Awareness and Forecasting Initiatives - Fire Potential Index WLDFR-M07K | AB6 | The O&M work in FPI will focus on annual recalibration, which will support operations and help inform fire mitigations on a daily basis. | Exhibit (PG&E-4), Chapter 4.1, Section C1,d,3, p. 4.1-27 | Exhibit (PG&E-4), Chapter 4 Workpapers | Volume 1 Ch. 1-6: https://pgera.azurewebsites.net/Regulation/ValidateDocAccess?docID=660354
8.3.4 | 8.3.4 | Ignition detection systems | Development and deployment of systems which discover or identify the presence or existence of an ignition, such as cameras | Situational Awareness | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1
8.2.3.8 | 8.2.3.8 | Emergency response vegetation management | Planning and execution of vegetation activities in response to emergency situations including weather conditions that indicate an elevated fire threat and post-wildfire service restoration. | Vegetation Management | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1
8.2.3.7 | 8.2.3.7 | Fire-resilient rights-of-way | Actions taken to promote vegetation communities that are sustainable, fire-resilient, and compatible with the use of the land as an electrical corporation right-of-way. | Vegetation Management | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1
8.2.3.6 | 8.2.3.6 | High-risk species | Actions taken to reduce the ignition probability and wildfire consequence attributable to high-risk species of vegetation. | Vegetation Management | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | N/A | Tranche 1
8.2.7 | 8.2.7 | Workforce Planning | Programs to ensure that the electrical corporation has qualified vegetation management personnel and to ensure that both employees and contractors tasked with vegetation management responsibilities are adequately trained to perform relevant work. | Vegetation Management | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | N/A | Tranche 1
7 | 7 | Wildfire Mitigation Strategy Development | Development and use of processes for deciding on a portfolio of mitigation initiatives to achieve maximum feasible risk reduction and that meet the goals of the WMP. | Wildfire Mitigation Strategy Development | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | N/A | Tranche 1
6 | 6 | Risk Methodology and Assessment | Development and use of tools and processes to assess the risk of wildfire and PSPS across an electrical corporation’s service territory. | Risk Methodology Assessment | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Capital | Tranche 1
5.4.5 | 5.4.5 | Environmental compliance and permitting | Development and implementation of process and procedures to ensure compliance with applicable environmental laws, regulations, and permitting related to the implementation of the WMP. | Overview of Service Territory | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | N/A | Tranche 1
8.4.3 | 8.4.3 | External collaboration and coordination | Actions taken to coordinate wildfire and PSPS emergency preparedness with relevant public safety partners including the state, cities, counties, and tribes. | Emergency Preparedness | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1
8.1.4 | 8.1.4 | Equipment maintenance and repair | Remediation, adjustments, or installations of new equipment to improve or replace existing connector equipment, such as hotline clamps. | Grid Design Ops Maintenance | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Both | Tranche 1
8.1.8.2 | 8.1.8.2 | Grid Response Procedures and Notifications | The electrical corporation’s procedures it uses to respond to faults, ignitions, or other issues detected on its grid that may result in a wildfire. | Grid Design Ops Maintenance | non-unitized | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | N/A | Tranche 1
8.2.2.3 | 8.2.2.3 | Vegetation Inspections - Substations | Inspections of vegetation around and adjacent to electrical facilities and equipment that may be hazardous by growing, blowing, or falling into electrical facilities or equipment. | Vegetation Management | # of substation defensible space inspections | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf | Expense | Tranche 1
|  | Other - Wildfire | There is no definition for this in Table PG&E-A-2 |  |  | https://www.pge.com/assets/pge/docs/outages-and-safety/outage-preparedness-and-support/pge-wmp-r6-07052024.pdf |  | Tranche 1
SA-Other-Grid Monitoring Systems | SA-Other-Grid Monitoring Systems |  |  | Situational Awareness

## HFTD, CapEx (2 of 5)
HFTD, CapEx Costs and Recoveries | Section A: WMP Cost and Unit Data | [5 empty] | Section B: Costs and Units Authorized in Last GRC | [5 empty] | Section C: Costs and Units Forecast to be Requested in the Next GRC | [5 empty] | Section D: Costs Recorded via Application (Memo or Balancing Account) | [5 empty] | Section E: SB 884 Activity | [5 empty] | Section F: FERC or Other
Mitigation Initiative Cost Reporting Identification Code | Costs and Amounts by Year | [5 empty] | WMP Year 1 |  | WMP Year 2 |  | WMP Year 3 |  | WMP Year 1 |  | WMP Year 2 |  | WMP Year 3 |  | WMP Year 1 |  | WMP Year 2 |  | WMP Year 3 |  | WMP Year 1 |  | WMP Year 2 |  | WMP Year 3 |  | WMP Year 1 |  | WMP Year 2 |  | WMP Year 3
Mitigation Initiative Cost Reporting Identification Code | WMP 2023 Recorded ($ in 1,000s) | WMP 2023 Number of Units (where applicable) | WMP 2024 Forecast ($ in 1,000s) | WMP 2024 Number of Units (where applicable) | WMP 2025 Forecast ($ in 1,000s) | WMP 2025 Number of Units (where applicable) | Costs authorized in last GRC (2023) ($) for WMP 2023 | Units authorized in last GRC (2023) for WMP 2023 | Costs authorized in last GRC (2023) ($) for WMP 2024 | Units authorized in last GRC (2023) for WMP 2024 | Costs authorized in last GRC (2023) ($) for WMP 2025 | Units authorized in last GRC (2023) for WMP 2025 | Costs to be requested in next GRC (2027) ($) for WMP 2023 | Units to be requested in next GRC (2027) for WMP 2023 | Costs to be requested in next GRC (2027) ($) for WMP 2024 | Units to be requested in next GRC (2027) for WMP 2024 | Costs to be requested in next GRC (2027) ($) for WMP 2025 | Units to be requested in next GRC (2027) for WMP 2025 | Costs ($ in 1,000s) recorded via Application for WMP 2023 | Units recorded via Application for WMP 2023 | Costs ($) recorded via Application for WMP 2024 | Units recorded via Application for WMP 2024 | Costs ($) recorded via Application for WMP 2025 | Units recorded via Application for WMP 2025 | SB 884 Activity, Forecasted Costs ($) for WMP 2023 | SB 884 Activity, Forecasted Units for WMP 2023 | SB 884 Activity, Forecasted Costs ($) for WMP 2024 | SB 884 Activity, Forecasted Units for WMP 2024 | SB 884 Activity, Forecasted Costs ($) for WMP 2025 | SB 884 Activity, Forecasted Units for WMP 2025 | FERC or Other Forecasted Costs ($) to be recovered for WMP 2023 | FERC or Other Forecasted Units to be recovered for WMP 2023 | FERC or Other Forecasted Costs ($) to be recovered for WMP 2024 | FERC or Other Forecasted Units to be recovered for WMP 2024 | FERC or Other Forecasted Costs ($) to be recovered for WMP 2025 | FERC or Other Forecasted Units to be recovered for WMP 2025 | Comments
AI-01
AI-02
AI-03
AI-04
AI-05
AI-06
AI-07
AI-08
AI-09
AI-10
AI-11
CO-01
CO-02
CO-04
CO-05
EP-01
EP-02
EP-04
EP-06
EP-07
EP-08
EP-09
GH-01 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0
GH-02
GH-03
GH-04 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0
GH-05
GH-06
GH-07
GH-08
GH-09
GH-10
GH-11
GM-01
GM-02
GM-03
GM-06
GM-07
GM-08
GM-09
PS-01
PS-02
PS-05
PS-06
PS-07
PS-08
PS-09
PS-10
PS-11
SA-01
SA-02 | 3008 | 55 | 2463 | 40 | 8274 | 40 | 8717.0196 | 900 | 9103.9662 | 900 | 9362.9188 | 900 | [6 empty] | 3008
SA-03 |  | Not Applicable |  | Not Applicable |  | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available
SA-04
SA-05
SA-06
SA-07 |  | Not Applicable |  | Not Applicable |  | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available
SA-08 |  | Not Applicable |  | Not Applicable |  | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available
SA-09 |  | Not Applicable |  | Not Applicable |  | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available
SA-10 | 180 | 5 | 3000 | 15 | 1061 | 15 | 9468.4874 | 116 | 9888.7914 | 116 | 10170.0676 | 116 | [6 empty] | 180
SA-11 | 644 | 2 | 7000 | 2 | 1061 | 4 | 5739.5277 | 250 | 5994.3041 | 250 | 6164.8057 | 250 | [6 empty] | 644
SA-12 |  | Not Applicable |  | Not Applicable |  | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available
VM-01
VM-02
VM-03
VM-04
VM-05
VM-06
VM-07
VM-08
VM-09
VM-10
VM-11
VM-12
VM-13
VM-14
VM-15
VM-16
VM-17
VM-18
VM-19
VM-20
VM-21
VM-22
8.4.6
8.4.4
8.1.2.3
8.1.2.6
8.1.2.9
8.1.2.7
8.1.2.11
8.1.2.12
8.1.8.3
8.2.3.2
8.1.9
8.1.2.4
8.3.6
8.3.4
8.2.3.8
8.2.3.7
8.2.3.6
8.2.7
7
6
5.4.5
8.4.3
8.1.4
8.1.8.2
8.2.2.3
Other-Wildfire

## HFTD, OpEx (3 of 5)
HFTD, OpEx Costs and Recoveries | Section A: WMP Cost and Unit Data | [5 empty] | Section B: Costs and Units Authorized in Last GRC | [5 empty] | Section C: Costs and Units Forecast to be Requested in the Next GRC | [5 empty] | Section D: Costs Recorded via Application (Memo or Balancing Account) | [5 empty] | Section E: SB 884 Activity | [5 empty] | Section F: FERC or Other
Mitigation Initiative Cost Reporting Identification Code | Costs and Amounts by Year | [5 empty] | WMP Year 1 |  | WMP Year 2 |  | WMP Year 3 |  | WMP Year 1 |  | WMP Year 2 |  | WMP Year 3 |  | WMP Year 1 |  | WMP Year 2 |  | WMP Year 3 |  | WMP Year 1 |  | WMP Year 2 |  | WMP Year 3 |  | WMP Year 1 |  | WMP Year 2 |  | WMP Year 3
Mitigation Initiative Cost Reporting Identification Code | WMP 2023 Recorded ($ in 1,000s) | WMP 2023 Number of Units (where applicable) | WMP 2024 Forecast ($ in 1,000s) | WMP 2024 Number of Units (where applicable) | WMP 2025 Forecast ($ in 1,000s) | WMP 2025 Number of Units (where applicable) | Costs authorized in last GRC (2023) ($) for WMP 2023 | Units authorized in last GRC (2023) for WMP 2023 | Costs authorized in last GRC (2023) ($) for WMP 2024 | Units authorized in last GRC (2023) for WMP 2024 | Costs authorized in last GRC (2023) ($) for WMP 2025 | Units authorized in last GRC (2023) for WMP 2025 | Costs to be requested in next GRC (2027) ($) for WMP 2023 | Units to be requested in next GRC (2027) for WMP 2023 | Costs to be requested in next GRC (2027) ($) for WMP 2024 | Units to be requested in next GRC (2027) for WMP 2024 | Costs to be requested in next GRC (2027) ($) for WMP 2025 | Units to be requested in next GRC (2027) for WMP 2025 | Costs ($ in 1,000s) recorded via Application for WMP 2023 | Units recorded via Application for WMP 2023 | Costs ($) recorded via Application for WMP 2024 | Units recorded via Application for WMP 2024 | Costs ($) recorded via Application for WMP 2025 | Units recorded via Application for WMP 2025 | SB 884 Activity, Forecasted Costs ($) for WMP 2023 | SB 884 Activity, Forecasted Units for WMP 2023 | SB 884 Activity, Forecasted Costs ($) for WMP 2024 | SB 884 Activity, Forecasted Units for WMP 2024 | SB 884 Activity, Forecasted Costs ($) for WMP 2025 | SB 884 Activity, Forecasted Units for WMP 2025 | FERC or Other Forecasted Costs ($) to be recovered for WMP 2023 | FERC or Other Forecasted Units to be recovered for WMP 2023 | FERC or Other Forecasted Costs ($) to be recovered for WMP 2024 | FERC or Other Forecasted Units to be recovered for WMP 2024 | FERC or Other Forecasted Costs ($) to be recovered for WMP 2025 | FERC or Other Forecasted Units to be recovered for WMP 2025 | Comments
AI-01
AI-02
AI-03
AI-04
AI-05
AI-06
AI-07
AI-08
AI-09
AI-10
AI-11
CO-01
CO-02
CO-04
CO-05
EP-01
EP-02
EP-04
EP-06
EP-07
EP-08
EP-09
GH-01 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0
GH-02
GH-03
GH-04 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0
GH-05
GH-06
GH-07
GH-08
GH-09
GH-10
GH-11
GM-01
GM-02
GM-03
GM-06
GM-07
GM-08
GM-09
PS-01
PS-02
PS-05
PS-06
PS-07
PS-08
PS-09
PS-10
PS-11
SA-01
SA-02 |  | Not Applicable |  | Not Applicable |  | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available | [18 empty] | WMP target SA-02 represents a scope of work that falls within the GRC mitigation "Line Sensors WLDFR-M07A", which covers the installation and maintenance of line sensors. The SA-02 commitment is specific to line sensor installaion and does not include the associated maintenance; therefore, no expense costs have been recorded in alignment with SA-02. For transparency and consistency, we have provided the expense adopted amounts associated with WLDFR-M07A despite them not being direcly tied to SA-02.
SA-03 |  | Not Applicable |  | Not Applicable |  | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available
SA-04
SA-05
SA-06
SA-07 |  | Not Applicable |  | Not Applicable |  | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available
SA-08 |  | Not Applicable |  | Not Applicable |  | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available
SA-09 |  | Not Applicable |  | Not Applicable |  | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available
SA-10 |  | Not Applicable |  | Not Applicable |  |  | 0 |  | 0 |  | 0 |  | Not Applicable | Not Applicable | Not Available | Not Available | Not Available | Not Available | [18 empty] | There is no expense forecast in the GRC for DFA
SA-11 |  | Not Applicable |  | Not Applicable |  |  | 0 |  | 0 |  | 0 |  | Not Applicable | Not Applicable | Not Available | Not Available | Not Available | Not Available | [18 empty] | There is no expense forecast in the GRC for EFD
SA-12 |  | Not Applicable |  | Not Applicable |  | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available
VM-01
VM-02
VM-03
VM-04
VM-05
VM-06
VM-07
VM-08
VM-09
VM-10
VM-11
VM-12
VM-13
VM-14
VM-15
VM-16
VM-17
VM-18
VM-19
VM-20
VM-21
VM-22
8.4.6
8.4.4
8.1.2.3
8.1.2.6
8.1.2.9
8.1.2.7
8.1.2.11
8.1.2.12
8.1.8.3
8.2.3.2
8.1.9
8.1.2.4
8.3.6
8.3.4
8.2.3.8
8.2.3.7
8.2.3.6
8.2.7
7
6
5.4.5
8.4.3
8.1.4
8.1.8.2
8.2.2.3

## non-HFTD, CapEx (4 of 5)
non-HFTD, CapEx Costs and Recoveries | Section A: WMP Cost and Unit Data | [5 empty] | Section B: Costs and Units Authorized in Last GRC | [5 empty] | Section C: Costs and Units Forecast to be Requested in the Next GRC | [5 empty] | Section D: Costs Recorded via Application (Memo or Balancing Account) | [5 empty] | Section E: SB 884 Activity | [5 empty] | Section F: FERC or Other
Report $ in Thousands | Costs and Amounts by Year | [5 empty] | WMP Year 1 |  | WMP Year 2 |  | WMP Year 3 |  | WMP Year 1 |  | WMP Year 2 |  | WMP Year 3 |  | WMP Year 1 |  | WMP Year 2 |  | WMP Year 3 |  | WMP Year 1 |  | WMP Year 2 |  | WMP Year 3 |  | WMP Year 1 |  | WMP Year 2 |  | WMP Year 3
Mitigation Initiative Cost Reporting Identification Code | WMP 2023 Recorded ($ in 1,000s) | WMP 2023 Number of Units (where applicable) | WMP 2024 Forecast ($ in 1,000s) | WMP 2024 Number of Units (where applicable) | WMP 2025 Forecast ($ in 1,000s) | WMP 2025 Number of Units (where applicable) | Costs authorized in last GRC (2023) ($) for WMP 2023 | Units authorized in last GRC (2023) for WMP 2023 | Costs authorized in last GRC (2023) ($) for WMP 2024 | Units authorized in last GRC (2023) for WMP 2024 | Costs authorized in last GRC (2023) ($) for WMP 2025 | Units authorized in last GRC (2023) for WMP 2025 | Costs to be requested in next GRC (2027) ($) for WMP 2023 | Units to be requested in next GRC (2027) for WMP 2023 | Costs to be requested in next GRC (2027) ($) for WMP 2024 | Units to be requested in next GRC (2027) for WMP 2024 | Costs to be requested in next GRC (2027) ($) for WMP 2025 | Units to be requested in next GRC (2027) for WMP 2025 | Costs ($ in 1,000s) recorded via Application for WMP 2023 | Units recorded via Application for WMP 2023 | Costs ($) recorded via Application for WMP 2024 | Units recorded via Application for WMP 2024 | Costs ($) recorded via Application for WMP 2025 | Units recorded via Application for WMP 2025 | SB 884 Activity, Forecasted Costs ($) for WMP 2023 | SB 884 Activity, Forecasted Units for WMP 2023 | SB 884 Activity, Forecasted Costs ($) for WMP 2024 | SB 884 Activity, Forecasted Units for WMP 2024 | SB 884 Activity, Forecasted Costs ($) for WMP 2025 | SB 884 Activity, Forecasted Units for WMP 2025 | FERC or Other Forecasted Costs ($) to be recovered for WMP 2023 | FERC or Other Forecasted Units to be recovered for WMP 2023 | FERC or Other Forecasted Costs ($) to be recovered for WMP 2024 | FERC or Other Forecasted Units to be recovered for WMP 2024 | FERC or Other Forecasted Costs ($) to be recovered for WMP 2025 | FERC or Other Forecasted Units to be recovered for WMP 2025 | Comments
AI-01
AI-02
AI-03
AI-04
AI-05
AI-06
AI-07
AI-08
AI-09
AI-10
AI-11
CO-01
CO-02
CO-04
CO-05
EP-01
EP-02
EP-04
EP-06
EP-07
EP-08
EP-09
GH-01 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0
GH-02
GH-03
GH-04 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0
GH-05
GH-06
GH-07
GH-08
GH-09
GH-10
GH-11
GM-01
GM-02
GM-03
GM-06
GM-07
GM-08
GM-09
PS-01
PS-02
PS-05
PS-06
PS-07
PS-08
PS-09
PS-10
PS-11
SA-01
SA-02 |  | Not Applicable |  | Not Applicable |  | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available
SA-03 |  | Not Applicable |  | Not Applicable |  | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available
SA-04
SA-05
SA-06
SA-07 |  | Not Applicable |  | Not Applicable |  | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available
SA-08 |  | Not Applicable |  | Not Applicable |  | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available
SA-09 |  | Not Applicable |  | Not Applicable |  | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available
SA-10 |  | Not Applicable |  | Not Applicable |  | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available
SA-11 |  | Not Applicable |  | Not Applicable |  | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available
SA-12 |  | Not Applicable |  | Not Applicable |  | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available
VM-01
VM-02
VM-03
VM-04
VM-05
VM-06
VM-07
VM-08
VM-09
VM-10
VM-11
VM-12
VM-13
VM-14
VM-15
VM-16
VM-17
VM-18
VM-19
VM-20
VM-21
VM-22
8.4.6
8.4.4
8.1.2.3
8.1.2.6
8.1.2.9
8.1.2.7
8.1.2.11
8.1.2.12
8.1.8.3
8.2.3.2
8.1.9
8.1.2.4
8.3.6
8.3.4
8.2.3.8
8.2.3.7
8.2.3.6
8.2.7
7
6
5.4.5
8.4.3
8.1.4
8.1.8.2
8.2.2.3

## non-HFTD, OpEx (5 of 5)
non-HFTD, OpEx Costs and Recoveries | Section A: WMP Cost and Unit Data | [5 empty] | Section B: Costs and Units Authorized in Last GRC | [5 empty] | Section C: Costs and Units Forecast to be Requested in the Next GRC | [5 empty] | Section D: Costs Recorded via Application (Memo or Balancing Account) | [5 empty] | Section E: SB 884 Activity | [5 empty] | Section F: FERC or Other
Report $ in Thousands | Costs and Amounts by Year | [5 empty] | WMP Year 1 |  | WMP Year 2 |  | WMP Year 3 |  | WMP Year 1 |  | WMP Year 2 |  | WMP Year 3 |  | WMP Year 1 |  | WMP Year 2 |  | WMP Year 3 |  | WMP Year 1 |  | WMP Year 2 |  | WMP Year 3 |  | WMP Year 1 |  | WMP Year 2 |  | WMP Year 3
Mitigation Initiative Cost Reporting Identification Code | WMP 2023 Recorded ($ in 1,000s) | WMP 2023 Number of Units (where applicable) | WMP 2024 Forecast ($ in 1,000s) | WMP 2024 Number of Units (where applicable) | WMP 2025 Forecast ($ in 1,000s) | WMP 2025 Number of Units (where applicable) | Costs authorized in last GRC (2023) ($) for WMP 2023 | Units authorized in last GRC (2023) for WMP 2023 | Costs authorized in last GRC (2023) ($) for WMP 2024 | Units authorized in last GRC (2023) for WMP 2024 | Costs authorized in last GRC (2023) ($) for WMP 2025 | Units authorized in last GRC (2023) for WMP 2025 | Costs to be requested in next GRC (2027) ($) for WMP 2023 | Units to be requested in next GRC (2027) for WMP 2023 | Costs to be requested in next GRC (2027) ($) for WMP 2024 | Units to be requested in next GRC (2027) for WMP 2024 | Costs to be requested in next GRC (2027) ($) for WMP 2025 | Units to be requested in next GRC (2027) for WMP 2025 | Costs ($ in 1,000s) recorded via Application for WMP 2023 | Units recorded via Application for WMP 2023 | Costs ($) recorded via Application for WMP 2024 | Units recorded via Application for WMP 2024 | Costs ($) recorded via Application for WMP 2025 | Units recorded via Application for WMP 2025 | SB 884 Activity, Forecasted Costs ($) for WMP 2023 | SB 884 Activity, Forecasted Units for WMP 2023 | SB 884 Activity, Forecasted Costs ($) for WMP 2024 | SB 884 Activity, Forecasted Units for WMP 2024 | SB 884 Activity, Forecasted Costs ($) for WMP 2025 | SB 884 Activity, Forecasted Units for WMP 2025 | FERC or Other Forecasted Costs ($) to be recovered for WMP 2023 | FERC or Other Forecasted Units to be recovered for WMP 2023 | FERC or Other Forecasted Costs ($) to be recovered for WMP 2024 | FERC or Other Forecasted Units to be recovered for WMP 2024 | FERC or Other Forecasted Costs ($) to be recovered for WMP 2025 | FERC or Other Forecasted Units to be recovered for WMP 2025 | Comments
AI-01
AI-02
AI-03
AI-04
AI-05
AI-06
AI-07
AI-08
AI-09
AI-10
AI-11
CO-01
CO-02 | [36 empty] | Community surveys as a unit cannot be broken out into HFTD vs non-HFTD
CO-04
CO-05
EP-01
EP-02
EP-04
EP-06
EP-07
EP-08
EP-09
GH-01 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0
GH-02
GH-03
GH-04 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0
GH-05
GH-06
GH-07
GH-08
GH-09
GH-10
GH-11
GM-01
GM-02
GM-03
GM-06
GM-07
GM-08
GM-09
PS-01
PS-02
PS-05
PS-06
PS-07
PS-08
PS-09
PS-10
PS-11
SA-01
SA-02 |  | Not Applicable |  | Not Applicable |  | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available
SA-03 |  | Not Applicable |  | Not Applicable |  | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available
SA-04
SA-05
SA-06
SA-07 |  | Not Applicable |  | Not Applicable |  | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available
SA-08 |  | Not Applicable |  | Not Applicable |  | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available
SA-09 |  | Not Applicable |  | Not Applicable |  | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available
SA-10 | [6 empty] | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available
SA-11 | [6 empty] | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available
SA-12 |  | Not Applicable |  | Not Applicable |  | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available
VM-01
VM-02
VM-03
VM-04
VM-05
VM-06
VM-07
VM-08
VM-09
VM-10
VM-11
VM-12
VM-13
VM-14
VM-15
VM-16
VM-17
VM-18
VM-19
VM-20
VM-21
VM-22
8.4.6
8.4.4
8.1.2.3
8.1.2.6
8.1.2.9
8.1.2.7
8.1.2.11
8.1.2.12
8.1.8.3
8.2.3.2
8.1.9
8.1.2.4
8.3.6
8.3.4
8.2.3.8
8.2.3.7
8.2.3.6
8.2.7
7
6
5.4.5
8.4.3
8.1.4
8.1.8.2
8.2.2.3

## Account_Tracking (hidden)
Date:
Wildfire Mitigation Initiative | Wildfire Mitigation Category | Utility Initiative Tracking ID | GRC Activity Code (MAT, WBS, Budget Code/Cost Center) | FERC USOA | Authorized Amount, Balancing or Memorandum Account Name | CPUC Proceeding Number | CPUC Decision Number | SCE Accounting Number | Any Other ID Number | GRC Authorized Expenditures | [7 empty] | GRC Authorized Revenue Requirement (Entered Rates) | [7 empty] | Recorded Cost Expenditures | [7 empty] | Recorded Costs Revenue Requirement (Entered Rates) | [7 empty] | Recorded Costs Revenue Requirement (Yet to Enter Rates) | [7 empty] | Non-GRC Authorized Expenditures | [7 empty] | Non-GRC Authorized Revenue Requirement (Entered Rates) | [7 empty] | Non-GRC Recorded Cost Expenditures | [7 empty] | Non-GRC Recorded Costs Revenue Requirement (Entered Rates) | [7 empty] | Non-GRC Recorded Costs Revenue Requirement (Yet to Enter Rates) | [7 empty] | Pending GRC Expenditures | [7 empty] | Pending GRC Revenue Requirement | [7 empty] | Pending Non-GRC Expenditures | [7 empty] | Pending Non-GRC Revenue Requests | [7 empty] | Account Total |  |  |  | Third-Party or Other Funding Source | Wildfire Mitigation Program Total |  |  |  | Notes
[10 empty] | CapEX |  |  |  | OpEx |  |  |  | CapEX |  |  |  | OpEx |  |  |  | CapEX |  |  |  | OpEx |  |  |  | CapEX |  |  |  | OpEx |  |  |  | CapEX |  |  |  | OpEx |  |  |  | CapEX |  |  |  | OpEx |  |  |  | CapEX |  |  |  | OpEx |  |  |  | CapEX |  |  |  | OpEx |  |  |  | CapEX |  |  |  | OpEx |  |  |  | CapEX |  |  |  | OpEx |  |  |  | CapEX |  |  |  | OpEx |  |  |  | CapEX |  |  |  | OpEx |  |  |  | CapEX |  |  |  | OpEx |  |  |  | CapEX |  |  |  | OpEx |  |  |  | Entered Rates | Not Yet in Rates | Entered Rate Base | Not Yet in Rate Base |  | Entered Rates | Not Yet in Rates | Entered Rate Base | Not Yet in Rate Base
[10 empty] | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD
[10 empty] | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $
Retainment of Inspectors and Internal Workforce Development | 1. Develop a plan to increase retention over time for trained and qualified inspectors. 2. Develop a plan to focus on increasing and sustaining a consistent, year-over-year internal workforce that builds on existing experience and mentors new employees for asset inspections. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives, p. 289 | AI-01 | [119 empty] | 0 | 0 | 0 | 0
Detailed Inspection Transmission – Ground | 2023: Complete detailed ground inspections on 27,000 transmission structures in PG&E’s asset registry as of January 1, 2023. 2024: Complete detailed ground inspections on approximately 20,000 transmission structures in PG&E’s asset registry as of January 1, 2024. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in accordance with Section 12.3 of the 2023-2025 WMP Process and Evaluation Guidelines. 2025: Complete detailed ground inspections on approximately 22,000 transmission structures in PG&E’s asset registry as of January 1, 2025. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in 2024 as part of the 2025 WMP Annual Update. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 336 | AI-02 | [119 empty] | 0 | 0 | 0 | 0
Develop Distribution Aerial Inspections program | Evaluate the continued use of aerial inspections for distribution overhead equipment. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 289 | AI-03 | [119 empty] | 0 | 0 | 0 | 0
Detailed Inspection Transmission – Aerial | 2023: Complete detailed aerial inspections on 24,000 transmission structures in PG&E’s asset registry as of January 1, 2023. 2024: Complete detailed aerial inspections on approximately 20,000 transmission structures in PG&E’s asset registry as of January 1, 2024. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in accordance with Section 12.3 of the 2023-2025 WMP Process and Evaluation Guidelines. 2025: Complete detailed aerial inspections on approximately 19,000 transmission structures in PG&E’s asset registry as of January 1, 2025. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in 2024 as part of the 2025 WMP Annual Update. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 336 | AI-04 | [119 empty] | 0 | 0 | 0 | 0
Detailed Inspection Transmission – Climbing | 2023: Complete detailed climbing inspections of 1,700 transmission structures in PG&E’s asset registry as of January 1, 2023. 2024: Complete detailed climbing inspections on approximately 1,200 transmission structures in PG&E’s asset registry as of January 1, 2024. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in accordance with Section 12.3 of the 2023-2025 WMP Process and Evaluation Guidelines. 2025: Complete detailed climbing inspections on approximately 1,200 transmission structures in PG&E’s asset registry as of January 1, 2025. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in 2024 as part of the 2025 WMP Annual Update. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 337 | AI-05 | [119 empty] | 0 | 0 | 0 | 0
Perform transmission IR inspections | 2023: Infrared patrols will be performed on 4,000 circuit miles of energized transmission line. 2024: Infrared patrols will be performed on 4,000 circuit miles of energized transmission line. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in accordance with Section 12.3 of the 2023 -2025 WMP Process and Evaluation Guidelines. 2025: Infrared patrols will be performed on 3,500 circuit miles of energized transmission line. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in 2024 as part of the 2025 WMP Annual Update. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 336 | AI-06 | [119 empty] | 0 | 0 | 0 | 0
Detailed Ground and Aerial Inspections - Distribution | 2023: Complete detailed ground inspections on 234,648 distribution poles, which were identified in PG&E's asset registry as of December 27, 2022. As part of the target number above, detailed ground inspections will be completed on a 42,470-pole subset of distribution poles in Severe, Extreme, or High plat maps by July 31, 2023, which were identified in PG&E's asset registry as of December 27, 2022. Similarly, detailed ground inspections will be completed on a 30,062-pole subset of distribution poles in Medium plat maps by September 30, 2023, which were identified in PG&E's asset registry as of December 27, 2022. Lastly, detailed ground inspections will be completed on a 162,116-pole subset of distribution poles in Low plat maps by December 31, 2023, which were identified in PG&E's asset registry as of December 27, 2022. 2024: Complete detailed inspections on approximately 220,016 distribution poles, which will be identified in PG&E's asset registry as of December 27, 2022. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E's asset registry and updated in accordance with Section 12.3 of the 2023-2025 WMP Process and Evaluation Guidelines. 2025: Complete detailed inspections on approximately 244,000 distribution poles, which will be identified in PG&E's asset registry as of December 27, 2022. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E's asset registry and updated in 2024 as part of the 2025 WMP Annual Update. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 338 | AI-07 | [119 empty] | 0 | 0 | 0 | 0
Supplemental Inspections - Substation Distribution | 2023: Complete supplemental inspections on 52 distribution substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2024: Complete supplemental inspections on 76 distribution substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2025: Complete supplemental inspections on 78 distribution substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 339 | AI-08 | [119 empty] | 0 | 0 | 0 | 0
Supplemental Inspections - Substation Transmission | 2023: Complete supplemental inspections on 34 transmission substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2024: Complete supplemental inspections on 36 transmission substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2025: Complete supplemental inspections on 41 transmission substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 339 | AI-09 | [119 empty] | 0 | 0 | 0 | 0
Supplemental Inspections - Hydroelectric Substations and Powerhouses | 2023: Complete supplemental inspections on 41 Hydroelectric Generation Substations and Powerhouses. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2024: Complete supplemental inspections on 46 Hydroelectric Generation Substations and Powerhouses. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2025: Complete supplemental inspections on 40 Hydroelectric Generation Substations and Powerhouses. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 339 | AI-10 | [119 empty] | 0 | 0 | 0 | 0
Filling Asset Inventory Data Gaps | Populate missing age data in the Asset Registry (using “Installation Date” data element as a proxy) to 90 percent weighted average across risk prioritized distribution and transmission equipment. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 290 | AI-11 | [119 empty] | 0 | 0 | 0 | 0
Community Engagement - Meetings | For 2023-2025, PG&E will hold annually a total of 22 community engagement meetings within the five regions of service that will include, but are not limited to, a mix of webinars, open houses, town halls, and/or answer centers. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1 PG&E's WMP Objectives p. 297 | CO-01 | [119 empty] | 0 | 0 | 0 | 0
Community Engagement - Surveys | PG&E will complete two PSPS education and outreach surveys (per year, for a total of six). 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2 PG&E's WMP Targets p. 348 | CO-02 | [119 empty] | 0 | 0 | 0 | 0
Community Engagement - Outreach to HFRA Infrastructure Customers | PG&E will perform outreach via email and/or phone to assigned Critical Infrastructure customers in the HFRA through Business Energy Solutions (assigned account managers). Outreach will cover the CWSP, including potential PSPS and EPSS impacts, and updating contact information for critical accounts in the HFRA. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1 PG&E's WMP Objectives p. 298 | CO-04 | [119 empty] | 0 | 0 | 0 | 0
Community Engagement - Outage Preparedness Campaign | PG&E will also conduct at least one direct-to-customer outage preparedness campaign annually via email and/or direct mail targeting residential customers in the PSPS more likely or EPSS program scope. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1 PG&E's WMP Objectives p. 298 | CO-05 | [119 empty] | 0 | 0 | 0 | 0
Complete PSPS and Wildfire Tabletop and Functional Exercises | Complete PSPS and Wildfire Tabletop and Functional Exercise annually in compliance with the guiding principles of the Homeland Security Exercise Evaluation Program (HSEEP). 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 296 | EP-01 | [119 empty] | 0 | 0 | 0 | 0
Maintain All Hazards planning and preparedness program | Maintain the All Hazards Planning and Preparedness Program to provide emergency response and safely and expeditiously restore service. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 296 | EP-02 | [119 empty] | 0 | 0 | 0 | 0
Expand All Hazards planning to include additional threats and scenarios | Expand the All Hazards Planning and Preparedness Program to include additional threats and scenarios. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 296 | EP-04 | [119 empty] | 0 | 0 | 0 | 0
Annually review of the Company Emergency Response Plan (CERP) and Wildfire and PSPS Annex | 3 documents (1 CERP and 2 wildfire-related annexes) (per year) 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 348 | EP-06 | [119 empty] | 0 | 0 | 0 | 0
Common Operating Picture Technology | Design and deploy a common operating picture. A common operation picture (COP) is a continuously updated overview of an incident compiled throughout an incident’s life cycle from data shared between integrated communication, information management, and intelligence and information sharing systems. The goal of a COP is real-time situational awareness across all levels of incident management and across jurisdictions. https://www.dhs.gov/publication/common-operating-picture-emergency-responders 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 297 | EP-07 | [119 empty] | 0 | 0 | 0 | 0
Threats and Hazards Identification and Risk Assessment (THIRA) updates executive briefings. | Execute a Threats and Hazards Identification and Risk Assessment (THIRA) update every three years to address changes in hazard landscape. Use information from THIRA to inform changes to the CERP and hazard annexes. According to FEMA, The THIRA is a three-step risk assessment process that helps communities understand their risks and what they need to do to address those risks. https://www.fema.gov/emergency-managers/national-preparedness/goal/risk-capability-assessment#:~:text=The%20Threat%20and%20Hazard%20Identification,hazards%20can%20affect%20our%20community%3F 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 297 | EP-08 | [119 empty] | 0 | 0 | 0 | 0
County Execute Briefings | Hold briefings with 47 counties within PG&E’s service territory after every THIRA update to support integrated planning discussions. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 297 | EP-09 | [119 empty] | 0 | 0 | 0 | 0
System Hardening - Distribution | System hardening work which includes overhead system hardening, undergrounding, and removal of overhead lines in HFTD, HFRA, or buffer zone areas except for any mileage being undergrounded and tracked separately as part of our Butte County Rebuild and other Community Rebuild efforts | GH-01 | [119 empty] | 0 | 0 | 0 | 0
Evaluate Covered Conductor Effectiveness | Update the covered conductor recorded effectiveness calculation using 2023 and 2024 outage data on the lines that have Covered Conductors for consideration in future system hardening workplans. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 289 | GH-02 | [119 empty] | 0 | 0 | 0 | 0
Evaluate and Implement Covered Conductor Effectiveness Impact on Inspections and Maintenance Standards | Evaluate the output of the Phase 1 and Phase 2 covered conductor effectiveness study to: (1) determine the impacts of the study on the maintenance and inspections standards for deployed covered conductor assets; and (2) update TD-2305M-JA02 (overhead inspections job aid), as needed. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 289 | GH-03 | [119 empty] | 0 | 0 | 0 | 0
10K Undergrounding | Undergrounding work as follows: (1) undergrounding taking place as part of System Hardening, (2) undergrounding taking place as part of the Butte County Rebuild program (including a small volume of previously hardened overhead lines that are being placed underground) or other Community Rebuild programs, and (3) any other undergrounding work performed in HFTD, HFRA, Buffer Zone, or fire rebuild areas. Undergrounding includes various mitigations includes line removal, conversion from overhead to underground and remote grid alternatives. | GH-04 | [119 empty] | 0 | 0 | 0 | 0
System Hardening - Transmission | 2023: Remove or replace 43 circuit miles of transmission conductor on lines. 2024: N/A 2025: Remove or replace 5 circuit miles of transmission conductor. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 334 | GH-05 | [119 empty] | 0 | 0 | 0 | 0
System Hardening - Transmission Shunt Splices | 2023: Install shunt splice(s) on 20 transmission lines. 2024: Install shunt splice(s) on 22 transmission lines. 2025: Install shunt splice(s) on 25 transmission lines. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 335 | GH-06 | [119 empty] | 0 | 0 | 0 | 0
Distribution Protective Devices | 2023: Install and SCADA commission 75 new SCADA protective devices (Line Recloser, Fuse Saver, or Interrupter). 2024: N/A 2025: N/A 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 335 | GH-07 | [119 empty] | 0 | 0 | 0 | 0
Surge Arrestor - Removals | 2023: Remove 663 non-exempt surge arrestors (based on the known population as of 01/12/2023) where known grounding issues exist. If no non-exempt surge arrestor is identified at a location during pre-field work, the unit will be resolved, and the notification will be canceled. Canceled notifications will count towards this target. 2024: N/A 2025: N/A 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 335 | GH-08 | [119 empty] | 0 | 0 | 0 | 0
Distribution Line Motor Switch Operator (MSO) - Replacements | 2023: Replace or remove 20 MSOs (from the 47 identified as of January 26, 2023). 2024: Replace or remove the remaining MSOs from the 47 identified, as of January 26, 2023. 2025: N/A 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 335 | GH-09 | [119 empty] | 0 | 0 | 0 | 0
Non-Exempt Expulsion Fuse - Removal | 2023: Remove non-exempt expulsion fuses/ cutouts from 3,000 fuse locations identified on distribution poles. 2024: Remove non-exempt expulsion fuses/ cutouts from 3,000 fuse locations identified on distribution poles. 2025: Remove non-exempt expulsion fuses/ cutouts from approximately 1,400 fuse locations (based on known population as of 1/26/23) identified on distribution poles. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 335 | GH-10 | [119 empty] | 0 | 0 | 0 | 0
System Hardening – Transmission Conductor Segment Replacement | 2023: N/A 2024: N/A 2025: Replace conductor segments on 2 transmission lines 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 335 | GH-11 | [119 empty] | 0 | 0 | 0 | 0
Asset Inspections - Quality Assurance | 2023: Perform system inspection QA audits on QC completed locations and achieve the associated quality pass rates for each asset inspection program as specified below: Transmission Ground Inspection - HFTD/HFRA (Field): 500 audit locations*; 92% pass rate Distribution Ground Inspections - HFTD/HFRA (Field): 1,500 audit locations*; 82% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. 2024: Perform system inspection QA audits on QC completed locations and achieve the associated quality pass rates for each asset inspection program as specified below: Transmission Inspection - HFTD/HFRA: 500 audit locations*; 94% pass rate Distribution Inspections - HFTD/HFRA: 1,500 audit locations*; 90% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. 2025: Perform system inspection QA audits on QC completed locations and achieve the associated quality pass rates for each asset inspection program as specified below: Transmission Ground Inspection - HFTD/HFRA (Field): 500 audit locations*; 95% pass rate Distribution Ground Inspections - HFTD/HFRA (Field): 1,500 audit locations*; 95% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. | GM-01 | [119 empty] | 0 | 0 | 0 | 0
HFTD/HFRA Open Tag Reduction - Transmission | PG&E will eliminate the known 16,831 HFTD and HFRA transmission Ignition Risk tags (tags found prior to January 1, 2023, with required end dates in 2023 or earlier). | GM-02 | [119 empty] | 0 | 0 | 0 | 0
HFTD/HFRA Open Tag Reduction - Distribution Backlog | 2023: Close 52,000 distribution EC notifications, which at a minimum 29,000 are distribution backlog ignition risk EC notifications. Backlog is defined as the open ignition EC notifications known as of January 5, 2023, and found prior to Jan 1, 2023, in HFTD/HFRA locations. 2024: Close at least 25,000 additional EC notifications on top of closing an equivalent number of EC notifications created in HFRA/HFTD locations in 2024. Based on the forecasted amount of new EC notifications, we expect a total forecasted execution plan of 89,000 EC notifications for 2024. Of these EC notifications, we expect to close 46,000 distribution backlog ignition risk EC notifications with the remaining balance to be from backlog or newly identified EC notifications. 2025: Close at least 25,000 additional EC notifications on top of closing an equivalent number of EC notifications created in HFRA/HFTD locations in 2025. Based on the forecasted amount of new EC notifications, we expect a total forecasted execution plan of 92,000 EC notifications for 2025. Of these EC notifications, we expect to close 63,747 distribution backlog ignition risk EC notifications with the remaining balance to be from backlog or newly identified EC notifications. | GM-03 | [119 empty] | 0 | 0 | 0 | 0
EPSS - Down Conductor Detection (DCD) | 2023: Make capable for DCD 500 protective device controllers or relays. This count includes protection devices that due to repair status cannot receive the DCD settings, and circuit reconfiguration resulting in descoping of device. 2024: Make capable for DCD 400 protective device controllers or relays. This count includes protection devices that due to repair status cannot receive the DCD settings, and circuit reconfiguration resulting in descoping of device. 2025: Make capable for DCD 250 protective device controllers or relays. This count includes protection devices that due to repair status cannot receive the DCD settings, and circuit reconfiguration resulting in descoping of device. | GM-06 | [119 empty] | 0 | 0 | 0 | 0
Updates on EPSS Reliability Study | Provide annually an updated EPSS reliability impact study per ACI PG&E-22-32 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 290 | GM-07 | [119 empty] | 0 | 0 | 0 | 0
Eliminate HFTD/HFRA Distribution Backlog | Eliminate PG&E’s HFTD/HFRA EC notifications distribution backlog* by 2029 and have all HFTD/HFRA EC notifications in compliance with GO 95 Rule 18 barring External Factors. Backlog is defined as the open ignition EC notifications known as of January 5, 2023, and found prior to Jan 1, 2023, in HFTD/HFRA locations | GM-08 | [119 empty] | 0 | 0 | 0 | 0
Asset Inspection – Quality Control | 2023: Perform system inspection QC audits and achieve the associated quality pass rates for each asset inspection program as specified below: System Inspection Transmission - HFTD (Desktop): 20,000 audit locations*; 90% pass rate 2024: Perform system inspection QC audits and achieve the associated quality pass rates for each asset inspection program as specified below: System Inspection Transmission - HFTD: 16,300 audit locations*; 92% pass rate 2025: Perform system inspection QC audits and achieve the associated quality pass rates for each asset inspection program as specified below: System Inspection Transmission - HFTD (Desktop): 16,000 audit locations*; 95% pass rate | GM-09 | [119 empty] | 0 | 0 | 0 | 0
Evaluate enhancements for the PSPS Transmission guidance | Evaluate enhancements for the PSPS Transmission guidance to enhance focus of PSPS events. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 298 | PS-01 | [119 empty] | 0 | 0 | 0 | 0
Evaluate incorporation of approved IPW enhancements into the PSPS Distribution guidance | Evaluate incorporation of approved IPW enhancements into the PSPS Distribution guidance to enhance focus of PSPS events. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 298 | PS-02 | [119 empty] | 0 | 0 | 0 | 0
Evaluate the transition of the Portable Battery Program to permanent battery solutions | Evaluate the transition of the Portable Battery Program to permanent battery solutions for PG&E customers at risk of PSPS or EPSS, focusing on but not limited to AFN, MBL, and self-identified vulnerable populations. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 299 | PS-05 | [119 empty] | 0 | 0 | 0 | 0
Provide 12,000 cumulative new or replacement portable and permanent batteries to PG&E customers at risk of PSPS or EPSS, focusing on but not limited to AFN, MBL, and self-identified vulnerable populations. | 2023: Provide 4,000 cumulative new or replacement portable batteries to PG&E customers. 2024: Provide 4,000 cumulative new or replacement portable batteries to PG&E customers 2025: Provide 3,300(i) cumulative new or replacement portable batteries to PG&E customers 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 348 | PS-06 | [119 empty] | 0 | 0 | 0 | 0
Reduce PSPS impacts by ~38k customer events (2.4%) for 2023-2025 period by completing planned Wildfire mitigation projects including but not limited to MSO switch replacements and undergrounding. | 2023: 15,000 customer events based on Wildfire mitigation projects including but not limited to MSO replacements and Undergrounded miles planned for 2023. 2024: 9,980 customer events based on Wildfire mitigation projects including but not limited to MSO replacements and Undergrounded miles planned for 2024.(k) (k): Target unit for 2024 reflects the approved 2024 Change Order Decision. The target unit is corrected to show the incremental number (not cumulative). This is consistent with Table PG&E-9-5. 2025: 13,000(i) customer events based on Wildfire mitigation projects including but not limited to MSO replacements and Undergrounded miles planned for 2025.(l) (i): The target has been updated for 2025. See PG&E’s 2025 WMP Update for more information about the target change. (l): Target unit for 2025 is corrected to show the incremental number (not cumulative). This is consistent with Table PG&E-9-5. The incremental 2025 target unit in the base 2023-2025 WMP was 22,000. We have updated the target to 13,000 for 2025. See PG&E’s 2025 WMP Update for more information about the target change. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 349 | PS-07 | [119 empty] | 0 | 0 | 0 | 0
Evaluate emerging technologies to reduce PSPS customer impact | Evaluate emerging technologies for transmission and distribution that may further reduce scale, scope, or frequency of PSPS. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 299 | PS-08 | [119 empty] | 0 | 0 | 0 | 0
Reduce PSPS impacts via Undergrounding | Reduce PSPS size, duration, or frequency over the next ten years as part of our 10,000-mile undergrounding program. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 299 | PS-09 | [119 empty] | 0 | 0 | 0 | 0
Continue sharing PSPS lessons learned | Continue sharing PSPS lessons learned and best practices with CA IOUs through monthly meetings focused on PSPS. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 300 | PS-10 | [119 empty] | 0 | 0 | 0 | 0
Pilot using drones for PSPS restoration | Pilot using drones for PSPS restoration and/or damage assessment to improve PSPS outage restoration time. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 300 | PS-11 | [119 empty] | 0 | 0 | 0 | 0
Artificial Intelligence (AI) in Wildfire Cameras | Enable Artificial Intelligence processing of Wildfire Camera Data to provide automated wildfire notifications in the internal PG&E monitoring tool (Wildfire Incident Viewer). 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 292 | SA-01 | [119 empty] | 0 | 0 | 0 | 0
Line Sensor - Installations | 2023: Install Line Sensor devices on 40 circuits. 2024: Install Line Sensor devices on 40 circuits. 2025: Install Line Sensor devices on 40 circuits. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 347 | SA-02 | [119 empty] | 0 | 0 | 0 | 0
EFD and DFA Reporting | Develop scalable processes to: (a) analyze alarms and alerts from Early Fault Detection (EFD) and DFA sensors; (b) conduct field investigation and reporting; (c) track identified mitigations to completion; and (d) track effectiveness of issue identification and remediation using EFD/DFA technologies. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 293 | SA-03 | [119 empty] | 0 | 0 | 0 | 0
FPI and IPW Modeling - Revision Evaluation | Evaluate enhancements to the FPI model and the Ignition Probability Weather model. This involves testing new features and types of model configurations that could improve model skill. At present we do not know if model skills can be improved but we will attempt to do so. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 293 | SA-04 | [119 empty] | 0 | 0 | 0 | 0
Evaluate FPI and IPW Modeling enhancements in 2023 - 2025 | Evaluate enhancements to the FPI (Fire Potential Index) model and the IPW (Ignition Probability Weather) model in 2023. This involves testing new features and types of model configurations that could improve model skill. For example, one of the features that will be evaluated for IPW is covered conductor and EPSS on the system. If covered conductor, EPSS, or other model enhancements, do not improve model skill, it will not be deployed as a part of the model improvement. At present we do not know if model skill can be improved but we will attempt to do so in 2023. If model skill can be improved and is approved, we plan to operationalize the new models in 2024 and continue operations in 2025. We do not know if any new models developed will be approved for operations by PG&E’s Wildfire risk governance committee. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 294 | SA-05 | [119 empty] | 0 | 0 | 0 | 0
Evaluate FPI and IPW Modeling enhancements in 2026 - 2032 | Evaluate enhancements to the FPI (Fire Potential Index) model and the IPW (Ignition Probability Weather) model in the 2026-2033 period. This work involves testing new features and types of model configurations that could improve model forecasting ability. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 294 | SA-06 | [119 empty] | 0 | 0 | 0 | 0
Monitor and evaluate the Cameras AI system’s performance | In partnership with Digital Path (the AI vendor that works with us and other agencies on the broader camera network) monitor and evaluate the AI system’s performance. Explore additional features and inputs to further enhance the system. At present we do not know what these enhancements will be specifically, however we will look for opportunities to explore best practices and incorporate enhancements with the vendor. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 295 | SA-07 | [119 empty] | 0 | 0 | 0 | 0
Evaluate the Cameras AI system functionalities and technologies | In partnership with Digital Path and its collaboration with other camera sponsors, evaluate the AI system for opportunities to test new functionalities and newly developed break-through technologies. We will also explore new best practices to ensure the ongoing effectiveness of the system. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 295 | SA-08 | [119 empty] | 0 | 0 | 0 | 0
EFD and DFA Reporting | Perform a feasibility study on the use of EFD/DFA technologies to successfully identify incipient failures as a supplement to field inspections. If feasible, complete a data driven proposal for integrating sensor findings into the inspection program. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 295 | SA-09 | [119 empty] | 0 | 0 | 0 | 0
Distribution Fault Anticipation (DFA) Installations | 2023: Install 5 Distribution Fault Anticipation (DFA) sensors on circuits.(g) One sensor will be installed per circuit at the initiating substation. 2024: Install 15 Distribution Fault Anticipation (DFA) sensors on circuits feeding into HFTD areas or HFRA. One sensor will be installed per circuit at the initiating substation. 2025: Install 15 Distribution Fault Anticipation (DFA) sensors on circuits feeding into HFTD areas or HFRA. One sensor will be installed per circuit at the initiating substation. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 348 | SA-10 | [119 empty] | 0 | 0 | 0 | 0
Early Fault Detection (EFD) Installations | 2023: Install Early Fault Detection (EFD) sensors on 2 circuits.(h) 2024: Install Early Fault Detection (EFD) sensors on 2 circuits. 2025: Install Early Fault Detection (EFD) sensors on 4 circuits. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 348 | SA-11 | [119 empty] | 0 | 0 | 0 | 0
Evaluate the use and effectiveness of real-time monitoring tools | Each year, we will evaluate and discuss our situational awareness tools internally, as well as with other IOUs. These evaluative discussions will include reviewing observations of our various situational awareness tools and identifying potential areas for improvement. We will also discuss best practices and lessons learned. These discussions will help inform potential changes to what situational awareness tools we incorporate, as well as how they are incorporated. This may include equipment upgrades, new tech integrations, model improvements, and enhanced data initiatives. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 296 | SA-12 | [119 empty] | 0 | 0 | 0 | 0
LiDAR Data Collection - Transmission | 2023: Collect LiDAR data of the Transmission System (17,500 circuit miles). The Transmission System circuit miles include both HFTD / HFRA and non-HTFD Transmission circuit miles. 2024: Collect LiDAR data of the Transmission System (17,500 circuit miles). The Transmission System circuit miles include both HFTD / HFRA and non-HFTD Transmission circuit miles. 2025: Collect LiDAR data of the Transmission System (17,500 circuit miles). The Transmission System circuit miles include both HFTD / HFRA and non-HFTD Transmission circuit miles. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 342 | VM-01 | [119 empty] | 0 | 0 | 0 | 0
Pole Clearing Program | 2023: Inspect, clear, and maintain, where clearing is necessary, 77,503 poles per Vegetation Control Standard TD-7112S. 2024: 2024 pole count to be adjusted by the ending pole population in the previous year (2023) poles per Vegetation Control Standard TD-7112S will be inspected, cleared, and maintained where clearing is necessary. 2025: 2025 pole count to be adjusted by the ending pole population in the previous year (2024) poles per Vegetation Control Standard TD-7112S will be inspected, cleared, and maintained where clearing is necessary. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 342 | VM-02 | [119 empty] | 0 | 0 | 0 | 0
Focused Tree Inspection (FTI) | 2023: Complete focus tree inspections of 250 Circuit Miles in defined Areas of Concern (AOC) locations.(c) 2024: Within Areas of Concern (AOC) locations, complete 1,500 circuit miles of FTI inspection which includes performing a level 2 inspection on all potential strike trees. 2025: Within Areas of Concern (AOC) locations complete 1,500 circuit miles of FTI inspection which includes performing a level 2 inspection on all potential strike trees. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 343 | VM-03 | [119 empty] | 0 | 0 | 0 | 0
Tree Removal Inventory (TRI) | 2023: Mitigate(d)15,000 trees identified from the legacy EVM program. 2024: Mitigate(d) 20,000 trees identified from the legacy EVM program. 2025: Mitigate(d) 25,000 trees identified from the legacy EVM program. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 343 | VM-04 | [119 empty] | 0 | 0 | 0 | 0
Defensible Space Inspections - Distribution Substation | 2023: Complete defensible space inspections in alignment with the guidelines set forth in LAND 4001P-01 at 131 distribution substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2024: Complete defensible space inspections in alignment with the guidelines set forth in LAND 4001P-01 at 131 distribution substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2025: Complete defensible space inspections in alignment with the guidelines set forth in LAND 4001P-01 at 131 distribution substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 343 | VM-05 | [119 empty] | 0 | 0 | 0 | 0
Defensible Space Inspections - Transmission Substation | 2023: Complete defensible space inspections in alignment with the guidelines set forth in LAND 4001P-01 at 55 transmission substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2024: Complete defensible space inspections in alignment with the guidelines set forth in LAND 4001P-01 at 55 transmission substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2025: Complete defensible space inspections in alignment with the guidelines set forth in LAND 4001P-01 at 55 transmission substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 343 | VM-06 | [119 empty] | 0 | 0 | 0 | 0
Defensible Space Inspections - Hydroelectric Substations and Powerhouses | 2023: Complete defensible space inspections in alignment with the guidelines set forth in LAND 5201P-01 at 61 Hydroelectric Generation Substations and Powerhouses. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2024: Complete defensible space inspections in alignment with the guidelines set forth in LAND 5201P-01 at 61 Hydroelectric Generation Substations and Powerhouses. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2025: Complete defensible space inspections in alignment with the guidelines set forth in LAND 5201P-01 at 61 Hydroelectric Generation Substations and Powerhouses. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 344 | VM-07 | [119 empty] | 0 | 0 | 0 | 0
Vegetation Management – Quality Assurance | 2023: Perform vegetation management QA audits on QC completed locations and achieve the associated quality pass rates for each vegetation management program as specified below: Distribution Routine VM - HFTD: 2,500 audit locations*; 95% pass rate Transmission VM - HFTD: 1,200 audit locations; 95% pass rate Vegetation Control Pole Clearing - HFTD: 1,800 audit locations*; 95% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. 2024: Perform vegetation management QA audits on QC completed locations and achieve the associated quality pass rates for each vegetation management program as specified below: Distribution Routine VM - HFTD: 2,675 audit locations*; 95% pass rate Transmission VM - HFTD: 1,284 audit locations; 95% pass rate Vegetation Control Pole Clearing - HFTD: 1,926 audit locations*; 95% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. 2025: Perform vegetation management QA audits on QC completed locations and achieve the associated quality pass rates for each vegetation management program as specified below: Distribution Routine VM - HFTD: 2,862 audit locations*; 95% pass rate Transmission VM - HFTD: 1,374 audit locations*; 95% pass rate Vegetation Control Pole Clearing - HFTD: 2,061 audit locations*; 95% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 345 | VM-08 | [119 empty] | 0 | 0 | 0 | 0
Constraint Resolution Procedural Guideline | Develop a process of centralizing constraints resolution. As part of the build out of the centralized constraints team, three major categories will be addressed: customer constraints, environmental constraints (including internal PG&E procedures required to perform work) and permitting constraints (including both Land and Environmental permits). For each major constraint category build a process for addressing each constraint type, implement the new process, and create metrics to track each constraint type. Reporting will track total constraints by type and the time it takes to resolve a constraint after it has been identified. PG&E will consider creating a “right tree-right place” program, as part of the centralize Constraints Resolution process. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 8-12 Vegetation Management Implementation Objectives (3-Year Plan) p. 606 | VM-09 | [119 empty] | 0 | 0 | 0 | 0
Inspection in HFTD and HFRA supporting key vegetation management initiatives | Continue multiple inspection activities in HFTD and HFRA supporting key vegetation management initiatives 2023-2025 Wildfire Mitigation Plan R6 Revised Table 8-13 Vegetation Management Implementation Objectives (10-Year Plan) p. 607 | VM-10 | [119 empty] | 0 | 0 | 0 | 0
Enhance and refine Focus Tree Inspection – Areas of Concern (AOC) | Enhance and refine Focus Tree Inspection - Areas of Concern (AOC) development criteria and application of the AOCs to vegetation management programs. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 8-13 Vegetation Management Implementation Objectives (10-Year Plan) p. 607 | VM-11 | [119 empty] | 0 | 0 | 0 | 0
Evaluate emerging technologies | Evaluate emerging technologies to enhance focus of and streamline execution of vegetation management inspections. | VM-12 | [119 empty] | 0 | 0 | 0 | 0
Routine Ground - Transmission | 2023: Complete Routine Transmission Ground Inspection of 17,740 circuit miles as defined by Transmissions Routine LiDAR detection point data systemwide. 2024: Complete Routine Transmission Ground Inspection of 17,740 circuit miles as defined by Transmissions Routine LiDAR detection point data systemwide. 2025: Complete Routine Transmission Ground Inspection of 17,740 circuit miles as defined by Transmissions Routine LiDAR detection point data systemwide. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 345 | VM-13 | [119 empty] | 0 | 0 | 0 | 0
Transmission Second Patrol | 2023: Complete Transmission Second Patrol Inspection of 5,625 circuit miles dependent 2024: Complete Transmission Second Patrol Inspection of 5,625 circuit 2025: Complete Transmission Second Patrol Inspection of 5,625 circuit miles dependent 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 345 | VM-14 | [119 empty] | 0 | 0 | 0 | 0
Integrated Vegetation Management - Transmission | 2023: Complete Integrated Vegetation Management and Fee Inspections of 11,194 acres ROW across the Transmission systemwide 2024: Complete Integrated Vegetation Management and Fee Inspections of 6,504 acres ROW across the Transmission systemwide 2025: Complete Integrated Vegetation Management and Fee Inspections of 6,504 acres ROW across the Transmission systemwide 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 346 | VM-15 | [119 empty] | 0 | 0 | 0 | 0
Distribution Routine Patrol | 2023: Complete Distribution Routine Annual Patrol Inspection of 79,000 overhead circuit miles system wide 2024: Complete Distribution Routine Annual Patrol Inspection of 78,650 overhead circuit miles system wide 2025: Complete Distribution Routine Annual Patrol Inspection of 78,200 overhead circuit miles system wide 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 346 | VM-16 | [119 empty] | 0 | 0 | 0 | 0
Distribution Second Patrol | 2023: Complete Distribution Second Patrol Inspection of 43,600 circuit miles that are in the following map layers FHSZ, WUI, SRA, FRA, HFTD, and HFRA locations. 2024: Complete Distribution Second Patrol Inspection of 25,685 circuit miles in HFTD and HFRA locations. 2025: Complete Distribution Second Patrol Inspection of 25,685 circuit miles in HFTD and HFRA locations. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 346 | VM-17 | [119 empty] | 0 | 0 | 0 | 0
VM for Operational Mitigations (VMOM) | 2023: N/A 2024: Mitigate 6,500 trees for VM for Operational Mitigations program, on EPSS capable circuits. This target will include the previous year's carry-over work and prescriptions resulting from pro-active patrols on EPSS circuits. Future workplans will be dependent on previous year's EPSS outage data analysis. 2025: Mitigate 6,500 trees for VM for Operational Mitigations program, on EPSS capable circuits. This target will include the previous year's carry-over work and prescriptions resulting from pro-active patrols on EPSS circuits. Future workplans will be dependent on previous year's EPSS outage data analysis. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 346 | VM-18 | [119 empty] | 0 | 0 | 0 | 0
One VM Application Record Keeping Enhancement (Routine, Second Patrol) | Enhance the One VM application for Routine, and Second Patrol to include capability to capture factors for prescribing trees for removal. | VM-19 | [119 empty] | 0 | 0 | 0 | 0
Record Keeping Enhancement (VMOM, TRI) | Enhance the application for the Vegetation Management for Operational Mitigations (VMOM) - VMPI2 - and Tree Removal Inventory (TRI) - Field Maps - program to include capability to capture factors for prescribing trees for removal. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 292 | VM-20 | [119 empty] | 0 | 0 | 0 | 0
Focused Tree Inspection (FTI) Program Record Keeping Enhancement | Enhance record keeping practices for the Focused Tree Inspection program (FTI) by creating records of all potential strike trees inspected using a digitized Tree Risk Assessment form. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 292 | VM-21 | [119 empty] | 0 | 0 | 0 | 0
Vegetation Management - Quality Control | 2023: Perform vegetation management QC audits and achieve the associated quality pass rates for each vegetation management program as specified below: 2024: Perform vegetation management QC audits and achieve the associated quality pass rates for each vegetation management program as specified below: 2025: Perform vegetation management QC audits and achieve the associated quality pass rates for each vegetation management program as specified below: 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 346 | VM-22 | [119 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0

## Account Tracking
Date:
Wildfire Mitigation Initiative | Wildfire Mitigation Category | Utility Initiative Tracking ID | GRC Activity Code (MAT, WBS, Budget Code/Cost Center) | FERC USOA | Authorized Amount, Balancing or Memorandum Account Name | CPUC Proceeding Number | CPUC Decision Number | SCE Accounting Number | Any Other ID Number | GRC Authorized Expenditures | [7 empty] | GRC Authorized Revenue Requirement (Entered Rates) | [7 empty] | Recorded Cost Expenditures | [7 empty] | Recorded Costs Revenue Requirement (Entered Rates) | [7 empty] | Recorded Costs Revenue Requirement (Yet to Enter Rates) | [7 empty] | Non-GRC Authorized Expenditures | [7 empty] | Non-GRC Authorized Revenue Requirement (Entered Rates) | [7 empty] | Non-GRC Recorded Cost Expenditures | [7 empty] | Non-GRC Recorded Costs Revenue Requirement (Entered Rates) | [7 empty] | Non-GRC Recorded Costs Revenue Requirement (Yet to Enter Rates) | [7 empty] | Pending GRC Expenditures | [7 empty] | Pending GRC Revenue Requirement | [7 empty] | Pending Non-GRC Expenditures | [7 empty] | Pending Non-GRC Revenue Requests | [7 empty] | Account Total |  |  |  | Third-Party or Other Funding Source | Wildfire Mitigation Program Total |  |  |  | Notes
[10 empty] | CapEX |  |  |  | OpEx |  |  |  | CapEX |  |  |  | OpEx |  |  |  | CapEX |  |  |  | OpEx |  |  |  | CapEX |  |  |  | OpEx |  |  |  | CapEX |  |  |  | OpEx |  |  |  | CapEX |  |  |  | OpEx |  |  |  | CapEX |  |  |  | OpEx |  |  |  | CapEX |  |  |  | OpEx |  |  |  | CapEX |  |  |  | OpEx |  |  |  | CapEX |  |  |  | OpEx |  |  |  | CapEX |  |  |  | OpEx |  |  |  | CapEX |  |  |  | OpEx |  |  |  | CapEX |  |  |  | OpEx |  |  |  | CapEX |  |  |  | OpEx |  |  |  | Entered Rates | Not Yet in Rates | Entered Rate Base | Not Yet in Rate Base |  | Entered Rates | Not Yet in Rates | Entered Rate Base | Not Yet in Rate Base
[10 empty] | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD |  | HFTD |  | Non-HFTD
[10 empty] | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $ | Units | $
Retainment of Inspectors and Internal Workforce Development | 1. Develop a plan to increase retention over time for trained and qualified inspectors. 2. Develop a plan to focus on increasing and sustaining a consistent, year-over-year internal workforce that builds on existing experience and mentors new employees for asset inspections. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives, p. 289 | AI-01 | [119 empty] | 0 | 0 | 0 | 0
Detailed Inspection Transmission – Ground | 2023: Complete detailed ground inspections on 27,000 transmission structures in PG&E’s asset registry as of January 1, 2023. 2024: Complete detailed ground inspections on approximately 20,000 transmission structures in PG&E’s asset registry as of January 1, 2024. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in accordance with Section 12.3 of the 2023-2025 WMP Process and Evaluation Guidelines. 2025: Complete detailed ground inspections on approximately 22,000 transmission structures in PG&E’s asset registry as of January 1, 2025. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in 2024 as part of the 2025 WMP Annual Update. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 336 | AI-02 | [119 empty] | 0 | 0 | 0 | 0
Develop Distribution Aerial Inspections program | Evaluate the continued use of aerial inspections for distribution overhead equipment. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 289 | AI-03 | [119 empty] | 0 | 0 | 0 | 0
Detailed Inspection Transmission – Aerial | 2023: Complete detailed aerial inspections on 24,000 transmission structures in PG&E’s asset registry as of January 1, 2023. 2024: Complete detailed aerial inspections on approximately 20,000 transmission structures in PG&E’s asset registry as of January 1, 2024. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in accordance with Section 12.3 of the 2023-2025 WMP Process and Evaluation Guidelines. 2025: Complete detailed aerial inspections on approximately 19,000 transmission structures in PG&E’s asset registry as of January 1, 2025. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in 2024 as part of the 2025 WMP Annual Update. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 336 | AI-04 | [119 empty] | 0 | 0 | 0 | 0
Detailed Inspection Transmission – Climbing | 2023: Complete detailed climbing inspections of 1,700 transmission structures in PG&E’s asset registry as of January 1, 2023. 2024: Complete detailed climbing inspections on approximately 1,200 transmission structures in PG&E’s asset registry as of January 1, 2024. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in accordance with Section 12.3 of the 2023-2025 WMP Process and Evaluation Guidelines. 2025: Complete detailed climbing inspections on approximately 1,200 transmission structures in PG&E’s asset registry as of January 1, 2025. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in 2024 as part of the 2025 WMP Annual Update. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 337 | AI-05 | [119 empty] | 0 | 0 | 0 | 0
Perform transmission IR inspections | 2023: Infrared patrols will be performed on 4,000 circuit miles of energized transmission line. 2024: Infrared patrols will be performed on 4,000 circuit miles of energized transmission line. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in accordance with Section 12.3 of the 2023 -2025 WMP Process and Evaluation Guidelines. 2025: Infrared patrols will be performed on 3,500 circuit miles of energized transmission line. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E’s asset registry and updated in 2024 as part of the 2025 WMP Annual Update. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 336 | AI-06 | [119 empty] | 0 | 0 | 0 | 0
Detailed Ground and Aerial Inspections - Distribution | 2023: Complete detailed ground inspections on 234,648 distribution poles, which were identified in PG&E's asset registry as of December 27, 2022. As part of the target number above, detailed ground inspections will be completed on a 42,470-pole subset of distribution poles in Severe, Extreme, or High plat maps by July 31, 2023, which were identified in PG&E's asset registry as of December 27, 2022. Similarly, detailed ground inspections will be completed on a 30,062-pole subset of distribution poles in Medium plat maps by September 30, 2023, which were identified in PG&E's asset registry as of December 27, 2022. Lastly, detailed ground inspections will be completed on a 162,116-pole subset of distribution poles in Low plat maps by December 31, 2023, which were identified in PG&E's asset registry as of December 27, 2022. 2024: Complete detailed inspections on approximately 220,016 distribution poles, which will be identified in PG&E's asset registry as of December 27, 2022. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E's asset registry and updated in accordance with Section 12.3 of the 2023-2025 WMP Process and Evaluation Guidelines. 2025: Complete detailed inspections on approximately 244,000 distribution poles, which will be identified in PG&E's asset registry as of December 27, 2022. Please note that this projected target may require modification based on changes in the risk output. The final inspection target units will be identified in PG&E's asset registry and updated in 2024 as part of the 2025 WMP Annual Update. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 338 | AI-07 | [119 empty] | 0 | 0 | 0 | 0
Supplemental Inspections - Substation Distribution | 2023: Complete supplemental inspections on 52 distribution substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2024: Complete supplemental inspections on 76 distribution substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2025: Complete supplemental inspections on 78 distribution substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 339 | AI-08 | [119 empty] | 0 | 0 | 0 | 0
Supplemental Inspections - Substation Transmission | 2023: Complete supplemental inspections on 34 transmission substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2024: Complete supplemental inspections on 36 transmission substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2025: Complete supplemental inspections on 41 transmission substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 339 | AI-09 | [119 empty] | 0 | 0 | 0 | 0
Supplemental Inspections - Hydroelectric Substations and Powerhouses | 2023: Complete supplemental inspections on 41 Hydroelectric Generation Substations and Powerhouses. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2024: Complete supplemental inspections on 46 Hydroelectric Generation Substations and Powerhouses. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2025: Complete supplemental inspections on 40 Hydroelectric Generation Substations and Powerhouses. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 339 | AI-10 | [119 empty] | 0 | 0 | 0 | 0
Filling Asset Inventory Data Gaps | Populate missing age data in the Asset Registry (using “Installation Date” data element as a proxy) to 90 percent weighted average across risk prioritized distribution and transmission equipment. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 290 | AI-11 | [119 empty] | 0 | 0 | 0 | 0
Community Engagement - Meetings | For 2023-2025, PG&E will hold annually a total of 22 community engagement meetings within the five regions of service that will include, but are not limited to, a mix of webinars, open houses, town halls, and/or answer centers. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1 PG&E's WMP Objectives p. 297 | CO-01 | [119 empty] | 0 | 0 | 0 | 0
Community Engagement - Surveys | PG&E will complete two PSPS education and outreach surveys (per year, for a total of six). 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2 PG&E's WMP Targets p. 348 | CO-02 | [119 empty] | 0 | 0 | 0 | 0
Community Engagement - Outreach to HFRA Infrastructure Customers | PG&E will perform outreach via email and/or phone to assigned Critical Infrastructure customers in the HFRA through Business Energy Solutions (assigned account managers). Outreach will cover the CWSP, including potential PSPS and EPSS impacts, and updating contact information for critical accounts in the HFRA. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1 PG&E's WMP Objectives p. 298 | CO-04 | [119 empty] | 0 | 0 | 0 | 0
Community Engagement - Outage Preparedness Campaign | PG&E will also conduct at least one direct-to-customer outage preparedness campaign annually via email and/or direct mail targeting residential customers in the PSPS more likely or EPSS program scope. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1 PG&E's WMP Objectives p. 298 | CO-05 | [119 empty] | 0 | 0 | 0 | 0
Complete PSPS and Wildfire Tabletop and Functional Exercises | Complete PSPS and Wildfire Tabletop and Functional Exercise annually in compliance with the guiding principles of the Homeland Security Exercise Evaluation Program (HSEEP). 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 296 | EP-01 | [119 empty] | 0 | 0 | 0 | 0
Maintain All Hazards planning and preparedness program | Maintain the All Hazards Planning and Preparedness Program to provide emergency response and safely and expeditiously restore service. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 296 | EP-02 | [119 empty] | 0 | 0 | 0 | 0
Expand All Hazards planning to include additional threats and scenarios | Expand the All Hazards Planning and Preparedness Program to include additional threats and scenarios. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 296 | EP-04 | [119 empty] | 0 | 0 | 0 | 0
Annually review of the Company Emergency Response Plan (CERP) and Wildfire and PSPS Annex | 3 documents (1 CERP and 2 wildfire-related annexes) (per year) 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 348 | EP-06 | [119 empty] | 0 | 0 | 0 | 0
Common Operating Picture Technology | Design and deploy a common operating picture. A common operation picture (COP) is a continuously updated overview of an incident compiled throughout an incident’s life cycle from data shared between integrated communication, information management, and intelligence and information sharing systems. The goal of a COP is real-time situational awareness across all levels of incident management and across jurisdictions. https://www.dhs.gov/publication/common-operating-picture-emergency-responders 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 297 | EP-07 | [119 empty] | 0 | 0 | 0 | 0
Threats and Hazards Identification and Risk Assessment (THIRA) updates executive briefings. | Execute a Threats and Hazards Identification and Risk Assessment (THIRA) update every three years to address changes in hazard landscape. Use information from THIRA to inform changes to the CERP and hazard annexes. According to FEMA, The THIRA is a three-step risk assessment process that helps communities understand their risks and what they need to do to address those risks. https://www.fema.gov/emergency-managers/national-preparedness/goal/risk-capability-assessment#:~:text=The%20Threat%20and%20Hazard%20Identification,hazards%20can%20affect%20our%20community%3F 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 297 | EP-08 | [119 empty] | 0 | 0 | 0 | 0
County Execute Briefings | Hold briefings with 47 counties within PG&E’s service territory after every THIRA update to support integrated planning discussions. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 297 | EP-09 | [119 empty] | 0 | 0 | 0 | 0
System Hardening - Distribution | System hardening work which includes overhead system hardening, undergrounding, and removal of overhead lines in HFTD, HFRA, or buffer zone areas except for any mileage being undergrounded and tracked separately as part of our Butte County Rebuild and other Community Rebuild efforts | GH-01 | [119 empty] | 0 | 0 | 0 | 0
Evaluate Covered Conductor Effectiveness | Update the covered conductor recorded effectiveness calculation using 2023 and 2024 outage data on the lines that have Covered Conductors for consideration in future system hardening workplans. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 289 | GH-02 | [119 empty] | 0 | 0 | 0 | 0
Evaluate and Implement Covered Conductor Effectiveness Impact on Inspections and Maintenance Standards | Evaluate the output of the Phase 1 and Phase 2 covered conductor effectiveness study to: (1) determine the impacts of the study on the maintenance and inspections standards for deployed covered conductor assets; and (2) update TD-2305M-JA02 (overhead inspections job aid), as needed. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 289 | GH-03 | [119 empty] | 0 | 0 | 0 | 0
10K Undergrounding | Undergrounding work as follows: (1) undergrounding taking place as part of System Hardening, (2) undergrounding taking place as part of the Butte County Rebuild program (including a small volume of previously hardened overhead lines that are being placed underground) or other Community Rebuild programs, and (3) any other undergrounding work performed in HFTD, HFRA, Buffer Zone, or fire rebuild areas. Undergrounding includes various mitigations includes line removal, conversion from overhead to underground and remote grid alternatives. | GH-04 | [119 empty] | 0 | 0 | 0 | 0
System Hardening - Transmission | 2023: Remove or replace 43 circuit miles of transmission conductor on lines. 2024: N/A 2025: Remove or replace 5 circuit miles of transmission conductor. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 334 | GH-05 | [119 empty] | 0 | 0 | 0 | 0
System Hardening - Transmission Shunt Splices | 2023: Install shunt splice(s) on 20 transmission lines. 2024: Install shunt splice(s) on 22 transmission lines. 2025: Install shunt splice(s) on 25 transmission lines. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 335 | GH-06 | [119 empty] | 0 | 0 | 0 | 0
Distribution Protective Devices | 2023: Install and SCADA commission 75 new SCADA protective devices (Line Recloser, Fuse Saver, or Interrupter). 2024: N/A 2025: N/A 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 335 | GH-07 | [119 empty] | 0 | 0 | 0 | 0
Surge Arrestor - Removals | 2023: Remove 663 non-exempt surge arrestors (based on the known population as of 01/12/2023) where known grounding issues exist. If no non-exempt surge arrestor is identified at a location during pre-field work, the unit will be resolved, and the notification will be canceled. Canceled notifications will count towards this target. 2024: N/A 2025: N/A 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 335 | GH-08 | [119 empty] | 0 | 0 | 0 | 0
Distribution Line Motor Switch Operator (MSO) - Replacements | 2023: Replace or remove 20 MSOs (from the 47 identified as of January 26, 2023). 2024: Replace or remove the remaining MSOs from the 47 identified, as of January 26, 2023. 2025: N/A 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 335 | GH-09 | [119 empty] | 0 | 0 | 0 | 0
Non-Exempt Expulsion Fuse - Removal | 2023: Remove non-exempt expulsion fuses/ cutouts from 3,000 fuse locations identified on distribution poles. 2024: Remove non-exempt expulsion fuses/ cutouts from 3,000 fuse locations identified on distribution poles. 2025: Remove non-exempt expulsion fuses/ cutouts from approximately 1,400 fuse locations (based on known population as of 1/26/23) identified on distribution poles. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 335 | GH-10 | [119 empty] | 0 | 0 | 0 | 0
System Hardening – Transmission Conductor Segment Replacement | 2023: N/A 2024: N/A 2025: Replace conductor segments on 2 transmission lines 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 335 | GH-11 | [119 empty] | 0 | 0 | 0 | 0
Asset Inspections - Quality Assurance | 2023: Perform system inspection QA audits on QC completed locations and achieve the associated quality pass rates for each asset inspection program as specified below: Transmission Ground Inspection - HFTD/HFRA (Field): 500 audit locations*; 92% pass rate Distribution Ground Inspections - HFTD/HFRA (Field): 1,500 audit locations*; 82% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. 2024: Perform system inspection QA audits on QC completed locations and achieve the associated quality pass rates for each asset inspection program as specified below: Transmission Inspection - HFTD/HFRA: 500 audit locations*; 94% pass rate Distribution Inspections - HFTD/HFRA: 1,500 audit locations*; 90% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. 2025: Perform system inspection QA audits on QC completed locations and achieve the associated quality pass rates for each asset inspection program as specified below: Transmission Ground Inspection - HFTD/HFRA (Field): 500 audit locations*; 95% pass rate Distribution Ground Inspections - HFTD/HFRA (Field): 1,500 audit locations*; 95% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. | GM-01 | [119 empty] | 0 | 0 | 0 | 0
HFTD/HFRA Open Tag Reduction - Transmission | PG&E will eliminate the known 16,831 HFTD and HFRA transmission Ignition Risk tags (tags found prior to January 1, 2023, with required end dates in 2023 or earlier). | GM-02 | [119 empty] | 0 | 0 | 0 | 0
HFTD/HFRA Open Tag Reduction - Distribution Backlog | 2023: Close 52,000 distribution EC notifications, which at a minimum 29,000 are distribution backlog ignition risk EC notifications. Backlog is defined as the open ignition EC notifications known as of January 5, 2023, and found prior to Jan 1, 2023, in HFTD/HFRA locations. 2024: Close at least 25,000 additional EC notifications on top of closing an equivalent number of EC notifications created in HFRA/HFTD locations in 2024. Based on the forecasted amount of new EC notifications, we expect a total forecasted execution plan of 89,000 EC notifications for 2024. Of these EC notifications, we expect to close 46,000 distribution backlog ignition risk EC notifications with the remaining balance to be from backlog or newly identified EC notifications. 2025: Close at least 25,000 additional EC notifications on top of closing an equivalent number of EC notifications created in HFRA/HFTD locations in 2025. Based on the forecasted amount of new EC notifications, we expect a total forecasted execution plan of 92,000 EC notifications for 2025. Of these EC notifications, we expect to close 63,747 distribution backlog ignition risk EC notifications with the remaining balance to be from backlog or newly identified EC notifications. | GM-03 | [119 empty] | 0 | 0 | 0 | 0
EPSS - Down Conductor Detection (DCD) | 2023: Make capable for DCD 500 protective device controllers or relays. This count includes protection devices that due to repair status cannot receive the DCD settings, and circuit reconfiguration resulting in descoping of device. 2024: Make capable for DCD 400 protective device controllers or relays. This count includes protection devices that due to repair status cannot receive the DCD settings, and circuit reconfiguration resulting in descoping of device. 2025: Make capable for DCD 250 protective device controllers or relays. This count includes protection devices that due to repair status cannot receive the DCD settings, and circuit reconfiguration resulting in descoping of device. | GM-06 | [119 empty] | 0 | 0 | 0 | 0
Updates on EPSS Reliability Study | Provide annually an updated EPSS reliability impact study per ACI PG&E-22-32 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 290 | GM-07 | [119 empty] | 0 | 0 | 0 | 0
Eliminate HFTD/HFRA Distribution Backlog | Eliminate PG&E’s HFTD/HFRA EC notifications distribution backlog* by 2029 and have all HFTD/HFRA EC notifications in compliance with GO 95 Rule 18 barring External Factors. Backlog is defined as the open ignition EC notifications known as of January 5, 2023, and found prior to Jan 1, 2023, in HFTD/HFRA locations | GM-08 | [119 empty] | 0 | 0 | 0 | 0
Asset Inspection – Quality Control | 2023: Perform system inspection QC audits and achieve the associated quality pass rates for each asset inspection program as specified below: System Inspection Transmission - HFTD (Desktop): 20,000 audit locations*; 90% pass rate 2024: Perform system inspection QC audits and achieve the associated quality pass rates for each asset inspection program as specified below: System Inspection Transmission - HFTD: 16,300 audit locations*; 92% pass rate 2025: Perform system inspection QC audits and achieve the associated quality pass rates for each asset inspection program as specified below: System Inspection Transmission - HFTD (Desktop): 16,000 audit locations*; 95% pass rate | GM-09 | [119 empty] | 0 | 0 | 0 | 0
Evaluate enhancements for the PSPS Transmission guidance | Evaluate enhancements for the PSPS Transmission guidance to enhance focus of PSPS events. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 298 | PS-01 | [119 empty] | 0 | 0 | 0 | 0
Evaluate incorporation of approved IPW enhancements into the PSPS Distribution guidance | Evaluate incorporation of approved IPW enhancements into the PSPS Distribution guidance to enhance focus of PSPS events. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 298 | PS-02 | [119 empty] | 0 | 0 | 0 | 0
Evaluate the transition of the Portable Battery Program to permanent battery solutions | Evaluate the transition of the Portable Battery Program to permanent battery solutions for PG&E customers at risk of PSPS or EPSS, focusing on but not limited to AFN, MBL, and self-identified vulnerable populations. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 299 | PS-05 | [119 empty] | 0 | 0 | 0 | 0
Provide 12,000 cumulative new or replacement portable and permanent batteries to PG&E customers at risk of PSPS or EPSS, focusing on but not limited to AFN, MBL, and self-identified vulnerable populations. | 2023: Provide 4,000 cumulative new or replacement portable batteries to PG&E customers. 2024: Provide 4,000 cumulative new or replacement portable batteries to PG&E customers 2025: Provide 3,300(i) cumulative new or replacement portable batteries to PG&E customers 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 348 | PS-06 | [119 empty] | 0 | 0 | 0 | 0
Reduce PSPS impacts by ~38k customer events (2.4%) for 2023-2025 period by completing planned Wildfire mitigation projects including but not limited to MSO switch replacements and undergrounding. | 2023: 15,000 customer events based on Wildfire mitigation projects including but not limited to MSO replacements and Undergrounded miles planned for 2023. 2024: 9,980 customer events based on Wildfire mitigation projects including but not limited to MSO replacements and Undergrounded miles planned for 2024.(k) (k): Target unit for 2024 reflects the approved 2024 Change Order Decision. The target unit is corrected to show the incremental number (not cumulative). This is consistent with Table PG&E-9-5. 2025: 13,000(i) customer events based on Wildfire mitigation projects including but not limited to MSO replacements and Undergrounded miles planned for 2025.(l) (i): The target has been updated for 2025. See PG&E’s 2025 WMP Update for more information about the target change. (l): Target unit for 2025 is corrected to show the incremental number (not cumulative). This is consistent with Table PG&E-9-5. The incremental 2025 target unit in the base 2023-2025 WMP was 22,000. We have updated the target to 13,000 for 2025. See PG&E’s 2025 WMP Update for more information about the target change. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 349 | PS-07 | [119 empty] | 0 | 0 | 0 | 0
Evaluate emerging technologies to reduce PSPS customer impact | Evaluate emerging technologies for transmission and distribution that may further reduce scale, scope, or frequency of PSPS. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 299 | PS-08 | [119 empty] | 0 | 0 | 0 | 0
Reduce PSPS impacts via Undergrounding | Reduce PSPS size, duration, or frequency over the next ten years as part of our 10,000-mile undergrounding program. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 299 | PS-09 | [119 empty] | 0 | 0 | 0 | 0
Continue sharing PSPS lessons learned | Continue sharing PSPS lessons learned and best practices with CA IOUs through monthly meetings focused on PSPS. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 300 | PS-10 | [119 empty] | 0 | 0 | 0 | 0
Pilot using drones for PSPS restoration | Pilot using drones for PSPS restoration and/or damage assessment to improve PSPS outage restoration time. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 300 | PS-11 | [119 empty] | 0 | 0 | 0 | 0
Artificial Intelligence (AI) in Wildfire Cameras | Enable Artificial Intelligence processing of Wildfire Camera Data to provide automated wildfire notifications in the internal PG&E monitoring tool (Wildfire Incident Viewer). 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 292 | SA-01 | [119 empty] | 0 | 0 | 0 | 0
Line Sensor - Installations | 2023: Install Line Sensor devices on 40 circuits. 2024: Install Line Sensor devices on 40 circuits. 2025: Install Line Sensor devices on 40 circuits. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 347 | SA-02 | [119 empty] | 0 | 0 | 0 | 0
EFD and DFA Reporting | Develop scalable processes to: (a) analyze alarms and alerts from Early Fault Detection (EFD) and DFA sensors; (b) conduct field investigation and reporting; (c) track identified mitigations to completion; and (d) track effectiveness of issue identification and remediation using EFD/DFA technologies. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 293 | SA-03 | [119 empty] | 0 | 0 | 0 | 0
FPI and IPW Modeling - Revision Evaluation | Evaluate enhancements to the FPI model and the Ignition Probability Weather model. This involves testing new features and types of model configurations that could improve model skill. At present we do not know if model skills can be improved but we will attempt to do so. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 293 | SA-04 | [119 empty] | 0 | 0 | 0 | 0
Evaluate FPI and IPW Modeling enhancements in 2023 - 2025 | Evaluate enhancements to the FPI (Fire Potential Index) model and the IPW (Ignition Probability Weather) model in 2023. This involves testing new features and types of model configurations that could improve model skill. For example, one of the features that will be evaluated for IPW is covered conductor and EPSS on the system. If covered conductor, EPSS, or other model enhancements, do not improve model skill, it will not be deployed as a part of the model improvement. At present we do not know if model skill can be improved but we will attempt to do so in 2023. If model skill can be improved and is approved, we plan to operationalize the new models in 2024 and continue operations in 2025. We do not know if any new models developed will be approved for operations by PG&E’s Wildfire risk governance committee. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 294 | SA-05 | [119 empty] | 0 | 0 | 0 | 0
Evaluate FPI and IPW Modeling enhancements in 2026 - 2032 | Evaluate enhancements to the FPI (Fire Potential Index) model and the IPW (Ignition Probability Weather) model in the 2026-2033 period. This work involves testing new features and types of model configurations that could improve model forecasting ability. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 294 | SA-06 | [119 empty] | 0 | 0 | 0 | 0
Monitor and evaluate the Cameras AI system’s performance | In partnership with Digital Path (the AI vendor that works with us and other agencies on the broader camera network) monitor and evaluate the AI system’s performance. Explore additional features and inputs to further enhance the system. At present we do not know what these enhancements will be specifically, however we will look for opportunities to explore best practices and incorporate enhancements with the vendor. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 295 | SA-07 | [119 empty] | 0 | 0 | 0 | 0
Evaluate the Cameras AI system functionalities and technologies | In partnership with Digital Path and its collaboration with other camera sponsors, evaluate the AI system for opportunities to test new functionalities and newly developed break-through technologies. We will also explore new best practices to ensure the ongoing effectiveness of the system. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 295 | SA-08 | [119 empty] | 0 | 0 | 0 | 0
EFD and DFA Reporting | Perform a feasibility study on the use of EFD/DFA technologies to successfully identify incipient failures as a supplement to field inspections. If feasible, complete a data driven proposal for integrating sensor findings into the inspection program. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 295 | SA-09 | [119 empty] | 0 | 0 | 0 | 0
Distribution Fault Anticipation (DFA) Installations | 2023: Install 5 Distribution Fault Anticipation (DFA) sensors on circuits.(g) One sensor will be installed per circuit at the initiating substation. 2024: Install 15 Distribution Fault Anticipation (DFA) sensors on circuits feeding into HFTD areas or HFRA. One sensor will be installed per circuit at the initiating substation. 2025: Install 15 Distribution Fault Anticipation (DFA) sensors on circuits feeding into HFTD areas or HFRA. One sensor will be installed per circuit at the initiating substation. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 348 | SA-10 | [119 empty] | 0 | 0 | 0 | 0
Early Fault Detection (EFD) Installations | 2023: Install Early Fault Detection (EFD) sensors on 2 circuits.(h) 2024: Install Early Fault Detection (EFD) sensors on 2 circuits. 2025: Install Early Fault Detection (EFD) sensors on 4 circuits. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 348 | SA-11 | [119 empty] | 0 | 0 | 0 | 0
Evaluate the use and effectiveness of real-time monitoring tools | Each year, we will evaluate and discuss our situational awareness tools internally, as well as with other IOUs. These evaluative discussions will include reviewing observations of our various situational awareness tools and identifying potential areas for improvement. We will also discuss best practices and lessons learned. These discussions will help inform potential changes to what situational awareness tools we incorporate, as well as how they are incorporated. This may include equipment upgrades, new tech integrations, model improvements, and enhanced data initiatives. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 296 | SA-12 | [119 empty] | 0 | 0 | 0 | 0
LiDAR Data Collection - Transmission | 2023: Collect LiDAR data of the Transmission System (17,500 circuit miles). The Transmission System circuit miles include both HFTD / HFRA and non-HTFD Transmission circuit miles. 2024: Collect LiDAR data of the Transmission System (17,500 circuit miles). The Transmission System circuit miles include both HFTD / HFRA and non-HFTD Transmission circuit miles. 2025: Collect LiDAR data of the Transmission System (17,500 circuit miles). The Transmission System circuit miles include both HFTD / HFRA and non-HFTD Transmission circuit miles. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 342 | VM-01 | [119 empty] | 0 | 0 | 0 | 0
Pole Clearing Program | 2023: Inspect, clear, and maintain, where clearing is necessary, 77,503 poles per Vegetation Control Standard TD-7112S. 2024: 2024 pole count to be adjusted by the ending pole population in the previous year (2023) poles per Vegetation Control Standard TD-7112S will be inspected, cleared, and maintained where clearing is necessary. 2025: 2025 pole count to be adjusted by the ending pole population in the previous year (2024) poles per Vegetation Control Standard TD-7112S will be inspected, cleared, and maintained where clearing is necessary. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 342 | VM-02 | [119 empty] | 0 | 0 | 0 | 0
Focused Tree Inspection (FTI) | 2023: Complete focus tree inspections of 250 Circuit Miles in defined Areas of Concern (AOC) locations.(c) 2024: Within Areas of Concern (AOC) locations, complete 1,500 circuit miles of FTI inspection which includes performing a level 2 inspection on all potential strike trees. 2025: Within Areas of Concern (AOC) locations complete 1,500 circuit miles of FTI inspection which includes performing a level 2 inspection on all potential strike trees. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 343 | VM-03 | [119 empty] | 0 | 0 | 0 | 0
Tree Removal Inventory (TRI) | 2023: Mitigate(d)15,000 trees identified from the legacy EVM program. 2024: Mitigate(d) 20,000 trees identified from the legacy EVM program. 2025: Mitigate(d) 25,000 trees identified from the legacy EVM program. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 343 | VM-04 | [119 empty] | 0 | 0 | 0 | 0
Defensible Space Inspections - Distribution Substation | 2023: Complete defensible space inspections in alignment with the guidelines set forth in LAND 4001P-01 at 131 distribution substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2024: Complete defensible space inspections in alignment with the guidelines set forth in LAND 4001P-01 at 131 distribution substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2025: Complete defensible space inspections in alignment with the guidelines set forth in LAND 4001P-01 at 131 distribution substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 343 | VM-05 | [119 empty] | 0 | 0 | 0 | 0
Defensible Space Inspections - Transmission Substation | 2023: Complete defensible space inspections in alignment with the guidelines set forth in LAND 4001P-01 at 55 transmission substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2024: Complete defensible space inspections in alignment with the guidelines set forth in LAND 4001P-01 at 55 transmission substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2025: Complete defensible space inspections in alignment with the guidelines set forth in LAND 4001P-01 at 55 transmission substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 343 | VM-06 | [119 empty] | 0 | 0 | 0 | 0
Defensible Space Inspections - Hydroelectric Substations and Powerhouses | 2023: Complete defensible space inspections in alignment with the guidelines set forth in LAND 5201P-01 at 61 Hydroelectric Generation Substations and Powerhouses. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2024: Complete defensible space inspections in alignment with the guidelines set forth in LAND 5201P-01 at 61 Hydroelectric Generation Substations and Powerhouses. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2025: Complete defensible space inspections in alignment with the guidelines set forth in LAND 5201P-01 at 61 Hydroelectric Generation Substations and Powerhouses. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 344 | VM-07 | [119 empty] | 0 | 0 | 0 | 0
Vegetation Management – Quality Assurance | 2023: Perform vegetation management QA audits on QC completed locations and achieve the associated quality pass rates for each vegetation management program as specified below: Distribution Routine VM - HFTD: 2,500 audit locations*; 95% pass rate Transmission VM - HFTD: 1,200 audit locations; 95% pass rate Vegetation Control Pole Clearing - HFTD: 1,800 audit locations*; 95% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. 2024: Perform vegetation management QA audits on QC completed locations and achieve the associated quality pass rates for each vegetation management program as specified below: Distribution Routine VM - HFTD: 2,675 audit locations*; 95% pass rate Transmission VM - HFTD: 1,284 audit locations; 95% pass rate Vegetation Control Pole Clearing - HFTD: 1,926 audit locations*; 95% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. 2025: Perform vegetation management QA audits on QC completed locations and achieve the associated quality pass rates for each vegetation management program as specified below: Distribution Routine VM - HFTD: 2,862 audit locations*; 95% pass rate Transmission VM - HFTD: 1,374 audit locations*; 95% pass rate Vegetation Control Pole Clearing - HFTD: 2,061 audit locations*; 95% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 345 | VM-08 | [119 empty] | 0 | 0 | 0 | 0
Constraint Resolution Procedural Guideline | Develop a process of centralizing constraints resolution. As part of the build out of the centralized constraints team, three major categories will be addressed: customer constraints, environmental constraints (including internal PG&E procedures required to perform work) and permitting constraints (including both Land and Environmental permits). For each major constraint category build a process for addressing each constraint type, implement the new process, and create metrics to track each constraint type. Reporting will track total constraints by type and the time it takes to resolve a constraint after it has been identified. PG&E will consider creating a “right tree-right place” program, as part of the centralize Constraints Resolution process. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 8-12 Vegetation Management Implementation Objectives (3-Year Plan) p. 606 | VM-09 | [119 empty] | 0 | 0 | 0 | 0
Inspection in HFTD and HFRA supporting key vegetation management initiatives | Continue multiple inspection activities in HFTD and HFRA supporting key vegetation management initiatives 2023-2025 Wildfire Mitigation Plan R6 Revised Table 8-13 Vegetation Management Implementation Objectives (10-Year Plan) p. 607 | VM-10 | [119 empty] | 0 | 0 | 0 | 0
Enhance and refine Focus Tree Inspection – Areas of Concern (AOC) | Enhance and refine Focus Tree Inspection - Areas of Concern (AOC) development criteria and application of the AOCs to vegetation management programs. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 8-13 Vegetation Management Implementation Objectives (10-Year Plan) p. 607 | VM-11 | [119 empty] | 0 | 0 | 0 | 0
Evaluate emerging technologies | Evaluate emerging technologies to enhance focus of and streamline execution of vegetation management inspections. | VM-12 | [119 empty] | 0 | 0 | 0 | 0
Routine Ground - Transmission | 2023: Complete Routine Transmission Ground Inspection of 17,740 circuit miles as defined by Transmissions Routine LiDAR detection point data systemwide. 2024: Complete Routine Transmission Ground Inspection of 17,740 circuit miles as defined by Transmissions Routine LiDAR detection point data systemwide. 2025: Complete Routine Transmission Ground Inspection of 17,740 circuit miles as defined by Transmissions Routine LiDAR detection point data systemwide. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 345 | VM-13 | [119 empty] | 0 | 0 | 0 | 0
Transmission Second Patrol | 2023: Complete Transmission Second Patrol Inspection of 5,625 circuit miles dependent 2024: Complete Transmission Second Patrol Inspection of 5,625 circuit 2025: Complete Transmission Second Patrol Inspection of 5,625 circuit miles dependent 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 345 | VM-14 | [119 empty] | 0 | 0 | 0 | 0
Integrated Vegetation Management - Transmission | 2023: Complete Integrated Vegetation Management and Fee Inspections of 11,194 acres ROW across the Transmission systemwide 2024: Complete Integrated Vegetation Management and Fee Inspections of 6,504 acres ROW across the Transmission systemwide 2025: Complete Integrated Vegetation Management and Fee Inspections of 6,504 acres ROW across the Transmission systemwide 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 346 | VM-15 | [119 empty] | 0 | 0 | 0 | 0
Distribution Routine Patrol | 2023: Complete Distribution Routine Annual Patrol Inspection of 79,000 overhead circuit miles system wide 2024: Complete Distribution Routine Annual Patrol Inspection of 78,650 overhead circuit miles system wide 2025: Complete Distribution Routine Annual Patrol Inspection of 78,200 overhead circuit miles system wide 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 346 | VM-16 | [119 empty] | 0 | 0 | 0 | 0
Distribution Second Patrol | 2023: Complete Distribution Second Patrol Inspection of 43,600 circuit miles that are in the following map layers FHSZ, WUI, SRA, FRA, HFTD, and HFRA locations. 2024: Complete Distribution Second Patrol Inspection of 25,685 circuit miles in HFTD and HFRA locations. 2025: Complete Distribution Second Patrol Inspection of 25,685 circuit miles in HFTD and HFRA locations. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 346 | VM-17 | [119 empty] | 0 | 0 | 0 | 0
VM for Operational Mitigations (VMOM) | 2023: N/A 2024: Mitigate 6,500 trees for VM for Operational Mitigations program, on EPSS capable circuits. This target will include the previous year's carry-over work and prescriptions resulting from pro-active patrols on EPSS circuits. Future workplans will be dependent on previous year's EPSS outage data analysis. 2025: Mitigate 6,500 trees for VM for Operational Mitigations program, on EPSS capable circuits. This target will include the previous year's carry-over work and prescriptions resulting from pro-active patrols on EPSS circuits. Future workplans will be dependent on previous year's EPSS outage data analysis. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 346 | VM-18 | [119 empty] | 0 | 0 | 0 | 0
One VM Application Record Keeping Enhancement (Routine, Second Patrol) | Enhance the One VM application for Routine, and Second Patrol to include capability to capture factors for prescribing trees for removal. | VM-19 | [119 empty] | 0 | 0 | 0 | 0
Record Keeping Enhancement (VMOM, TRI) | Enhance the application for the Vegetation Management for Operational Mitigations (VMOM) - VMPI2 - and Tree Removal Inventory (TRI) - Field Maps - program to include capability to capture factors for prescribing trees for removal. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 292 | VM-20 | [119 empty] | 0 | 0 | 0 | 0
Focused Tree Inspection (FTI) Program Record Keeping Enhancement | Enhance record keeping practices for the Focused Tree Inspection program (FTI) by creating records of all potential strike trees inspected using a digitized Tree Risk Assessment form. 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-1: PG&E's WMP Objectives p. 292 | VM-21 | [119 empty] | 0 | 0 | 0 | 0
Vegetation Management - Quality Control | 2023: Perform vegetation management QC audits and achieve the associated quality pass rates for each vegetation management program as specified below: 2024: Perform vegetation management QC audits and achieve the associated quality pass rates for each vegetation management program as specified below: 2025: Perform vegetation management QC audits and achieve the associated quality pass rates for each vegetation management program as specified below: 2023-2025 Wildfire Mitigation Plan R6 Revised Table 7-3-2: PG&E's WMP Targets p. 346 | VM-22 | [119 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0