## DOT SampleREDACTED
[13 empty] | Totals | [59 empty] | Scoping |  |  |  |  | Basemap | [7 empty] | Estimating | [16 empty] | Estimating | [12 empty] | Joint Pole |  |  |  |  | Land | [8 empty] | Easements | [9 empty] | Caltrans | [20 empty] | Railroad Section |  |  |  | Environmental | [18 empty] | Permits | [11 empty] | Business Case |  |  | Business Case | Contract Planning | [17 empty] | Release | [6 empty] | Veg | [18 empty] | Portfolio Target & Planned Variances | [13 empty] | Construction | [49 empty] | Financial | [27 empty] | QA/QC | [41 empty] | QA/QC | [14 empty] | QA/QC |  |  |  | Project Stakeholders | [8 empty] | Project Info |  |  |  | Project Info |  |  |  |  | Project Info |  | Project Info | [10 empty] | Circuit Info
Order | Job Owner Name | Job Owner | Supervisor Name | PCA Supervisor Name | PCA Name | Order Description | SAP Status | Secondary SAP Status | Program | Sub-Program | Div | Region | Planned Circuit Miles | Planned Circuit Feet | UG Miles | UG Feet | OH Miles | OH Feet | Removal Miles | Removal | 2024 Forecast Total Miles | 2024 Forecast OH Miles | 2024 Forecast UG Miles | 2024 Forecast Removal Miles | 2024 Forecast Total Feet | 2024 Forecast OH Feet | 2024 Forecast UG Feet | 2024 Forecast Removal Feet | 2024 Remaining Total Miles | 2024 Remaining OH Miles | 2024 Remaining UG Miles | 2024 Remaining Removal Miles | 2025 Forecast Total Miles | 2025 Forecast OH Miles | 2025 Forecast UG Miles | 2025 Forecast Removal Miles | 2025 Forecast Total Feet | 2025 Forecast OH Feet | 2025 Forecast UG Feet | 2025 Forecast Removal Feet | 2026 Forecast Total Miles | 2026 Forecast OH Miles | 2026 Forecast UG Miles | 2026 Forecast Removal Miles | 2026 Forecast Total Feet | 2026 Forecast OH Feet | 2026 Forecast UG Feet | 2026 Forecast Removal Feet | 2027 Forecast Total Miles | 2027 Forecast OH Miles | 2027 Forecast UG Miles | 2027 Forecast Removal Miles | 2027 Forecast Total Feet | 2027 Forecast OH Feet | 2027 Forecast UG Feet | 2027 Forecast Removal Feet | 2028 Forecast Total Miles | 2028 Forecast OH Miles | 2028 Forecast UG Miles | 2028 Forecast Removal Miles | 2028 Forecast Total Feet | 2028 Forecast OH Feet | 2028 Forecast UG Feet | 2028 Forecast Removal Feet | Unallocated Total Forecast Miles | Unallocated OH Forecast Miles | Unallocated UG Forecast Miles | Unallocated Removal Forecast Miles | MAT | Ready to Break Ground | Open Dependencies | ELP Dependency Out | Scope Status | Scoping Session Date | Segment Maps Submitted to GD Date | DBM & Docs Sent to PM to Route | DBM Routed for Approval - EDRS | Basemap Status | Basemap Start Date | ETA Prelim Basemap COMP | Previous Expected Base Map Complete | Actual Deliv Prelim Basemap | Vendor Basemap Due Date | Survey Vendor | Land Surveyor | Customer Outreach Complete - Welcome Kit | Project Kick-off Complete | Project Kick-off Date | Energization Predecessor | Estimating Start Date | Walkdown Complete | Walkdown Schedule Date | Customer Outreach Complete - Job Walkdown | 30% Design Complete (Forecast) | 30% Drawing Complete (Actual) | Key Sketch Approved | 60% Design Complete (Forecast) | 60% Drawing Complete (Actual) | DS73 In Process Date | DS73 Completion Date | CMCS Approved | EOD Source | Est Out Date | Previous EOD Forecast | Initial EOD | First Est Out Date | DS18 Date | First DS18 Out | PEND IN Date | Redesign Needed | Estimating Resource | Estimating Assignment | Estimating Manager | ADE | Estimator | Expected Joint Pole Date | Joint Pole Complete | DS42 JP Intent Sent | PC20 JPole Intent Authorized | Joint Pole Coordinator | Land Clear Date | Partial Land Clear Date | RP57 Planned Finish Date | Land Complete | Formulaic Land Clear Date | SP57 Land Serv Required | RP57 Land Services Complete | Land Agent Name | Previous Land Clear Date | No. of Easements Remaining | No. of Easements Acquired | Number of Easements Needed | Land Rights Needed (Salesforce) | Design Status at Reivew | Land Rights Review Due | Land Rights Review Complete | Easement Expected Duration | Formulaic Easement Delivery Date | Acquisition Agent | Caltrans Permit Needed | Early CT Notification to Land | Caltrans Required | Exception to Policy Status Date | Caltrans Access Controlled ROW | DSDD Required (Salesforce) | CUPA Status | Caltrans Expected Duration | Formulaic Caltrans Delivery Date | SHUG Estimating Status | CalTrans Permit Status | DSDD Completed Date | Vegetation Status Completion Date | Environmental Status Completion Date | CalTrans Anticipated Application Date | CalTrans Date Application Filed | Agency Rejection Reason | CalTrans Anticipated Issued Date | Date Obtained from Caltrans | Caltrans Permit Expiration Date | Caltrans District | RR Permit Required | RR Date Application Filed | RR Anticipated Issue Date | RR Date Issued/Approved | ERTC Planned Date | PERTC Planned Date | Initial ERTC | Anticipated ERTC Date | ERTC Complete | Partial Released Mileage | Formulaic ERTC Date | Previous ERTC Date | DS11 Env Service Required | PC21 Env Service Complete | Drawings Under Review | Land Environmental Status | Return To LOB Reason | Project Complexity | Project Complexity Description | ERTC Expiration Date | Salesforce ERTC Call Date | Planner | L and ERTC Complete | Expected Permit Date | Anticipated Permit Date | Permit Formulaic Date | SP56 Encroach Permit Sent | RP56 Encroach Permit Rcvd | Permit Status | Permits Complete | Permit Expire Date | Latest Expiration Date | Permit Type | Permit Agency Name | Permit Coordinator | Phase Gate Meeting Date | P6 Business Case Date | Business Case vs. Ready to Break Ground | BC Complete | Elec MPP Resource | Elec Contract Ready Date | Elec Created Date | Elec Start Date | Elec End Date | Elec Contractor | Elec CMDB Proposal Due Date | Elec CMDB Status | Elec Contract Status | Civil MPP Resource | Civil Contract Ready Date | Civil Created Date | Civil Start Date | Civil End Date | Civil Contractor | Civil CMDB Proposal Due Date | Civil CMDB Status | Civil Contract Status | AP25 Status | PM DOR Comments | AP25 Out Date | DS24 Status | UNSC In Date | UNSC Out Date | Contract Type | Customer Outreach Complete - Pre Inspection Veg | PI Start | PO Expiration Date | Vegetation Estimate to PM | CMDB Request Date | Veg Contractor | PO Request Status | PO Number | ERTC Call Complete | ERTC Call Date | Early Start Date | Veg Customer Outreach Complete | VPM Forecast Start Date | VPM Actual Start Date | VPM Forecast Finish Date | VPM Actual Finish Date | Construction Start | Veg Completed | VPM | Planned Base Map Complete | Planned EST Out Date | Planned RP57 Planned Finish | Planned ERTC Date | Planned Permit Date | Planned Civil Start | Planned Civil End | Planned Electric Start | Planned Electric End | Baseline Target Electric End | Updated Target Electric End | Target Flag Type | Target Flag | Target Date Var Reason Code | Pre-Construction Customer Outreach Complete | Contractor Baseline Civil Start | Contractor Baseline Civil End | Approved Civil Duration Extension | Contractor Baseline Electric Start | Contractor Baseline Electric End | Approved Electric Duration Extension | CLICK Construction Start | Previous Click Construction Start | Materials Ready Date | Materials Ready | Civil Complete | CLICK Civil Start | CLICK Civil End | Previous CLICK Civil End | Civil CM Start Date | Civil CM End Date | PM Civil Start | PM Civil End | P6 Construction Start | Civil Est Work Hours | Civil Actual Work Hours | Total Primary Conduit Installed | Remaining Civil Units | Electric Complete | Days Between Civil End and Electric Start | CLICK Electric Start | CLICK Electric End | Previous CLICK Electric End | AFW | AFW Final Clearance Date | PM Electric Start | PM Electric End | Electric Est Work Hours | Electric Actual Work Hours | Post-Construction Customer Outreach Complete | CLICK Construction End | Restoration Start Date | Restoration End Date | CN24 Complete | CN24 Out Date | P6 Operative Date | P6 Operative Actualized | CN07 Out Date | DC05 Out Date | DC10 Date | P6 Forecast In Service | Operative Date | QA Complete | QA Year Complete/Forecast | Auth Amt without Contingency (Expected Case) | Total EAC | UG EAC | OH EAC | Removal EAC | Remote Grid EAC | MPP Approved Budget (2023) | Auth Amt with Contingency (High Case) | Remaining Contingency | Expected - (Actuals + Committed) | Total EAC / Expected Case | Total Forecast | MTD Actuals | ITD Actual | UG ITD Actuals | OH ITD Actuals | Removal ITD Actuals | Remote Grid ITD Actuals | Open Commitments | Total Act + Com | Credits and Reimbursements | Expected Unit Cost | Cost Type | 2022 Cost Category | 2023 Cost Category | 2024 Cost Category | 2025 Cost Category | 2026 Cost Category | Total Installed Miles | Total OH Miles Installed | Total UG Miles Installed | Total Removal Miles Installed | 2018 Total Miles Completed | 2018 OH Miles Completed | 2018 UG Miles Completed | 2018 Removal Miles Completed | 2019 Total Miles Completed | 2019 OH Miles Completed | 2019 UG Miles Completed | 2019 Removal Miles Completed | 2020 Total Miles Completed | 2020 OH Miles Completed | 2020 UG Miles Completed | 2020 Removal Miles Completed | 2021 Total Miles Completed | 2021 OH Miles Completed | 2021 UG Miles Completed | 2021 Removal Miles Completed | 2022 Total Miles Completed | 2022 OH Miles Completed | 2022 UG Miles Completed | 2022 Removal Miles Completed | 2023 Total Miles Completed | 2023 OH Miles Completed | 2023 UG Miles Completed | 2023 Removal Miles Completed | 2024 Total Miles Completed | 2024 OH Miles Completed | 2024 UG Miles Completed | 2024 Removal Miles Completed | Remaining Planned Miles | Remaining OH Miles | Remaining UG Miles | Remaining Removal Miles | QA Pass OH | QA Pass UG | QA Pass Removal | QA Fix OH | QA Fix UG | QA Fix Removal | QA Pass | QA Fix | Total QA Span Length | OH QA Span | UG QA Span | Removal QA Span | QA Remaining | QA Trailing Installed | iAudit Uploaded | IA Pass OH | IA Pass UG | IA Pass Removal | IA Fail OH | IA Fail UG | IA Fail Removal | IA Pass | IA Fail | IA Trailing QA Passed | Span Notes | Customer Outreach | Civil CM | Electric CM | Planning Engineer | DLT | Telecom | SCADA Specialist | SWPPP Status | FE Primary or Support | City | County | Average Elevation | Number of Applications (FRRB Only) | Tribal LAR | Water Agency | Incorporated City 1 | Incorporated City 2 | KMZ | KMZ Link | GeoTech URL | GeoTech Report Link | Latitude | Longitude | Forecasted Construction Quarter Start | Hardening Method | Mainline or Tapline | Project Managed | Project Type | Functional Location | IN03 Completion Date | Approval Category | Circuit Name | Circuit | Primary CPZ | Second CPZ | Third CPZ | Fourth CPZ | Fifth CPZ | Sixth CPZ
35299631 | [6 empty] | CONS | crdy | SH | Base | NV | Region 2 - North East | 3.5237 | 18605 | 3.5237 | 18605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8.8818e-16 | 0 | -8.8818e-16 | 0 | 08W | 2023-04-13 |  | 2023-06-12 | Scoped |  |  |  |  | Completed |  | 2022-08-22 | 2022-08-22 | 2022-08-01 |  |  |  |  | Y | 2022-04-28 |  |  | Yes | 2022-04-28 | [6 empty] | 2022-12-23 | 2022-12-30 | Yes | SAP | 2023-04-22 | 2023-04-22 | 2023-04-22 | 2023-04-22 | 2023-04-12 | 2022-12-30 | 2023-04-12 |  | CNTRCT_EST | ENENG |  |  |  | 2023-02-21 | Yes | 2023-01-05 | 2023-02-21 |  | 2023-03-28 |  | 2023-06-12 | Full | 2023-06-06 | 2023-01-30 | 2023-03-22 |  | 2023-03-28 | 0 | 2 | 2 | Yes | Redesign review | 2023-05-11 | 2023-05-10 | 60 | 2023-06-21 |  | No |  | N |  | No | No | No | 0 | 2023-04-22 | [11 empty] | 3 | No |  |  |  | 2023-03-28 |  | 2023-03-28 | 2023-03-28 | Full |  | 2023-06-21 | 2023-03-28 | 2023-01-10 | 2023-03-28 | Completed Engineering | Released to Construction | Other | Medium |  | 2024-09-28 | 2023-03-31 |  | Full | 2023-02-06 | 2023-02-20 | 2023-06-12 | 2023-01-30 | 2023-02-06 | Permit Approved | Yes | 2024-10-15 |  | Encroachment | County of Butte |  | 2023-02-27 | 2023-03-10 | -34 | Yes | Contract | 2023-02-24 | 2023-02-01 10:08 | 2023-04-03 | 2024-03-31 | UNDERGROUND ELECTRIC CONSTRUCTION C | 2023-02-21 |  | Fully Executed PO | Contract | 2023-02-24 | 2023-02-01 10:08 | 2023-04-03 | 2024-03-31 | UNDERGROUND ELECTRIC CONSTRUCTION C | 2023-02-21 |  | Fully Executed PO |  |  |  | COMP | 2023-04-13 | 2023-04-13 | All Work |  | 2023-01-25 | 2024-03-31 | 2023-02-22 | 2023-02-22 22:03 | MOUNTAIN F ENTERPRISES INC | Fully Executed PO | 2700870396 | Y |  | 2023-03-28 |  | 2023-04-05 | 2023-04-03 | 2023-04-10 | 2023-04-05 | 2023-05-01 | Y | [13 empty] | N | [8 empty] | 2023-05-01 |  |  | Yes | Complete | 2023-05-01 | 2024-07-09 | 2024-07-09 | 2023-05-01 | 2023-08-04 |  |  | 2023-05-01 08:00 | 5510 | 7 | 18605 | 0 | Complete | -318 | 2023-08-26 | 2024-02-16 | 2024-02-16 | 23-0127917 | 2023-10-27 |  |  | 1500 | 0 |  | 2024-07-09 |  |  | N |  | 2023-09-29 08:00 | Yes |  |  |  | 2023-10-27 08:00 | 2023-09-29 | Y | 2023 | 9653629 | 8259725.3 | 8259725.3 | 0 | 0 |  |  | 0 | -9653629 | 684973.4 | 85.56% | 6399.6 | 3835.6 | 8257161.3 | 8257161.3 | 0 | 0 |  | 711494.3 | 8968655.6 | 0 | 2344066.0889 | UG | Readiness | Construction | Closeout |  |  | 3.5237 | 0 | 3.5237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5237 | 0 | 3.5237 | 0 | 0 | 0 | 0 | 0 | -8.8818e-16 | 0 | -8.8818e-16 | 0 | 0 | 3.5237 | 0 | 0 | 0 | 0 | 3.5237 | 0 | 3.5237 | 0 | 18605 | 0 | 0 | 8.8818e-16 |  | 0 | 3.5237 | 0 | 0 | 0 | 0 | 3.5237 | 0 | 0 | [10 empty] | Oroville | BUTTE | 408 |  |  | Butte County of(100) |  |  | https://pge.sharepoint.com/sites/EDOSProjMgmt/EDOS%20Project%20Management/System%20Hardening%20Website%20Folder/System%20Hardening/Master%20KMZ%20File/02%20PM%20ONLY_FOR%20DOT%20HL/Region%202/SH/35299631.kmz | Link | https://pge.sharepoint.com/sites/EDOSProjMgmt/EDOS%20Project%20Management/System%20Hardening%20Website%20Folder/System%20Hardening/Master%20Geotechnical%20Science%20Report%20File/PM%20Only_For%20DOT/Region%202/SH/35299631.pdf | Link | 39.6474 | -121.6306 |  | UG | MX |  | PSPS | ED.17-V330000000.STRU.POLE | 2022-03-21 | PSPS | CLARK ROAD 1102 | 103091102 | CLARK ROAD 110281296 | 0 | 0 | 0 | 0 | 0
35329009 | [6 empty] | CONS | CONS | SH | Base | NV | Region 2 - North East | 0.73163 | 3863 | 0.70795 | 3738 | 0 | 0 | 0.023674 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1102e-16 | 0 | 1.1102e-16 | 0 | 08W | 2023-03-13 |  | 2023-03-27 | Scoped |  |  |  |  | Completed |  | 2022-08-29 | 2022-08-29 | 2022-08-23 |  |  |  |  | Y | 2022-04-28 |  |  | Yes | 2022-11-16 | [6 empty] | 2023-02-27 | 2023-02-27 | Yes | SAP | 2022-12-16 | 2022-12-16 | 2022-12-16 | 2022-12-16 | 2023-05-12 | 2022-12-16 | 2023-05-12 |  | CNTRCT_EST | ENENG |  |  |  | 2023-02-06 | Yes | 2022-12-22 | 2023-02-06 |  | 2023-01-27 |  | 2023-03-27 | Full | 2023-01-30 | 2023-01-19 | 2023-01-19 |  | 2023-01-27 | 0 | 0 | 0 | No | 100% review | 2023-01-19 | 2023-01-19 | 45 | 2023-01-30 |  | No |  | N |  | No | No | No | 0 | 2022-12-16 | [11 empty] | 3 | No |  |  |  | 2023-03-02 |  | 2023-03-02 | 2023-03-02 | Full |  | 2023-02-14 | 2023-03-02 | 2023-01-03 | 2023-02-24 | Completed Engineering | Released to Construction | Design Required;Other | Medium |  | 2024-08-24 | 2023-03-22 |  | Full | 2023-03-15 | 2023-01-20 | 2023-02-05 | 2022-12-23 | 2023-02-14 | Permit Approved | Yes | 2024-10-15 |  | Encroachment | County of Butte |  | 2023-02-27 | 2023-03-10 17:00 | -3 | Yes | Contract | 2023-02-27 | 2023-02-01 10:08 | 2023-04-20 | 2024-03-31 | UNDERGROUND ELECTRIC CONSTRUCTION C | 2023-02-17 |  | Fully Executed PO | Contract | 2023-03-02 | 2023-02-01 10:08 | 2023-04-20 | 2024-03-31 | UNDERGROUND ELECTRIC CONSTRUCTION C | 2023-02-17 |  | Fully Executed PO |  |  |  | COMP | 2023-03-13 | 2023-03-27 | All Work |  | 2023-01-25 | 2024-03-31 | 2023-02-22 | 2023-02-22 21:56 | MOUNTAIN F ENTERPRISES INC | Fully Executed PO | 2700869003 | Y |  | 2023-03-15 |  | 2023-03-21 | 2023-03-21 | 2023-03-28 | 2023-03-22 | 2023-04-03 | Y | [13 empty] | N | [8 empty] | 2023-04-05 |  |  | Yes | Complete | 2023-04-05 | 2023-07-28 | 2023-07-28 | 2023-04-05 | 2023-08-02 | 2023-04-05 | 2023-06-08 | 2023-04-03 | 2410 | 2 | 3738 | 0 | Complete | -11 | 2023-07-17 | 2024-02-29 | 2024-02-29 | 23-0143464 | 2023-12-13 |  |  | 2050 | 0.75 | 2023-12-07 | 2024-02-29 |  |  | N |  | 2023-11-02 08:00 | Yes |  |  |  | 2024-01-23 | 2023-11-02 | Y | 2023 | 5204384 | 4204475.7 | 4167622.7775 | 0 | 36852.9225 |  |  | 0 | -5204384 | 879982.7 | 80.78% | 0 | 187 | 4204662.7 | 4167808.1384 | 0 | 36854.5616 |  | 119738.6 | 4324401.3 | 0 | 5746733.548 | UG | Readiness | Construction | Closeout |  |  | 0.73163 | 0 | 0.70795 | 0.023674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73163 | 0 | 0.70795 | 0.023674 | 0 | 0 | 0 | 0 | 1.1102e-16 | 0 | 1.1102e-16 | 0 | 0 | 0.70795 | 0.023674 | 0 | 0 | 0 | 0.73163 | 0 | 0.73163 | 0 | 3738 | 125 | 0 | -1.1102e-16 |  | 0 | 0.70795 | 0.023674 | 0 | 0 | 0 | 0.73163 | 0 | 0 | [10 empty] | Oroville | BUTTE | 448 |  |  | Butte County of(100) |  |  | https://pge.sharepoint.com/sites/EDOSProjMgmt/EDOS%20Project%20Management/System%20Hardening%20Website%20Folder/System%20Hardening/Master%20KMZ%20File/02%20PM%20ONLY_FOR%20DOT%20HL/Region%202/SH/35329009.kmz | Link | https://pge.sharepoint.com/sites/EDOSProjMgmt/EDOS%20Project%20Management/System%20Hardening%20Website%20Folder/System%20Hardening/Master%20Geotechnical%20Science%20Report%20File/PM%20Only_For%20DOT/Region%202/SH/35329009.pdf | Link | 39.655 | -121.5839 |  | UG | MX |  | PSPS | ED.17-V340000000.STRU.POLE | 2022-03-21 | PSPS | CLARK ROAD 1102 | 103091102 | CLARK ROAD 110281296 | 0 | 0 | 0 | 0 | 0
35329010 | [6 empty] | CONS | srdy | SH | Base | NV | Region 2 - North East | 2.336 | 12334 | 2.336 | 12334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4.4409e-16 | 0 | -4.4409e-16 | 0 | 08W | 2023-05-05 |  | 2023-08-24 | Scoped |  |  |  |  | Completed |  | 2022-09-16 | 2022-09-16 | 2022-09-19 |  |  |  |  | Y | 2022-04-28 |  |  | Yes | 2022-04-28 | [6 empty] | 2022-12-22 | 2023-04-19 | Yes | SAP | 2023-07-28 | 2023-07-28 | 2023-07-28 | 2023-07-28 | 2023-07-26 | 2022-12-23 | 2023-07-26 | C | CNTRCT_EST | ENENG |  |  |  | 2023-02-13 | Yes | 2022-12-28 | 2023-02-13 |  | 2023-05-03 |  | 2023-07-14 | Full | 2023-09-11 | 2023-01-24 | 2023-05-05 |  | 2023-05-03 | 0 | 9 | 9 | Yes | Redesign review | 2023-08-23 | 2023-08-20 | 60 | 2023-09-26 |  | No |  | N |  | No | No | No | 0 | 2023-07-28 | [11 empty] | 3 | No |  |  |  | 2023-08-24 |  | 2023-08-24 | 2023-08-24 | Full |  | 2023-09-26 | 2023-08-24 | 2023-01-03 | 2023-05-04 | Completed Engineering | Released to Construction | Design Required;Other | Medium |  | 2024-11-04 |  |  | Full | 2023-02-06 | 2023-03-01 | 2023-09-17 | 2023-02-01 | 2023-02-06 | Permit Approved | Yes | 2024-10-15 |  | Encroachment | County of Butte |  | 2023-04-20 | 2023-05-01 17:00 | -4 | Yes | Contract | 2023-05-09 | 2023-02-01 10:08 | 2023-07-14 | 2024-03-31 | UNDERGROUND ELECTRIC CONSTRUCTION C | 2023-04-28 |  | Fully Executed PO | Contract | 2023-05-09 | 2023-02-01 10:08 | 2023-07-14 | 2024-03-31 | UNDERGROUND ELECTRIC CONSTRUCTION C | 2023-04-28 |  | Fully Executed PO |  |  |  | COMP | 2023-05-05 | 2023-05-20 | All Work |  | 2023-01-31 | 2024-03-31 | 2023-04-17 | 2023-04-28 16:51 | MOUNTAIN F ENTERPRISES INC | Fully Executed PO | 2700888681 | Y |  | 2023-08-24 |  | 2023-05-16 | 2023-05-16 | 2023-08-30 | 2023-08-22 | 2023-05-22 08:00 | Y | [13 empty] | N |  | 2023-05-12 | [6 empty] | 2023-05-25 |  |  | Yes | Complete | 2023-05-25 | 2023-09-22 | 2023-09-22 | 2023-05-25 | 2023-09-26 |  | 2023-09-30 | 2023-05-22 08:00 | 3240.5 | 0 | 12334 | 0 | Complete | 1 | 2023-09-23 | 2024-01-26 | 2024-01-26 | 23-0122733 | 2023-11-14 |  |  | 4950 | 0 | 2023-11-21 | 2024-01-26 | 2024-06-10 | 2024-06-14 | N |  | 2023-11-02 08:00 | Yes |  |  |  | 2024-01-26 | 2023-11-02 | Y | 2023 | 8489653 | 6259011.6 | 6259011.6 | 0 | 0 |  |  | 0 | -8489653 | 151995.1 | 73.72% | 0 | 2827 | 6261838.6 | 6261838.6 | 0 | 0 |  | 2075819.3 | 8337657.9 | 0 | 2679388.7829 | UG | Readiness | Construction | Closeout |  |  | 2.336 | 0 | 2.336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.336 | 0 | 2.336 | 0 | 0 | 0 | 0 | 0 | -4.4409e-16 | 0 | -4.4409e-16 | 0 | 0 | 2.336 | 0 | 0 | 0 | 0 | 2.336 | 0 | 2.336 | 0 | 12334 | 0 | 0 | 4.4409e-16 | 12/12/2023 | 0 | 2.336 | 0 | 0 | 0 | 0 | 2.336 | 0 | 0 | [10 empty] | Oroville | BUTTE | 473 |  |  | Butte County of(100), Del Oro Water Company(18) |  |  | https://pge.sharepoint.com/sites/EDOSProjMgmt/EDOS%20Project%20Management/System%20Hardening%20Website%20Folder/System%20Hardening/Master%20KMZ%20File/02%20PM%20ONLY_FOR%20DOT%20HL/Region%202/SH/35329010.kmz | Link | https://pge.sharepoint.com/sites/EDOSProjMgmt/EDOS%20Project%20Management/System%20Hardening%20Website%20Folder/System%20Hardening/Master%20Geotechnical%20Science%20Report%20File/PM%20Only_For%20DOT/Region%202/SH/35329010.pdf | Link | 39.6564 | -121.5838 |  | UG | MX |  | PSPS | ED.17-V340000000.STRU.POLE | 2022-03-21 | PSPS | CLARK ROAD 1102 | 103091102 | CLARK ROAD 110281296 | 0 | 0 | 0 | 0 | 0
35329011 | [6 empty] | CONS | srdy | SH | Base | NV | Region 2 - North East | 1.5634 | 8255 | 1.5634 | 8255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2.2204e-16 | 0 | -2.2204e-16 | 0 | 08W | 2023-03-28 |  | 2023-03-10 | Scoped |  |  |  |  | Completed |  | 2022-09-05 | 2022-09-05 | 2022-09-02 |  |  |  |  | Y | 2022-04-28 |  |  | Yes | 2022-04-28 | [6 empty] | 2023-01-11 | 2023-01-19 | Yes | SAP | 2023-01-20 | 2023-01-20 | 2023-01-20 | 2023-01-20 | 2023-01-20 | 2023-01-20 | 2023-03-14 |  | CNTRCT_EST | ENENG |  |  |  | 2023-03-10 | Yes | 2023-03-14 | 2023-03-10 |  | 2023-03-03 |  | 2023-03-10 | Full | 2023-03-06 | 2023-03-03 | 2023-03-03 |  | 2023-03-03 | 0 |  | 0 | No | Redesign review | 2023-06-29 | 2023-06-22 | 45 | 2023-03-06 |  | No |  | N |  | No | No | No | 0 | 2023-01-20 | [11 empty] | 3 | No |  |  |  | 2023-03-09 |  | 2023-03-09 | 2023-03-09 | Full |  | 2023-03-21 | 2023-03-09 | 2023-01-23 | 2023-03-09 | Completed Engineering | Released to Construction |  | Medium |  | 2024-09-09 | 2023-03-31 |  | Full | 2023-06-01 | 2023-02-23 | 2023-03-12 | 2023-01-26 | 2023-02-07 | Permit Approved | Yes | 2024-10-15 |  | Encroachment | County of Butte |  | 2023-03-10 | 2023-03-28 | 0 | Yes | Contract | 2023-03-21 | 2023-02-24 09:37 | 2023-06-14 | 2024-03-31 | UNDERGROUND ELECTRIC CONSTRUCTION C | 2023-03-08 |  | Fully Executed PO | Contract | 2023-03-21 | 2023-02-24 09:37 | 2023-06-14 | 2024-03-31 | UNDERGROUND ELECTRIC CONSTRUCTION C | 2023-03-08 |  | Fully Executed PO |  |  |  | COMP | 2023-03-28 | 2023-05-08 | All Work |  | 2023-02-08 | 2024-03-31 | 2023-02-28 | 2023-02-28 17:59 | MOUNTAIN F ENTERPRISES INC | Fully Executed PO | 2700870434 | Y |  | 2023-06-01 |  | 2023-04-10 | 2023-04-03 | 2023-04-15 | 2023-04-03 | 2023-05-22 | Y | [13 empty] | N |  | 2023-05-12 | [6 empty] | 2023-05-22 |  |  | Yes | Complete | 2023-05-22 | 2023-07-21 | 2023-07-21 | 2023-05-22 | 2023-07-25 |  |  | 2023-05-22 08:00 | 2000 | 0.5 | 8255 | 0 | Complete | -21 | 2023-06-30 | 2024-01-18 | 2024-01-18 | 23-0137298 | 2023-12-05 |  |  | 2160 | 11.25 | 2023-11-27 | 2024-01-18 | 2024-06-10 | 2024-06-06 | N |  | 2023-11-02 08:00 | Yes |  |  |  | 2024-01-18 | 2023-11-02 | Y | 2023 | 5388709 | 3352571.2 | 3352571.2 | 0 | 0 |  |  | 0 | -5388709 | 1277971.9 | 62.21% | 0 | 3819 | 3356390.2 | 3356390.2 | 0 | 0 |  | 754346.9 | 4110737.1 | 0 | 2144345.9644 | UG | Readiness | Construction | Closeout |  |  | 1.5634 | 0 | 1.5634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5634 | 0 | 1.5634 | 0 | 0 | 0 | 0 | 0 | -2.2204e-16 | 0 | -2.2204e-16 | 0 | 0 | 1.5634 | 0 | 0 | 0 | 0 | 1.5634 | 0 | 1.5634 | 0 | 8255 | 0 | 0 | 2.2204e-16 | 12/12/2023 | 0 | 1.397 | 0 | 0 | 0.16648 | 0 | 1.397 | 0.16648 | 2.7756e-17 | [10 empty] | Oroville | BUTTE | 616 |  |  | Butte County of(100), Del Oro Water Company(81) |  |  | https://pge.sharepoint.com/sites/EDOSProjMgmt/EDOS%20Project%20Management/System%20Hardening%20Website%20Folder/System%20Hardening/Master%20KMZ%20File/02%20PM%20ONLY_FOR%20DOT%20HL/Region%202/SH/35329011.kmz | Link | https://pge.sharepoint.com/sites/EDOSProjMgmt/EDOS%20Project%20Management/System%20Hardening%20Website%20Folder/System%20Hardening/Master%20Geotechnical%20Science%20Report%20File/PM%20Only_For%20DOT/Region%202/SH/35329011.pdf | Link | 39.6668 | -121.5824 |  | UG | MX |  | PSPS | ED.17-V340000000.STRU.POLE | 2022-03-21 | PSPS | CLARK ROAD 1102 | 103091102 | CLARK ROAD 110281296 | 0 | 0 | 0 | 0 | 0

## Report Sections
Section | Columns | Description
Totals | N-BQ | Quantifies planned feet/miles (UG, OH, Removal, and Total) and allocates to current year or future years. Note, if the project is completed in prior years, the yearly completed miles will appear in the QA/QC section.
Scoping | BV-BZ | Tracks high-level Scoping deliverables
Basemap | CA-CH | Part of Scoping, tracked in detail as input to Estimating
Estimating | CI-CX, CZ-DL | Tracks the project through the various Estimating stages
Joint Pole | DM-DQ | Tracks Joint Pole (third party telecoms) requirements
Land | DR-DY | Identifies and tracks any Land Rights dependencies
Easements | EA-EJ | Containts detailed data and tracking of private and public land easements
Caltrans | EK-FE | Tracks long-lead CalTrans dependency requirements if applicable
Railroad | FF-FI | Identifies and tracks any Railroad dependencies
Environmental | FJ-JB | Identifies and tracks any Environmenal Permit dependencies from state and federal agencies
Permits | GC-GN | Identifies and tracks any Encroachment Permit dependencies from local agencies and juristictions
Business Case | GO-GR | Summarizes key Business Case dates and completion
Contract Planning | GS-HJ | Also referred to as Resource Planning secion. Identifies resource type, resource names, and initial committed construction dates
Release | HK-HP | Key gate check to ensure all preceding dependecies ( to the left) are complete prior to Releasing to Construction
Veg | HR-IJ | Tracks Vegetation scope and work prior to Civil/Electrical work
Portfolio Target & Planned Variances | IK-IX | Starting in 2024, critical planned project milestones are stored and tracked for change control purposes
Construction | IY-KV | Extensive schedule tracking of Civil Construction, Electric Construction, and Energization dates
Financial | KW-LX | Containts project-level financial data including authorized amounts, spend-to-date, and Estimate-At-Completion (EAC)
QA/QC | LY-NW | Stores miles achieved in a given year during the key post-construction milestones of QA Pass (Fire Risk Safety Audit) and IA (Internal Audit) Pass
Project Stakeholders | OH-OP | Names of key stakeholders outside of cross-functional project teams
Project Info | OQ-PL | Primarily contains geospatial data like city, county, and Lat/Long
Circuit Info | PM-PT | Contains Circuit and Circuit Protection Zone (CPZ) information associated with the project